## Details (hidden)
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Legend title is in cell I1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | BUILD PLAN | [15 empty] | Legend:
Enter Company Name in cell B2. A legend is in cells I2 through AC2. | P. IMES Corp | [15 empty] | On Track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell F3 or allow the sample formula to find the smallest date value from the Gantt Data table. Project Start Date: label is in cell D3. | as of Aug. 29, 2019 | [6 empty] | 2019-08-26
A Scrolling Increment is in cell F4. Months for the dates in row 5 are displayed starting in cells I4 through cell BL4. Do not modify these cells. They are auto updated based on the project start date in cell F3. | [7 empty] | 0 | [8 empty] | August | [6 empty] | September | [34 empty] | October
Cells I5 through BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated. Do not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2019-08-26 to 2019-10-20
A scrollbar is in cells I6 through BL6. The increment for paging through the data is defined as 2 pages at a time and can be configured in the settings for the control bar. To jump forward or backward in the timeline, enter a value of 0 or higher in cell F4. A value of 0 takes you to the beginning of the chart. | [12 empty] | PPIC | MFG
This row contains headers for the project schedule that follows below them. Navigate from B7 through BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues through cell BL7. All project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table. | PROJECT | PROJECT PN | PROJECT SAP PN | PROJECT DESCRIPTION | PLANNER | PROJECT NO | BUILD QTY | START BUILD DATE | TARGET COMPLETION | ACTUAL COMPLETION | TARGET SHIP DATE | STATUS | MATERIAL COMPLETION | BUILD STATUS | REMARKS | No. Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | OLB | 100006503 | LFCH-OB-100006503 | DELTA Test Handling Equipment Handler Machine Equipment | Diana Azarcon | OLB#24 | 1 | 2019-06-03 | 2019-06-18 |  | 2019-06-17 | Milestone | 100% | 100% | Push out from June 17 to June 18 due to 1946214101; Completed | 15
| OLB | 100006503 | LFCH-OB-100006503 | DELTA Test Handling Equipment Handler Machine Equipment | Diana Azarcon | OLB#25 | 1 | 2019-06-14 | 2019-06-27 | 2019-07-29 | 2019-07-29 | Milestone | 100% | 100% | Delayed shipment from June 28 to June 29 due to Upper and Enclosure Frame Completed | 14
| OLB | 100006503 | LFCH-OB-100006503 | DELTA Test Handling Equipment Handler Machine Equipment | Diana Azarcon | OLB#26 | 1 | 2019-06-14 | 2019-07-03 | 2019-07-04 | 2019-07-04 | Milestone | 100% | 100% | Delayed shipment from June 28 to July 4 due to runner block HIWIN parts and KVM switch completed | 20
| OLB | 100006503 | LFCH-OB-100006503 | DELTA Test Handling Equipment Handler Machine Equipment | Diana Azarcon | OLB#27 | 1 | 2019-08-26 | 2019-09-08 |  | 2019-09-20 | On Track | 98% | 0% | On going production and materials expediting | 14
| JLP | 8337800001 | LFCH-JLP-8337800001 | JLP Gen 3, Main Assembly (8337800001) | Jo-Ann Bintulan | JLP#481-485 | 5 | 2019-06-03 | 2019-06-12 | 2019-06-12 | 2019-06-13 | Milestone | 100% | 100% | Completed | 10
| JLP | 8337800001 | LFCH-JLP-8337800001 | JLP Gen 3, Main Assembly (8337800001) | Jo-Ann Bintulan | JLP#486-490 | 5 | 2019-06-10 | 2019-06-19 | 2019-06-20 | 2019-06-20 | Milestone | 100% | 100% | Completed | 10
| JLP | 8337800001 | LFCH-JLP-8337800001 | JLP Gen 3, Main Assembly (8337800001) | Jo-Ann Bintulan | JLP#491-495 | 5 | 2019-07-01 | 2019-07-10 |  | 2019-07-11 | Milestone | 100% | 100% | Lacking part 1977725501 from Quantronic ETA 7/15- received 7/16; Affected starting JLP#490 and Flipper; borrowed 4pcs at XTA to complete JLP 491-493 Complete Parts as of 7/16 | 10
| JLP | 8337800001 | LFCH-JLP-8337800001 | JLP Gen 3, Main Assembly (8337800001) | Jo-Ann Bintulan | JLP#496-500 | 5 | 2019-07-08 | 2019-07-17 |  | 2019-07-18 | Milestone | 100% | 90% | Lacking part 1977725501 from Quantronic received 7/16 Additional lacking parts due to wrong part 3604200 ETA 7/17 | 10
| JLP | 8337800001 | LFCH-JLP-8337800001 | JLP Gen 3, Main Assembly (8337800001) | Jo-Ann Bintulan | JLP#501-505 | 5 | 2019-07-29 | 2019-08-07 | 2019-08-07 | 2019-08-08 | Milestone | 100% | 100% | Waiting for 3604165 from Kaman ETA 8/14 received | 10
| JLP | 8337800001 | LFCH-JLP-8337800001 | JLP Gen 3, Main Assembly (8337800001) | Jo-Ann Bintulan | JLP#506-510 | 5 | 2019-08-05 | 2019-08-14 |  | TBA | Milestone | 100% | 100% | Waiting for lacking parts: 1503932 from Allied ETA 8/17 received 8/16 3604165 from Kaman ETA 8/14 received 3401623 from United Bearing ETA 8/9 received | 10
| JLP | 8337800001 | LFCH-JLP-8337800001 | JLP Gen 3, Main Assembly (8337800001) | Jo-Ann Bintulan | JLP#511-515 | 5 | 2019-08-19 | 2019-08-28 |  | TBA | Med Risk | 98.21% | 0% | Waiting for 18 lacking parts Parts issued to production WK 33 | 10
| MTP | 8332104901 | LFCH-JLP-MTPF4901 | Kit, Manual Tray Platf, JLP G2 (8332104901) | Jo-Ann Bintulan | MTP#181-190 | 10 | 2019-06-03 | 2019-06-12 | 2019-06-12 | 2019-06-13 | Milestone | 100% | 100% | Completed | 10
| MTP | 8332104901 | LFCH-JLP-MTPF4901 | Kit, Manual Tray Platf, JLP G2 (8332104901) | Jo-Ann Bintulan | MTP#191-200 | 10 | 2019-06-24 | 2019-07-07 | 2019-07-07 | TBA | Milestone | 100% | 100% | Completed | 14
| MTP | 8332104901 | LFCH-JLP-MTPF4901 | Kit, Manual Tray Platf, JLP G2 (8332104901) | Jo-Ann Bintulan | MTP#201-205 | 5 | 2019-07-08 | 2019-07-21 |  | TBA | Milestone | 100% | 100% | Completed | 14
| MTP | 8332104901 | LFCH-JLP-MTPF4901 | Kit, Manual Tray Platf, JLP G2 (8332104901) | Jo-Ann Bintulan | MTP#206-209 | 5 | 2019-08-26 | 2019-09-08 |  | TBA | Milestone | 100% | 100% | Completed | 14 | bar: M to S
| IONIZER | 8335499901 | LFCH-JLP-8335499901 | Kit, JLP Air Knife Option (8335499901) | Jo-Ann Bintulan | ION#66-70 | 5 | 2019-06-03 | 2019-06-12 | 2019-06-12 | 2019-06-27 | Milestone | 100% | 100% | Completed | 10
| IONIZER | 8335499901 | LFCH-JLP-8335499901 | Kit, JLP Air Knife Option (8335499901) | Jo-Ann Bintulan | ION#71-75 | 5 | 2019-06-24 | 2019-07-03 | 2019-07-03 | TBA | Milestone | 100% | 100% | Completed | 10
| IONIZER | 8335499901 | LFCH-JLP-8335499901 | Kit, JLP Air Knife Option (8335499901) | Jo-Ann Bintulan | ION# | 1 | 2019-08-19 | 2019-08-28 |  | TBA | Milestone | 100% | 0% | lacking parts | 10 | bar: M to W
| FLIPPER | 8333454901 | LFCH-JLP-8333454901 | Kit Tray Flip Mechanism (8333454901) | Jo-Ann Bintulan | FLIP#33-35 | 3 | 2019-07-15 | 2019-07-24 |  | TBA | Milestone | 100% | 100% |  | 10
| FLIPPER | 8333454901 | LFCH-JLP-8333454901 | Kit Tray Flip Mechanism (8333454901) | Jo-Ann Bintulan | FLIP#39-40 | 2 | 2019-09-02 | 2019-09-11 |  | TBA | Milestone | 97.69% | 0% | waiting for 1 PN at MRB due to oversized thread for rework | 10 | bar: M to W
| JTP | 8330201001 | LFCH-JT-8330201001 | DELTA Test Handling Equipment Handler Machine Equipment | Jo-Ann Bintulan | JTP#10 | 1 | 2019-05-27 | 2019-06-09 | 2019-06-10 | 2019-06-10 | Milestone | 100% | 100% | Completed | 14
| JTP | 8330201001 | LFCH-JT-8330201001 | DELTA Test Handling Equipment Handler Machine Equipment | Jo-Ann Bintulan | JTP#11 | 1 | 2019-09-06 | 2019-09-19 |  | 2019-09-25 | Goal | 83% | 0% | On going parts ordering | 14 | F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2
| XT | 8334633901 | LFCH-EC-8334633901 | X1-X16 TS No Contactor (D2006066) (8334633901) | Jo-Ann Bintulan | XT#60 | 1 | 2019-07-01 | 2019-07-14 |  | 2019-07-22 | Milestone | 100% | 100% | with ECO on 8337322501 ETA 7/2 received; Shipment is pushed out to July 22 ready to ship as of 7/9 TO BE SHIPPED 7/18 | 14
| XT | 8334633901 | LFCH-EC-8334633901 | X1-X16 TS No Contactor (D2006066) (8334633901) | Jo-Ann Bintulan | XT#61 | 1 | 2019-07-01 | 2019-07-14 |  | TBA | Milestone | 100% | 100% | Waiting the upgraded 8337322501 ETA 7/2 received; Awaiting 8337393101 for rework to Alpha ETA 7/11 Delay due additional lacking part 3603123 due to quality issue ETA 7/18 | 14
| XT | 8334633901 | LFCH-EC-8334633901 | X1-X16 TS No Contactor (D2006066) (8334633901) | Jo-Ann Bintulan | XT#62 | 1 | 2019-07-01 | 2019-07-14 |  | TBA | Milestone | 100% | 100% | Waiting the upgraded 8337322501 ETA 7/2 received; Awaiting 8337393101 for rework to Alpha ETA 7/11 Delay due additional lacking part 3603123 due to quality issue ETA 7/18 | 14
| XT | 8334633901 | LFCH-EC-8334633901 | X1-X16 TS No Contactor (D2006066) (8334633901) | Jo-Ann Bintulan | XT#63 & XT#64 | 2 | 2019-07-22 | 2019-08-05 |  | TBA | Milestone | 100% | 100% | IT 7/17 request urgent issuance from WH | 14
| XT | 8334633901 | LFCH-EC-8334633901 | X1-X16 TS No Contactor (D2006066) (8334633901) | Jo-Ann Bintulan | XT#65 & XT#66 | 2 | 2019-09-02 | 2019-09-16 |  | TBA | Goal | 98.4% | 0% | Push out plan due to ECO; waiting for lacking parts | 14
| XT | 8334633901 | LFCH-EC-8334633901 | X1-X16 TS No Contactor (D2006066) (8334633901) | Jo-Ann Bintulan | XT#67 & XT#68 | 1 | 2019-09-09 | 2019-09-22 |  | TBA | Goal | 96.6% | 0% |  | 14 | M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2
| XTA | 100004565 | LFCH-EC-100004565 | XTA X1-X16 TS No Contactor (100004565) | Jo-Ann Bintulan | XTA 21 - 25 | 5 | 2019-09-09 | 2019-09-22 |  | TBA | Goal | 99% | 0% |  | 14 | M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2
| PNP T | 8307700002 | LFCH-MX-8307700002 | PNP Assy, X8-DPH Transfer U (8307700002) | Flor Ancheta | 193 & 194 | 2 | 2019-06-24 | 2019-07-03 | 2019-06-29 | TBA | Milestone | 100% | 100% | Completed | 10
| PNP I/O | 8307700001 | LFCH-MX-8307700001 | PNP Assy, X8-DPH Input/Output U (8307700001) | Flor Ancheta | 193 & 194 | 4 | 2019-06-24 | 2019-07-03 | 2019-06-29 | TBA | Milestone | 100% | 100% | Completed | 10
| PNP T | 8307700002 | LFCH-MX-8307700002 | PNP Assy, X8-DPH Transfer U (8307700002) | Flor Ancheta | 195 & 196 | 2 | 2019-07-01 | 2019-07-10 |  | TBA | Milestone | 100% | 100% | Completed | 10
| PNP I/O | 8307700001 | LFCH-MX-8307700001 | PNP Assy, X8-DPH Input/Output U (8307700001) | Flor Ancheta | 195 & 196 | 4 | 2019-07-01 | 2019-07-10 |  | TBA | Milestone | 100% | 100% | Completed | 10
| PNP T | 8307700002 | LFCH-MX-8307700002 | PNP Assy, X8-DPH Transfer U (8307700002) | Flor Ancheta | 197 - 201 | 5 | 2019-07-08 | 2019-07-17 |  | TBA | Milestone | 100% | 100% | With 13 lacking PNs worst ETA 7/19 | 10
| PNP I/O | 8307700001 | LFCH-MX-8307700001 | PNP Assy, X8-DPH Input/Output U (8307700001) | Flor Ancheta | 197 - 201 | 10 | 2019-07-08 | 2019-07-17 |  | TBA | Milestone | 100% | 100% | With 13 lacking PNs worst ETA 7/19 | 10
| PNP T | 8307700002 | LFCH-MX-8307700002 | PNP Assy, X8-DPH Transfer U (8307700002) | Flor Ancheta | 204-206 | 3 | 2019-08-05 | 2019-08-14 |  | TBA | Milestone | 100% | 100% | Completed | 10
| PNP I/O | 8307700001 | LFCH-MX-8307700001 | PNP Assy, X8-DPH Input/Output U (8307700001) | Flor Ancheta | 202-205 | 6 | 2019-08-05 | 2019-08-14 |  | TBA | Milestone | 100% | 100% | Completed | 10
| PNP T | 8307700002 | LFCH-MX-8307700002 | PNP Assy, X8-DPH Transfer U (8307700002) | Flor Ancheta | 207-211 | 5 | 2019-09-02 | 2019-09-11 |  | TBA | Goal | 75.8% | 0% | Resume production on WK 36 | 10 | M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2
| PNP I/O | 8307700001 | LFCH-MX-8307700001 | PNP Assy, X8-DPH Input/Output U (8307700001) | Flor Ancheta | 207-211 | 10 | 2019-09-02 | 2019-09-11 |  | TBA | Goal | 75.8% | 0% | Resume production on WK 36 | 10 | M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2
| PYRAMID | 8307700001 | LFCH-PYIO-1975022001 | PNP Assy, X8-DPH Input/Output U (8307700001) | Flor Ancheta |  | 1 |  | 1900-01-08 |  | TBA | Goal | 85% | 0% | Parts for issuance and lacking parts for PR/PO | 10
This is an empty row
This row marks the end of the Gantt milestone data. DO NOT enter anything in this row. To add more items, insert new rows above this one. | To add more data, Insert new rows ABOVE this one

## MASTER SCHEDULE
ATS MASTER SCHEDULE |  |  |  | WITH PO
CTRL # MS 2023_0074 |  |  |  | SHIPPED
As of: | 2023-07-10 |  |  | FORECAST
WK 27
| PF/FG | PF/WIP | MK | MONTH | DECEMBER |  |  |  | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  |  | DECEMBER
PRODUCT |  |  |  | WW | WK 50 | WK 51 | WK 52 | WK 53 | WK 1 | WK 2 | WK 3 | WK 4 | WK 5 | WK 6 | WK 7 | WK 8 | WK 9 | WK 10 | WK 11 | WK 12 | WK 13 | WK 14 | WK 15 | WK 16 | WK 17 | WK 18 | WK 19 | WK 20 | WK 21 | WK 22 | WK 23 | WK 24 | WK 25 | WK 26 | WK 27 | WK 28 | WK 29 | WK 30 | WK 31 | WK 32 | WK 33 | WK 34 | WK 35 | WK 36 | WK 37 | WK 38 | WK 39 | WK 40 | WK 41 | WK 42 | WK 44 | WK 44 | WK 45 | WK 46 | WK 47 | WK 48 | WK 49 | WK 50 | WK 51 | WK 52
CONTRACT |  |  |  | Start Build Plan | time axis 2022-12-04 to 2023-12-24
COMPLIANCE |  |  |  | End Build Date | time axis 2022-12-10 to 2023-12-30
JLP | 3 | 5 | 0 | Prod Build Qty | 3 | 2 |  |  | 3 | 2 | 2 | 3 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2
|  |  |  | JLP No | 1062 | 1064 | 1064 | 1064 | 1067 | 1069 | 1071 | 1074 | 1076 | 1078 | 1078 | 1080 | 1082 | 1084 | 1086 | 1088 | 1090 | 1090 | 1092 | 1094 | 1096 | 1096 | 1096 | 1096 | 1096 | 1096 | 1097 | 1098 | 1099 | 1100 | 1101 | 1103 | 1105 | 1107 | 1108 | 1109 | 1110 | 1111 | 1112 | 1114 | 1116 | 1118 | 1120 | 1122 | 1124 | 1126 | 1128 | 1128 | 1130 | 1132 | 1134 | 1136 | 1138 | 1140 | 1140 | 1140
Available sets
8 |  |  |  | Shipment Qty | 2022-12-17: 9; 2022-12-24: 2; 2022-12-31: 2; 2023-01-07: 2; 2023-01-14: 4; 2023-01-21: 2; 2023-01-28: 4; 2023-02-11: 2; 2023-03-04: 2; 2023-03-11: 4; 2023-03-18: 3; 2023-03-25: 4; 2023-04-01: 1; 2023-04-08: 2; 2023-04-15: 2; 2023-04-22: 3; 2023-07-15: 2; 2023-08-19: 2; 2023-08-26: 1; 2023-09-02: 2; 2023-09-23: 1; 2023-10-07: 2; 2023-10-28: 4; 2023-11-04: 8; 2023-11-11: 6; 2023-11-18: 6; 2023-11-25: 4; 2023-12-09: 2; 2023-12-16: 2
11 |  |  |  | BOH/EOH | 15 | 9 | 10 | 8 | 10 | 8 | 8 | 7 | 9 | 9 | 9 | 11 | 11 | 9 | 8 | 6 | 7 | 5 | 5 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 8 | 9 | 10 | 11 | 11 | 13 | 15 | 16 | 17 | 16 | 16 | 15 | 17 | 19 | 20 | 22 | 22 | 24 | 26 | 24 | 16 | 12 | 8 | 6 | 8 | 8 | 8 | 8 | 8
|  |  |  | Actual Batch Output | 2022-12-10: 1056; 2022-12-17: 1059; 2023-01-07: 1064; 2023-01-14: 1065; 2023-01-21: 1067; 2023-01-28: 1071; 2023-02-04: 1071; 2023-02-11: 1073; 2023-02-18: 1075; 2023-02-25: 1077; 2023-03-04: 1080; 2023-03-11: 1080; 2023-03-18: 1083; 2023-03-25: 1084; 2023-04-01: 1087; 2023-04-08: 1088; 2023-04-15: 1089; 2023-04-22: 1092; 2023-04-29: 1092; 2023-05-06: 1095; 2023-05-13: 1096; 2023-05-20: 1096; 2023-05-27: 1096; 2023-06-10: 1098; 2023-06-17: 1098; 2023-06-24: 1101; 2023-07-01: 1101; 2023-07-08: 1101
|  |  |  | BUILD PLAN DELAY | 2022-12-10: -6; 2022-12-17: -6; 2023-01-07: -3; 2023-01-14: -4; 2023-01-21: -4; 2023-01-28: -3; 2023-02-04: -5; 2023-02-11: -5; 2023-02-18: -3; 2023-02-25: -3; 2023-03-04: -2; 2023-03-11: -4; 2023-03-18: -3; 2023-03-25: -4; 2023-04-01: -3; 2023-04-08: -2; 2023-04-15: -3; 2023-04-22: -2; 2023-04-29: -4; 2023-05-06: -1; 2023-05-13: 0; 2023-05-20: 0; 2023-05-27: 0; 2023-06-10: 1; 2023-06-17: 0; 2023-06-24: 2; 2023-07-01: 1; 2023-07-08: 0
PRODUCT | PF/FG | PF/WIP | MK/LLI | WW | WK 50 | WK 51 | WK 52 | WK 53 | WK 1 | WK 2 | WK 3 | WK 4 | WK 5 | WK 6 | WK 7 | WK 8 | WK 9 | WK 10 | WK 11 | WK 12 | WK 13 | WK 14 | WK 15 | WK 16 | WK 17 | WK 18 | WK 19 | WK 20 | WK 21 | WK 22 | WK 23 | WK 24 | WK 25 | WK 26 | WK 27 | WK 28 | WK 29 | WK 30 | WK 31 | WK 32 | WK 33 | WK 34 | WK 35 | WK 36 | WK 37 | WK 38 | WK 39 | WK 40 | WK 41 | WK 42 | WK 44 | WK 44 | WK 45 | WK 46 | WK 47 | WK 48 | WK 49 | WK 50 | WK 51 | WK 52
CONTRACT |  |  |  | Start Build Plan | time axis 2022-12-04 to 2023-12-24
COMPLIANCE |  |  |  | End Build Date | time axis 2022-12-10 to 2023-12-30
FLIPPER | 0 | 0 | 10 | Prod Build Qty | 2022-12-10: 3; 2022-12-17: 2; 2022-12-24: 1; 2023-01-07: 1; 2023-01-14: 1; 2023-03-11: 1; 2023-03-18: 1; 2023-03-25: 1; 2023-04-01: 1; 2023-05-27: 1; 2023-06-03: 1; 2023-08-19: 1; 2023-09-02: 1; 2023-09-16: 1; 2023-10-14: 1; 2023-10-28: 1; 2023-11-04: 1; 2023-11-18: 1; 2023-12-02: 1; 2023-12-09: 1; 2023-12-16: 1
|  |  |  | Flipper No | 148 | 150 | 151 | 151 | 152 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 153 | 154 | 155 | 156 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 158 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 160 | 160 | 161 | 161 | 162 | 162 | 162 | 162 | 163 | 163 | 164 | 165 | 165 | 166 | 166 | 167 | 168 | 169 | 169 | 169
10 |  |  |  | Shipment Qty | 2022-12-17: 2; 2023-01-14: 2; 2023-01-28: 2; 2023-08-26: 1; 2023-09-02: 2; 2023-09-23: 1; 2023-11-04: 2; 2023-12-09: 2; 2023-12-16: 2
11 |  |  |  | BOH/EOH | 6 | 6 | 7 | 7 | 7 | 6 | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 6 | 7 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 11 | 10 | 10 | 11 | 10 | 10 | 10 | 11 | 11 | 12 | 11 | 11 | 12 | 12 | 13 | 11 | 10 | 10 | 10
|  |  |  | Actual Batch Output | 2022-12-10: 145; 2022-12-17: 145; 2023-01-07: 150; 2023-01-14: 151; 2023-01-21: 151; 2023-01-28: 151; 2023-02-04: 154; 2023-02-11: 154; 2023-02-18: 154; 2023-02-25: 154; 2023-03-04: 154; 2023-03-11: 157; 2023-03-18: 157; 2023-03-25: 157; 2023-04-01: 157; 2023-04-08: 157; 2023-04-15: 157; 2023-04-22: 157; 2023-04-29: 157; 2023-05-06: 157; 2023-05-13: 157; 2023-05-20: 157; 2023-05-27: 159; 2023-06-10: 159; 2023-06-17: 159; 2023-06-24: 159; 2023-07-01: 159; 2023-07-08: 159
|  |  |  | BUILD PLAN DELAY | 2022-12-10: -3; 2022-12-17: -5; 2023-01-07: -2; 2023-01-14: -2; 2023-01-21: -2; 2023-01-28: -2; 2023-02-04: 1; 2023-02-11: 1; 2023-02-18: 1; 2023-02-25: 1; 2023-03-04: 1; 2023-03-11: 3; 2023-03-18: 2; 2023-03-25: 1; 2023-04-01: 0; 2023-04-08: 0; 2023-04-15: 0; 2023-04-22: 0; 2023-04-29: 0; 2023-05-06: 0; 2023-05-13: 0; 2023-05-20: 0; 2023-05-27: 1; 2023-06-10: 0; 2023-06-17: 0; 2023-06-24: 0; 2023-07-01: 0; 2023-07-08: 0
PRODUCT | PF/FG | PF/WIP | MK/LLI | WW | WK 50 | WK 51 | WK 52 | WK 53 | WK 1 | WK 2 | WK 3 | WK 4 | WK 5 | WK 6 | WK 7 | WK 8 | WK 9 | WK 10 | WK 11 | WK 12 | WK 13 | WK 14 | WK 15 | WK 16 | WK 17 | WK 18 | WK 19 | WK 20 | WK 21 | WK 22 | WK 23 | WK 24 | WK 25 | WK 26 | WK 27 | WK 28 | WK 29 | WK 30 | WK 31 | WK 32 | WK 33 | WK 34 | WK 35 | WK 36 | WK 37 | WK 38 | WK 39 | WK 40 | WK 41 | WK 42 | WK 44 | WK 44 | WK 45 | WK 46 | WK 47 | WK 48 | WK 49 | WK 50 | WK 51 | WK 52
CONTRACT |  |  |  | Start Build Plan | time axis 2022-12-04 to 2023-12-24
COMPLIANCE |  |  |  | End Build Date | time axis 2022-12-10 to 2023-12-30
MTP | 3 | 5 | 0 | Prod Build Qty | 2 | 2 | 2 |  |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 2 |  | 2 | 2 | 2 | 1 | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1
|  |  |  | MTP Number | 780 | 782 | 784 | 784 | 784 | 786 | 788 | 788 | 788 | 790 | 792 | 794 | 796 | 797 | 799 | 801 | 803 | 803 | 805 | 807 | 809 | 810 | 810 | 810 | 810 | 810 | 810 | 810 | 810 | 810 | 811 | 812 | 813 | 814 | 815 | 816 | 817 | 818 | 819 | 821 | 823 | 825 | 827 | 829 | 831 | 833 | 835 | 837 | 839 | 841 | 843 | 844 | 844 | 844 | 844 | 844
8 |  |  |  | Shipment Qty | 2022-12-17: 8; 2022-12-24: 2; 2023-01-07: 2; 2023-01-14: 4; 2023-01-21: 2; 2023-01-28: 1; 2023-02-11: 2; 2023-03-04: 2; 2023-03-11: 4; 2023-03-18: 3; 2023-03-25: 4; 2023-04-01: 1; 2023-04-08: 2; 2023-04-15: 2; 2023-04-22: 3; 2023-06-24: 2; 2023-07-15: 2; 2023-08-19: 2; 2023-10-07: 2; 2023-10-28: 6; 2023-11-04: 4; 2023-11-11: 6; 2023-11-18: 4; 2023-11-25: 4; 2023-12-09: 1; 2023-12-16: 1
7 |  |  |  | BOH/EOH | 19 | 13 | 13 | 13 | 11 | 9 | 9 | 8 | 8 | 8 | 10 | 12 | 12 | 9 | 8 | 6 | 7 | 6 | 6 | 5 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 7 | 6 | 7 | 8 | 9 | 10 | 9 | 10 | 11 | 13 | 15 | 17 | 19 | 19 | 21 | 23 | 19 | 17 | 13 | 11 | 9 | 10 | 9 | 8 | 8 | 8
|  |  |  | Actual Batch Output | 2022-12-10: 776; 2022-12-17: 776; 2023-01-07: 780; 2023-01-14: 786; 2023-01-21: 786; 2023-01-28: 786; 2023-02-04: 788; 2023-02-11: 792; 2023-02-18: 794; 2023-02-25: 794; 2023-03-04: 794; 2023-03-11: 796; 2023-03-18: 800; 2023-03-25: 800; 2023-04-01: 801; 2023-04-08: 803; 2023-04-15: 806; 2023-04-22: 807; 2023-04-29: 810; 2023-05-06: 810; 2023-05-13: 811; 2023-05-20: 811; 2023-05-27: 811; 2023-06-10: 811; 2023-06-17: 811; 2023-06-24: 811; 2023-07-01: 811; 2023-07-08: 811
|  |  |  | BUILD PLAN DELAY | 2022-12-10: -4; 2022-12-17: -6; 2023-01-07: -4; 2023-01-14: 0; 2023-01-21: -2; 2023-01-28: -2; 2023-02-04: 0; 2023-02-11: 2; 2023-02-18: 2; 2023-02-25: 0; 2023-03-04: -2; 2023-03-11: -1; 2023-03-18: 1; 2023-03-25: -1; 2023-04-01: -2; 2023-04-08: 0; 2023-04-15: 1; 2023-04-22: 0; 2023-04-29: 1; 2023-05-06: 0; 2023-05-13: 1; 2023-05-20: 1; 2023-05-27: 1; 2023-06-10: 1; 2023-06-17: 1; 2023-06-24: 1; 2023-07-01: 1; 2023-07-08: 0
PRODUCT | PF/FG | PF/WIP | MK/LLI | WW | WK 50 | WK 51 | WK 52 | WK 53 | WK 1 | WK 2 | WK 3 | WK 4 | WK 5 | WK 6 | WK 7 | WK 8 | WK 9 | WK 10 | WK 11 | WK 12 | WK 13 | WK 14 | WK 15 | WK 16 | WK 17 | WK 18 | WK 19 | WK 20 | WK 21 | WK 22 | WK 23 | WK 24 | WK 25 | WK 26 | WK 27 | WK 28 | WK 29 | WK 30 | WK 31 | WK 32 | WK 33 | WK 34 | WK 35 | WK 36 | WK 37 | WK 38 | WK 39 | WK 40 | WK 41 | WK 42 | WK 44 | WK 44 | WK 45 | WK 46 | WK 47 | WK 48 | WK 49 | WK 50 | WK 51 | WK 52
CONTRACT |  |  |  | Start Build Plan | time axis 2022-12-04 to 2023-12-24
COMPLIANCE |  |  |  | End Build Date | time axis 2022-12-10 to 2023-12-30
IONIZER | 3 | 5 | 0 | Prod Build Qty | 2022-12-24: 2; 2023-01-07: 2; 2023-01-14: 2; 2023-01-21: 1; 2023-01-28: 1; 2023-02-04: 1; 2023-02-11: 1; 2023-02-25: 1; 2023-03-11: 1; 2023-03-25: 1; 2023-04-01: 1; 2023-04-15: 1; 2023-04-29: 1; 2023-07-15: 1; 2023-07-22: 1; 2023-08-12: 1; 2023-09-02: 1; 2023-09-16: 1; 2023-10-07: 1; 2023-10-14: 1; 2023-10-21: 1; 2023-10-28: 1; 2023-11-04: 1; 2023-11-11: 1; 2023-11-18: 1; 2023-11-25: 1; 2023-12-02: 1
|  |  |  | Ionizer No | 333 | 333 | 335 | 335 | 337 | 339 | 340 | 341 | 342 | 343 | 343 | 344 | 344 | 345 | 345 | 346 | 347 | 347 | 348 | 348 | 349 | 349 | 349 | 349 | 349 | 349 | 349 | 349 | 349 | 349 | 349 | 350 | 351 | 351 | 351 | 352 | 352 | 352 | 353 | 353 | 354 | 354 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 363 | 363 | 363 | 363
8 |  |  |  | Shipment Qty | 2022-12-17: 4; 2022-12-24: 1; 2023-01-07: 1; 2023-01-14: 2; 2023-01-21: 1; 2023-01-28: 1; 2023-02-11: 1; 2023-03-04: 1; 2023-03-11: 2; 2023-03-18: 1; 2023-03-25: 2; 2023-04-08: 2; 2023-04-15: 1; 2023-06-24: 2; 2023-08-19: 1; 2023-09-02: 1; 2023-10-07: 1; 2023-10-28: 3; 2023-11-04: 3; 2023-12-09: 1; 2023-12-16: 1
6 |  |  |  | BOH/EOH | 13 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 11 | 10 | 9 | 8 | 9 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 6 | 7 | 8 | 8 | 8 | 9 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 10 | 11 | 9 | 7 | 8 | 9 | 10 | 10 | 9 | 8 | 8 | 8
|  |  |  | Actual Batch Output | 2022-12-10: 334; 2022-12-17: 334; 2023-01-07: 334; 2023-01-14: 334; 2023-01-21: 341; 2023-01-28: 342; 2023-02-04: 342; 2023-02-11: 342; 2023-02-18: 342; 2023-02-25: 342; 2023-03-04: 342; 2023-03-11: 346; 2023-03-18: 347; 2023-03-25: 347; 2023-04-01: 347; 2023-04-08: 347; 2023-04-15: 347; 2023-04-22: 348; 2023-04-29: 348; 2023-05-06: 348; 2023-05-13: 349; 2023-05-20: 349; 2023-05-27: 349; 2023-06-10: 349; 2023-06-17: 349; 2023-06-24: 349; 2023-07-01: 349; 2023-07-08: 349
|  |  |  | BUILD PLAN DELAY | 2022-12-10: 1; 2022-12-17: 1; 2023-01-07: -3; 2023-01-14: -5; 2023-01-21: 1; 2023-01-28: 1; 2023-02-04: 0; 2023-02-11: -1; 2023-02-18: -1; 2023-02-25: -2; 2023-03-04: -2; 2023-03-11: 1; 2023-03-18: 2; 2023-03-25: 1; 2023-04-01: 0; 2023-04-08: 0; 2023-04-15: -1; 2023-04-22: 0; 2023-04-29: -1; 2023-05-06: -1; 2023-05-13: 0; 2023-05-20: 0; 2023-05-27: 0; 2023-06-10: 0; 2023-06-17: 0; 2023-06-24: 0; 2023-07-01: 0; 2023-07-08: 0
PRODUCT | PF/FG | PF/WIP | MK/LLI | WW | WK 50 | WK 51 | WK 52 | WK 53 | WK 1 | WK 2 | WK 3 | WK 4 | WK 5 | WK 6 | WK 7 | WK 8 | WK 9 | WK 10 | WK 11 | WK 12 | WK 13 | WK 14 | WK 15 | WK 16 | WK 17 | WK 18 | WK 19 | WK 20 | WK 21 | WK 22 | WK 23 | WK 24 | WK 25 | WK 26 | WK 27 | WK 28 | WK 29 | WK 30 | WK 31 | WK 32 | WK 33 | WK 34 | WK 35 | WK 36 | WK 37 | WK 38 | WK 39 | WK 40 | WK 41 | WK 42 | WK 44 | WK 44 | WK 45 | WK 46 | WK 47 | WK 48 | WK 49 | WK 50 | WK 51 | WK 52
CONTRACT |  |  |  | Start Build Plan | time axis 2022-12-04 to 2023-12-24
COMPLIANCE |  |  |  | End Build Date | time axis 2022-12-10 to 2023-12-30
MTP REDUCER | 0 | 0 | 0 | Prod Build Qty | 2023-05-06: 2
|  |  |  | MTP Reducer No. | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29
0 |  |  |  | Shipment Qty | 2022-12-31: 2; 2023-03-04: 1; 2023-03-25: 1; 2023-04-01: 1; 2023-08-26: 1; 2023-11-04: 2
0 |  |  |  | BOH/EOH | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual Batch Output | 2022-12-10: 26; 2022-12-17: 26; 2023-01-07: 26; 2023-01-14: 26; 2023-01-21: 26; 2023-01-28: 26; 2023-02-04: 26; 2023-02-11: 26; 2023-02-18: 26; 2023-02-25: 27; 2023-03-04: 27; 2023-03-11: 27; 2023-03-18: 27; 2023-03-25: 27; 2023-04-01: 27; 2023-04-08: 27; 2023-04-15: 27; 2023-04-22: 27; 2023-04-29: 27; 2023-05-06: 27; 2023-05-13: 27; 2023-05-20: 27; 2023-05-27: 27; 2023-06-10: 29; 2023-06-17: 29; 2023-06-24: 29; 2023-07-01: 29; 2023-07-08: 29
|  |  |  | BUILD PLAN DELAY | 2022-12-10: -1; 2022-12-17: -1; 2023-01-07: -1; 2023-01-14: -1; 2023-01-21: -1; 2023-01-28: -1; 2023-02-04: -1; 2023-02-11: -1; 2023-02-18: -1; 2023-02-25: 0; 2023-03-04: 0; 2023-03-11: 0; 2023-03-18: 0; 2023-03-25: 0; 2023-04-01: 0; 2023-04-08: 0; 2023-04-15: 0; 2023-04-22: 0; 2023-04-29: 0; 2023-05-06: -2; 2023-05-13: -2; 2023-05-20: -2; 2023-05-27: -2; 2023-06-10: 0; 2023-06-17: 0; 2023-06-24: 0; 2023-07-01: 0; 2023-07-08: 0
PRODUCT | PF/FG | PF/WIP | MK/LLI | WW | WK 50 | WK 51 | WK 52 | WK 53 | WK 1 | WK 2 | WK 3 | WK 4 | WK 5 | WK 6 | WK 7 | WK 8 | WK 9 | WK 10 | WK 11 | WK 12 | WK 13 | WK 14 | WK 15 | WK 16 | WK 17 | WK 18 | WK 19 | WK 20 | WK 21 | WK 22 | WK 23 | WK 24 | WK 25 | WK 26 | WK 27 | WK 28 | WK 29 | WK 30 | WK 31 | WK 32 | WK 33 | WK 34 | WK 35 | WK 36 | WK 37 | WK 38 | WK 39 | WK 40 | WK 41 | WK 42 | WK 44 | WK 44 | WK 45 | WK 46 | WK 47 | WK 48 | WK 49 | WK 50 | WK 51 | WK 52
CONTRACT |  |  |  | Start Build Plan | time axis 2022-12-04 to 2023-12-24
COMPLIANCE |  |  |  | End Build Date | time axis 2022-12-10 to 2023-12-30
HIGH MAG FORCE | 0 | 0 | 14 | Prod Build Qty | 2022-12-10: 1; 2023-02-25: 2; 2023-04-15: 2; 2023-05-13: 1; 2023-07-29: 1; 2023-08-05: 1
|  |  |  | High Mag Force No. | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 46 | 46 | 46 | 46 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 48 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49
14 |  |  |  | Shipment Qty | 2022-12-31: 2; 2023-03-04: 2; 2023-08-12: 1; 2023-08-19: 1; 2023-09-23: 1; 2023-11-04: 2
0 |  |  |  | BOH/EOH | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 5 | 4 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual Batch Output | 2022-12-10: 41; 2022-12-17: 42; 2023-01-07: 42; 2023-01-14: 42; 2023-01-21: 42; 2023-01-28: 42; 2023-02-04: 42; 2023-02-11: 42; 2023-02-18: 42; 2023-02-25: 44; 2023-03-04: 44; 2023-03-11: 44; 2023-03-18: 44; 2023-03-25: 44; 2023-04-01: 44; 2023-04-08: 44; 2023-04-15: 44; 2023-04-22: 46; 2023-04-29: 46; 2023-05-06: 46; 2023-05-13: 47; 2023-05-20: 47; 2023-05-27: 47; 2023-06-10: 47; 2023-06-17: 47; 2023-06-24: 47; 2023-07-01: 47; 2023-07-08: 47
|  |  |  | BUILD PLAN DELAY | 2022-12-10: -1; 2022-12-17: 0; 2023-01-07: 0; 2023-01-14: 0; 2023-01-21: 0; 2023-01-28: 0; 2023-02-04: 0; 2023-02-11: 0; 2023-02-18: 0; 2023-02-25: 0; 2023-03-04: 0; 2023-03-11: 0; 2023-03-18: 0; 2023-03-25: 0; 2023-04-01: 0; 2023-04-08: 0; 2023-04-15: -2; 2023-04-22: 0; 2023-04-29: 0; 2023-05-06: 0; 2023-05-13: 0; 2023-05-20: 0; 2023-05-27: 0; 2023-06-10: 0; 2023-06-17: 0; 2023-06-24: 0; 2023-07-01: 0; 2023-07-08: 0
PRODUCT | PF/FG | PF/WIP | MK/LLI | WW | WK 50 | WK 51 | WK 52 | WK 53 | WK 1 | WK 2 | WK 3 | WK 4 | WK 5 | WK 6 | WK 7 | WK 8 | WK 9 | WK 10 | WK 11 | WK 12 | WK 13 | WK 14 | WK 15 | WK 16 | WK 17 | WK 18 | WK 19 | WK 20 | WK 21 | WK 22 | WK 23 | WK 24 | WK 25 | WK 26 | WK 27 | WK 28 | WK 29 | WK 30 | WK 31 | WK 32 | WK 33 | WK 34 | WK 35 | WK 36 | WK 37 | WK 38 | WK 39 | WK 40 | WK 41 | WK 42 | WK 44 | WK 44 | WK 45 | WK 46 | WK 47 | WK 48 | WK 49 | WK 50 | WK 51 | WK 52
CONTRACT |  |  |  | Start Build Plan | time axis 2022-12-04 to 2023-12-24
COMPLIANCE |  |  |  | End Build Date | time axis 2022-12-10 to 2023-12-30
JTP | 0 | 0 | 0 | Prod Build Qty | bar: 2023-03-25; 2023-05-13
|  |  |  | JTP No. | 2023-03-25: 41; 2023-05-13: 42
0 |  |  |  | Shipment Qty | 2023-11-18: 2
0 |  |  |  | BOH/EOH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual Batch Output | 2023-03-25: 40; 2023-04-01: 40; 2023-04-08: 41; 2023-04-15: 41; 2023-04-22: 41; 2023-04-29: 41; 2023-05-06: 41; 2023-05-13: 41; 2023-05-20: 41; 2023-05-27: 41; 2023-06-10: 41; 2023-06-17: 41; 2023-06-24: 41; 2023-07-01: 41; 2023-07-08: 41
|  |  |  | BUILD PLAN DELAY | 2023-03-25: -1; 2023-04-01: -1; 2023-04-08: 0; 2023-04-15: 0; 2023-04-22: 0; 2023-04-29: 0; 2023-05-06: 41; 2023-05-13: -1; 2023-05-20: -1; 2023-05-27: -1; 2023-06-10: -1; 2023-06-17: -1; 2023-06-24: -1; 2023-07-01: -1; 2023-07-08: -1
PRODUCT | PF/FG | PF/WIP | MK/LLI | WW | WK 50 | WK 51 | WK 52 | WK 53 | WK 1 | WK 2 | WK 3 | WK 4 | WK 5 | WK 6 | WK 7 | WK 8 | WK 9 | WK 10 | WK 11 | WK 12 | WK 13 | WK 14 | WK 15 | WK 16 | WK 17 | WK 18 | WK 19 | WK 20 | WK 21 | WK 22 | WK 23 | WK 24 | WK 25 | WK 26 | WK 27 | WK 28 | WK 29 | WK 30 | WK 31 | WK 32 | WK 33 | WK 34 | WK 35 | WK 36 | WK 37 | WK 38 | WK 39 | WK 40 | WK 41 | WK 42 | WK 44 | WK 44 | WK 45 | WK 46 | WK 47 | WK 48 | WK 49 | WK 50 | WK 51 | WK 52
CONTRACT |  |  |  | Start Build Plan | time axis 2022-12-04 to 2023-12-24
COMPLIANCE |  |  |  | End Build Date | time axis 2022-12-10 to 2023-12-30
OLB | 0 | 0 | 0 | Prod Build Qty | 2023-01-21: 1; 2023-06-10: 0.25; 2023-06-17: 0.25; 2023-06-24: 0.25; 2023-07-01: 0.25; 2023-07-15: 0.25; 2023-07-22: 0.25; 2023-07-29: 0.25; 2023-08-05: 0.25
|  |  |  | OLB No. | 2023-01-21: 43; 2023-06-10: 43.25; 2023-06-17: 43.5; 2023-06-24: 43.75; 2023-07-01: 44; 2023-07-15: 44.25; 2023-07-22: 44.5; 2023-07-29: 44.75; 2023-08-05: 45
0 |  |  |  | Shipment Qty | 2023-01-28: 1; 2023-11-18: 2
0 |  |  |  | BOH/EOH | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.5 | 0.75 | 1 | 1 | 1.25 | 1.5 | 1.75 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual Batch Output | 2022-12-10: 41; 2022-12-17: 41; 2023-01-14: 42; 2023-01-21: 43; 2023-06-10: 43.25; 2023-06-17: 43.49; 2023-06-24: 43.86; 2023-07-01: 43.86; 2023-07-08: 43.86
|  |  |  | BUILD PLAN DELAY | 2022-12-10: -1; 2022-12-17: -1; 2023-01-14: -1; 2023-01-21: 0; 2023-06-10: 0; 2023-06-17: -0.01; 2023-06-24: 0.11; 2023-07-01: -0.14; 2023-07-08: -0.14
PRODUCT | PF/FG | PF/WIP | MK/LLI | WW | WK 50 | WK 51 | WK 52 | WK 53 | WK 1 | WK 2 | WK 3 | WK 4 | WK 5 | WK 6 | WK 7 | WK 8 | WK 9 | WK 10 | WK 11 | WK 12 | WK 13 | WK 14 | WK 15 | WK 16 | WK 17 | WK 18 | WK 19 | WK 20 | WK 21 | WK 22 | WK 23 | WK 24 | WK 25 | WK 26 | WK 27 | WK 28 | WK 29 | WK 30 | WK 31 | WK 32 | WK 33 | WK 34 | WK 35 | WK 36 | WK 37 | WK 38 | WK 39 | WK 40 | WK 41 | WK 42 | WK 44 | WK 44 | WK 45 | WK 46 | WK 47 | WK 48 | WK 49 | WK 50 | WK 51 | WK 52
CONTRACT |  |  |  | Start Build Plan | time axis 2022-12-04 to 2023-12-24
COMPLIANCE |  |  |  | End Build Date | time axis 2022-12-10 to 2023-12-30
PNP I/O | 8 | 0 | 0 | Batch no. | 1532 | 1544 | 1556 | 1556 | 1548 | 1552 | 1560 | 1572 | 1584 | 1596 | 1608 | 1620 | 1632 | 1629 | 1629 | 1641 | 1648 | 1648 | 1648 | 1648 | 1648 | 1654 | 1658 | 1665 | 1678 | 1684 | 1692 | 1700 | 1700 | 1700 | 1700 | 1702 | 1706 | 1710 | 1714 | 1718 | 1722 | 1726 | 1730 | 1734 | 1738 | 1742 | 1746 | 1752 | 1758 | 1764 | 1770 | 1776 | 1782 | 1788 | 1794 | 1800 | 1806 | 1812 | 1818 | 1824
|  |  |  | Prod Build Qty | 12 | 12 | 12 | 0 | 4 | 4 | 8 | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 | 12 | 7 |  |  |  |  | 6 | 4 | 7 | 13 | 6 | 8 | 8 |  |  |  | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
|  |  |  | Shipment Qty | 0 | 0 | 0 | 8 | 4 | 4 | 8 | 12 | 12 | 12 | 12 | 12 |  |  | 12 | 12 | 0 | 7 | 0 | 0 | 0 | 6 | 4 | 7 | 13 | 6 |  | 8 |  |  | 2 |  |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
2 |  |  |  | BOH/EOH | 4 | 16 | 28 | 20 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 24 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 6 | 8 | 12 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
|  |  |  | Actual Output | 2022-12-10: 1532; 2022-12-17: 1544; 2023-01-07: 4; 2023-01-14: 4; 2023-01-21: 8; 2023-01-28: 12; 2023-02-04: 12; 2023-02-11: 1596; 2023-02-18: 1608; 2023-02-25: 1620; 2023-03-04: 1628; 2023-03-11: 1631; 2023-03-18: 1638; 2023-03-25: 1643; 2023-04-08: 1648; 2023-04-15: 1648; 2023-04-22: 1648; 2023-04-29: 1648; 2023-05-06: 1654; 2023-05-13: 1658; 2023-05-20: 1670; 2023-05-27: 1678; 2023-06-03: 1684; 2023-06-10: 1684; 2023-06-17: 1692; 2023-06-24: 1694; 2023-07-01: 1694; 2023-07-08: 1694
|  |  |  | BUILD PLAN DELAY | 2022-12-10: 0; 2022-12-17: 0; 2023-01-07: 0; 2023-01-14: 0; 2023-01-21: 0; 2023-01-28: 0; 2023-02-04: 0; 2023-02-11: 0; 2023-02-18: 0; 2023-02-25: 0; 2023-03-04: -4; 2023-03-11: 2; 2023-03-18: 9; 2023-03-25: 2; 2023-04-08: 0; 2023-04-15: 0; 2023-04-22: 0; 2023-04-29: 0; 2023-05-06: 0; 2023-05-13: 0; 2023-05-20: 5; 2023-05-27: 0; 2023-06-03: 0; 2023-06-10: -8; 2023-06-17: -8; 2023-06-24: -6; 2023-07-01: -6; 2023-07-08: -6
PRODUCT | PF/FG | PF/WIP | MK/LLI | WW | WK 50 | WK 51 | WK 52 | WK 53 | WK 1 | WK 2 | WK 3 | WK 4 | WK 5 | WK 6 | WK 7 | WK 8 | WK 9 | WK 10 | WK 11 | WK 12 | WK 13 | WK 14 | WK 15 | WK 16 | WK 17 | WK 18 | WK 19 | WK 20 | WK 21 | WK 22 | WK 23 | WK 24 | WK 25 | WK 26 | WK 27 | WK 28 | WK 29 | WK 30 | WK 31 | WK 32 | WK 33 | WK 34 | WK 35 | WK 36 | WK 37 | WK 38 | WK 39 | WK 40 | WK 41 | WK 42 | WK 44 | WK 44 | WK 45 | WK 46 | WK 47 | WK 48 | WK 49 | WK 50 | WK 51 | WK 52
CONTRACT |  |  |  | Start Build Plan | time axis 2022-12-04 to 2023-12-24
COMPLIANCE |  |  |  | End Build Date | time axis 2022-12-10 to 2023-12-30
|  |  |  | Batch no. | 831 | 837 | 843 | 843 | 847 | 849 | 853 | 859 | 865 | 871 | 877 | 883 | 889 | 887 | 887 | 893 | 899 | 899 | 899 | 899 | 899 | 902 | 904 | 907 | 915 | 918 | 922 | 926 | 926 | 926 | 926 | 927 | 929 | 931 | 933 | 935 | 937 | 939 | 941 | 943 | 945 | 947 | 949 | 952 | 955 | 958 | 961 | 964 | 967 | 970 | 973 | 976 | 979 | 982 | 985 | 988
PNP T | 4 | 0 | 0 | Prod Build Qty | 6 | 6 | 6 | 0 | 2 | 2 | 4 | 6 | 6 | 6 | 6 | 6 | 6 |  | 6 | 6 | 6 |  |  |  |  | 3 | 2 | 3 | 8 | 3 | 4 | 4 |  |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
|  |  |  | Shipment Qty | 0 | 0 | 0 | 4 | 2 | 2 | 4 | 6 | 6 | 6 | 6 | 6 |  |  | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 3 | 2 | 3 | 8 | 3 |  | 4 |  |  | 1 |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
1 |  |  |  | BOH/EOH | 2 | 8 | 14 | 10 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 12 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 3 | 4 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  |  |  | Actual Output | 2023-01-07: 6; 2023-01-14: 2; 2023-01-21: 4; 2023-01-28: 6; 2023-02-04: 6; 2023-02-11: 871; 2023-02-18: 877; 2023-02-25: 883; 2023-03-04: 886; 2023-03-11: 888; 2023-03-18: 892; 2023-03-25: 894; 2023-04-08: 899; 2023-04-15: 899; 2023-04-22: 899; 2023-04-29: 899; 2023-05-06: 902; 2023-05-13: 904; 2023-05-20: 910; 2023-05-27: 915; 2023-06-03: 918; 2023-06-10: 918; 2023-06-17: 922; 2023-06-24: 922; 2023-07-01: 922; 2023-07-08: 923
|  |  |  | BUILD PLAN DELAY | 2023-01-07: 0; 2023-01-14: 0; 2023-01-21: 0; 2023-01-28: 0; 2023-02-04: 0; 2023-02-11: 0; 2023-02-18: 0; 2023-02-25: 0; 2023-03-04: -3; 2023-03-11: 1; 2023-03-18: 1; 2023-03-25: 1; 2023-04-08: 0; 2023-04-15: 0; 2023-04-22: 0; 2023-04-29: 0; 2023-05-06: 0; 2023-05-13: 0; 2023-05-20: 3; 2023-05-27: 0; 2023-06-03: 0; 2023-06-10: -4; 2023-06-17: -4; 2023-06-24: -4; 2023-07-01: -4; 2023-07-08: -3
ATS-PPIF-006 |  |  |  |  | 2023-12-30: Rev. No. : 01
[5 empty] | 18 | 18 | 18 | 0 | 6 | 6 | 12 | 18 | 18 | 18 | 18 | 18 | 18 | 0 | 18 | 18 | 13 | 0 | 0 | 0 | 0 | 9 | 6 | 10 | 21 | 9 | 12 | 12 | 0 | 0 | 0 | 3 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
Formulas:
JANUARY = +"WK"&" "&WEEKNUM([JANUARY, row below])
Note on AJ32: SPARES
Note on AJ41: SPARES
Note on T50: SPARES
Note on W50: SPARES
Note on X50: SPARES
Note on T59: SPARES
Note on U85: no build for week 10 due to quality issue on side plate right
Note on U94: no build for week 10 due to quality issue on side plate right

## Plan vs. Actual-October (hidden)
REASON OF DELAY: | Material Delay
Capacity Issue
Quality Issue
PROJECT | WW DELAYED | REASON | Details | ACTION | IN-CHARGE | REMARKS | STATUS
JLP/MTP/FLIPPER | WW40 | Capacity Issue | Accumulated delay due to unavailability of manpower due to quarantine | Conduct Saturday/Sunday overtime | M. Tanag |  | Open

## Plan vs. Actual-August (hidden)
PLAN VS. ACTUAL OUTPUT (AUGUST 2021) | [6 empty] | REASON OF DELAY: | Material Delay
PLAN | [7 empty] | Capacity Issue
ACTUAL | [7 empty] | Quality Issue
| MONTH | AUGUST |  |  |  |  | PROJECT | WW DELAYED | REASON | Details | ACTION | IN-CHARGE | REMARKS | STATUS
PRODUCT | WW | WK 33 | WK 34 | WK 35 | WK 36 | WK 37 | Ionizer | WW33 | Capacity Issue | Prioritization of other project due to absences | Maximize production for WW34 | Joseph |  | Open
CONTRACT | Start Build Plan | 2021-08-09 | 2021-08-16 | 2021-08-23 | 2021-08-30 | 2021-09-06 | MTP
COMPLIANCE | End Build Date | 2021-08-15 | 2021-08-22 | 2021-08-29 | 2021-09-05 | 2021-09-12
JLP | Prod Build Plan | 6 | 7 | 7 | 7 | 7
| JLP Batch no. | 793 | 800 | 807 | 814 | 821
| Actual Output | 6 | 5
| JLP Batch no. | 793 | 798
| Accumulated Delay | 0 | -2 | -9 | -16 | -23
| Weekly Achievement Rate | 100% | 71.43% | 0% | 0% | 0%
| MONTHLY AVERAGE % | 34.29%
FLIPPER (NO PLAN) | Prod Build Plan | #REF! | #REF! | #REF! | #REF! | #REF!
Flipper Batch no.
Actual Output
Flipper Batch no.
| Accumulated Delay | #REF! | #REF! | #REF! | #REF! | #REF!
| Weekly Achievement Rate | #REF! | #REF! | #REF! | #REF! | #REF!
| MONTHLY AVERAGE % | #REF!
MTP | Prod Build Plan | 5 | 5 | 6 | 5 | 5
| MTP Batch no. | 572 | 577 | 582 | 587 | 592
| Actual Output | 1 | 3
| MTP Batch no. | 568 | 571
| Accumulated Delay | -4 | -6 | -12 | -17 | -22
| Weekly Achievement Rate | 20% | 60% | 0% | 0% | 0%
| MONTHLY AVERAGE % | 16%
IONIZER | Prod Build Plan | 2 | 1 | 1 | 1 | 1
| Ionizer Batch no. | 212 | 213 | 214 | 215 | 216
| Actual Output | 0 | 0
Ionizer Batch no.
| Accumulated Delay | -2 | -3 | -4 | -5 | -6
| Weekly Achievement Rate | 0% | 0% | 0% | 0% | 0%
| MONTHLY AVERAGE % | 0%
JTP (NO PLAN) | Prod Build Plan | 0 | 0 | 0 | 0 | 0
JTP Batch no.
Actual Output
JTP Batch no.
| Accumulated Delay | 0 | 0 | 0 | 0 | 0
| Weekly Achievement Rate | #DIV/0!
| MONTHLY AVERAGE % | #DIV/0!
PNP I/O | Prod Build Plan | 12 | 20 | 13 | 6 | 0
| PNP Batch no. | 167B~173A | 173B~183A |  | 183B~189B | 190A~192B
| Actual Output | 12 | 20 | 0 | 11 | 8
PNP Batch no.
| Accumulated Delay | 0 | 0 | -13 | -8 | 0
| Weekly Achievement Rate | 100% | 100% | 0% | 183.3% | #DIV/0!
PNP T | Prod Build Plan | 6 | 9 | 0 | 8 | 7
| Actual Output | 6 | 9
| Accumulated Delay | 0 | 0 | 0 | -8 | -15
| Weekly Achievement Rate | 100% | 100% | #DIV/0! | 0% | 0%
| MONTHLY AVERAGE % | #DIV/0!

## Plan vs. Actual-Jul (hidden)
PLAN VS. ACTUAL OUTPUT (JULY 2021) | [6 empty] | REASON OF DELAY: | Material Delay
PLAN | [7 empty] | Capacity Issue
ACTUAL | [7 empty] | Quality Issue
| MONTH | JULY |  |  |  |  | PROJECT | WW DELAYED | REASON | Details | ACTION | IN-CHARGE | REMARKS | STATUS
PRODUCT | WW | WK 28 | WK 29 | WK 30 | WK 31 | WK 32 | JLP | WW28 | Material Delay | Lacking: 8330542501 PCA,G2 CAN IO MOD,JLP | Cohu Manage Issued P.O. to Cohu My and Delta US | Ms. Lorraine | Received -x4 ETA 7/12-UNTIL JLP781 | Open
CONTRACT | Start Build Plan | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02 |  |  |  | Lacking:1977476501PCA, NETWORK TAP-4 |  |  | DHL 9163336324-x12-7/14 | Open
COMPLIANCE | End Build Date | 2021-07-11 | 2021-07-18 | 2021-07-25 | 2021-08-01 | 2021-08-08 | IONIZER |  | Material Delay | Lacking: 1210088 IONIZER BAR MODEL 5710 400MM | Follow delivery to DOU YEE ENTERPRISES(S) PTE LTD | Ms. Dana | decommit ETA 7/2--> ETA 7/12 | Open
JLP | Prod Build Plan | 5 | 5 | 4 | 4 | 6 |  |  |  | 3604457 BRACKET IONIZER ROTATABLE
| JLP Batch no. | 768 | 773 | 777 | 782 | 787 | JTP |  | Material Delay | Lacking:1977476501PCA, NETWORK TAP-4 | Cohu Manage, Issued P.O. to Delta US | Ms. Lorraine | DHL 9163336324-x12-7/14 | Open
| Actual Output | 3 | 2 | 1 | 2 | 7 | PNP Matrix |  | Quality Issue | with quality issue 1504000 O-RING 5IDX1CS VITON (BROWN) (McMaster) | Issued P.O. to Allied and Cohu | Ms. Lorraine | Received-x400-ETA 7/12 from Cohu | Open
| JLP Batch no. | 778 | 780 | 781 | 782 | 789 | JLP | WW29 | Material Delay | Lacking: 8330542501 PCA,G2 CAN IO MOD,JLP | Cohu Manage Issued P.O. to Cohu My and Delta US | Ms. Lorraine | Received -x4 ETA 7/12-UNTIL JLP781 | Open
| Accumulated Delay | -2 | -5 | -8 | -10 | -9 |  |  |  | Lacking:1977476501PCA, NETWORK TAP-4 |  |  | DHL 9163336324-x12-7/14 | Open
| Weekly Achievement Rate | 60% | 40% | 25% | 50% | 116.7% | IONIZER |  | Material Delay | Lacking: 1210088 IONIZER BAR MODEL 5710 400MM | Follow delivery to DOU YEE ENTERPRISES(S) PTE LTD | Ms. Dana | decommit ETA 7/2--> ETA 7/12 | Open
| MONTHLY AVERAGE % | 58.33% | [7 empty] | 3604457 BRACKET IONIZER ROTATABLE
FLIPPER (NO PLAN) | Prod Build Plan | #REF! | #REF! | #REF! | #REF! | #REF! | JTP |  | Material Delay | Lacking:1977476501PCA, NETWORK TAP-4 | Cohu Manage, Issued P.O. to Delta US | Ms. Lorraine | DHL 9163336324-x12-7/14 | Open
| Flipper Batch no. | [5 empty] | PNP Matrix |  | Quality Issue | with quality issue 1504000 O-RING 5IDX1CS VITON (BROWN) (McMaster) | Issued P.O. to Allied and Cohu | Ms. Lorraine | Received-x400-ETA 7/12 from Cohu | Closed
| Actual Output | [5 empty] | JLP | WW30 | Material Delay | Lacking: 8330542501 PCA,G2 CAN IO MOD,JLP | Cohu Manage Issued P.O. to Cohu My and Delta US | Ms. Lorraine | TBA | Open
| Flipper Batch no. | [8 empty] | 1977725501 PWA,CANOPEN DIO 3232 ROHS |  |  | 6422600225-x19 ETD 7/26 | Open
| Accumulated Delay | #REF! | #REF! | #REF! | #REF! | #REF! | JLP | WW31 | Material Delay | Lacking: 8330542501 PCA,G2 CAN IO MOD,JLP | Cohu Manage Issued P.O. to Cohu My and Delta US | Ms. Lorraine | Received -x4 ETA 7/12-UNTIL JLP781 | Closed
| Weekly Achievement Rate | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | Lacking:1977476501PCA, NETWORK TAP-4 |  |  | DHL 9163336324-x12-7/14 | Closed
| MONTHLY AVERAGE % | #REF! | [6 empty] | Quality Issue | Wrong material: Bushing, Singulator, Push-Off Finger (302030288) | Purchase to other supplier DESIGN SOLUTIONS AND MACHINING, INC. | Ms. Lorraine | Received x16-8/3 | Closed
MTP | Prod Build Plan | 3 | 3 | 3 | 3 | 4 | JLP | WW32 | Material Delay | Accumulated delay due shortage of quantronic parts | Cohu Manage | Ms. Lorraine | Continuous coordination with Quantronic/SK | Open
| MTP Batch no. | 558 | 561 | 564 | 567 | 571
| Actual Output | 3 | 2 | 4 | 3 | 0
| MTP Batch no. | 558 | 560 | 564 | 567 |  | PNP Matrix |  | Quality Issue | Accumulated delay due to encountered quality issue of O-ring |  |  |  | Closed
| Accumulated Delay | 0 | -1 | 0 | 0 | -4
| Weekly Achievement Rate | 100% | 66.67% | 133.3% | 100% | 0%
| MONTHLY AVERAGE % | 80%
IONIZER | Prod Build Plan |  |  |  |  | 2
| Ionizer Batch no. |  |  |  |  | 212
| Actual Output | 0 | 0 | 0 | 0 | 0
Ionizer Batch no.
| Accumulated Delay | 0 | 0 | 0 | 0 | -2
| Weekly Achievement Rate | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0%
| MONTHLY AVERAGE % | #DIV/0!
JTP | Prod Build Plan | 1
| JTP Batch no. | 32
| Actual Output |  |  | 1
JTP Batch no.
| Accumulated Delay | -1 | -1 | 0 | 0 | 0
| Weekly Achievement Rate | 0%
| MONTHLY AVERAGE % | 0%
PNP I/O | Prod Build Plan | 16 | 10 | 20 | 18 | 19
| PNP Batch no. | IO134A~IO141B | IO142A~IO149A | IO149B~IO154B | IO155A~IO159B | IO160A~IO164B
| Actual Output | 0 | 10 | 20 | 18
PNP Batch no.
| Accumulated Delay | -16 | -16 | -16 | -16 | -35
| Weekly Achievement Rate | 0% | 100% | 100% | 100% | 0%
PNP T | Prod Build Plan | 9 | 4 | 10 | 12 | 11
| Actual Output | 0 | 4 | 10 | 12
| Accumulated Delay | -9 | -9 | -9 | -9 | -20
| Weekly Achievement Rate | 0% | 100% | 100% | 100% | 0%
| MONTHLY AVERAGE % | 60%
Formulas:
JULY = [JULY, row above]+6
WK 29 = [WK 29, row above]+6
WK 30 = [WK 30, row above]+6
WK 31 = [WK 31, row above]+6
WK 32 = [WK 32, row above]+6

## Plan vs. Actual-Jun (hidden)
PLAN VS. ACTUAL OUTPUT (JUNE 2021) | [6 empty] | REASON OF DELAY: | Material Delay
PLAN | [7 empty] | Capacity Issue
ACTUAL | [7 empty] | Quality Issue
| MONTH | JUNE |  |  |  |  | PROJECT | WW DELAYED | REASON | Details | ACTION | IN-CHARGE | REMARKS | STATUS
PRODUCT | WW | WK 23 | WK 24 | WK 25 | WK 26 | WK 27 | JLP | WW23 | Material Delay | 1977725501 PWA,CANOPEN DIO 3232 ROHS | Cohu manage | Ms. Lorraine | ETA 6/11-x33 | OPEN
CONTRACT | Start Build Plan | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 |  |  | Material Delay | 100027704 COMPUTER ASSY, JLP GEN 3 | Coordination to supplier and monitoring of shipment | Ms. Lorraine | ETA 6/3-X7, ETA 6/4-x5 | CLOSED-next affected JLP775
COMPLIANCE | End Build Date | 2021-06-06 | 2021-06-13 | 2021-06-20 | 2021-06-27 | 2021-07-04 |  | WW24-25 | Material Delay | 1977725501 PWA,CANOPEN DIO 3232 ROHS | Cohu manage | Ms. Lorraine | ETA 6/21-RCV | CLOSED
JLP | Prod Build Plan | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | Material Delay | 8330227101 PULLEY, 36T, MOTOR, TXP Y-supplier plating issue | Issued P.O. to Cohu MY-x3, another P.O. x10 | Ms. Lorraine | X72-RCV 6/19 | CLOSED
| JLP Batch no. | 765 | 771 | 777 | 782 | 787
| Actual Output | 3 | 3 | 7 | 2 | 1
| JLP Batch no. | 762 | 765 | 772 | 774 | 775 |  | WW26 | Material Delay | 3602293 FILTER,POWER IN-LINE,30AMP | Continuous follow up of delivery to supplier | Ms. Christelle | ETA 6/29-x50-RCV | CLOSED
| Accumulated Delay | #REF! | #REF! | #REF! | #REF! | #REF! |  | WW27 | Material Delay | 8330542501 PCA,G2 CAN IO MOD,JLP | Cohu manage issued P.O. to Cohu and Delta | Ms. Lorraine | ETA 7/7-X2 ETA 7/9-X14 | OPEN
| Weekly Achievement Rate | #REF! | #REF! | #REF! | #REF! | #REF! | MTP | WW24-26 | Material Delay | 8333073001 TCA DIO8 BOB (Quantronic) | Cohu manage | Ms. Lorraine | ETA 6/8-X38, ETA 6/10-X19 | CLOSED
| MONTHLY AVERAGE % | #REF! |  |  |  |  | IONIZER | WW24-26 | Stocks x8 borrowed by spares due to wrong actual qty | 3604457 BRACKET IONIZER ROTATABLE | Request replacement to DOU YEE ENTERPRISES(S) PTE LTD | Ms. Dana | ETA 6/10-x24 | CLOSED
FLIPPER (NO PLAN) | Prod Build Plan | #REF! | #REF! | #REF! | #REF! | #REF! | JTP | WW24 | Material Delay | 8330528101 CARD COPLEY PCI-CAN JLP | Cohu manage | Ms. Christelle | ETA 6/29-x8-RCV | CLOSED
| Flipper Batch no. | [5 empty] | JTP | WW26 | Material Delay | 8330542501 PCA,G2 CAN IO MOD,JLP | Cohu manage issued P.O. to Cohu and Delta | Ms. Lorraine | ETA 7/7-X2 ETA 7/9-X14 | OPEN
| Actual Output | [5 empty] | Matrix | WW23-WW26 | Material Delay (Changed allocation by Cohu to increased Spline Delivery) | 1703057 SPLINE, 4mm X 116.6mmL X 3NUTS | Cohu manage | Jho |  | CLOSED
Flipper Batch no.
| Accumulated Delay | #REF! | #REF! | #REF! | #REF! | #REF!
| Weekly Achievement Rate | #REF! | #REF! | #REF! | #REF! | #REF!
| MONTHLY AVERAGE % | #REF!
MTP | Prod Build Plan | #REF! | #REF! | #REF! | #REF! | #REF!
| MTP Batch no. | 545 | 551 | 556 | 560 | 564
| Actual Output | 2 | 3 | 3 | 6 | 1
| MTP Batch no. | 545 | 548 | 551 | 557 | 558
| Accumulated Delay | #REF! | #REF! | #REF! | #REF! | #REF!
| Weekly Achievement Rate | #REF! | #REF! | #REF! | #REF! | #REF!
| MONTHLY AVERAGE % | #REF!
IONIZER | Prod Build Plan | #REF! | #REF! | #REF! | #REF! | #REF!
| Ionizer Batch no. | 203 | 206 | 209 | 211 | 213
| Actual Output | 3 | 0 | 4 | 3 | 0
| Ionizer Batch no. | 203 | 203 | 207 | 210
| Accumulated Delay | #REF! | #REF! | #REF! | #REF! | #REF!
| Weekly Achievement Rate | #REF! | #REF! | #REF! | #REF! | #REF!
| MONTHLY AVERAGE % | #REF!
JTP | Prod Build Plan | #REF! | 1 |  | 1 | #REF!
| JTP Batch no. |  | 30 |  | 31
| Actual Output |  | 0 | 0 | 1
JTP Batch no.
| Accumulated Delay |  | -1 | -1 | -1 | #REF!
| Weekly Achievement Rate |  | 0% |  | 100%
| MONTHLY AVERAGE % | 50%
PNP I/O | Prod Build Plan | 12 | 11 | 12 | 16 | 11
| PNP Batch no. | B111~125 | B119~133 | B127~141 | B135~149 | B143~157
| Actual Output | 12 | 11 | 14 | 16 | 17
PNP Batch no.
| Accumulated Delay | 0 | 0 | 2 | 2 | 8
| Weekly Achievement Rate | 100% | 100% | 116.7% | 100% | 154.5%
PNP T | Prod Build Plan | 14 | 5 | 4 | 6 | 6
| Actual Output | 14 | 5 | 3 | 6 | 12
| Accumulated Delay | 0 | 0 | -1 | -1 | 5
| Weekly Achievement Rate | 100% | 100% | 75% | 100% | 200%
| MONTHLY AVERAGE % | 114.6%

## JLP Slot Plan
Production | JLP Number Mark | Entity | SO # | Cohu MY PO to PIMES | SITE | New Stock Code/Cofig | DESCRIPTION | Intel Requested Monitor Side | Intel PO# | MY Need date | Transit Mode | P.IMES Commit | Remarks | Cohu SN
| JLP 1091 | JLP103b | 100172117 | PMY151149 | KM | 302053368 | JLP REV3 W/HIFORCE, RCMTP, FLIP, MODEL 5431 | RIGHT | 4200275559 | 2023-09-21 | AIR | 2023-09-21 | push out 8/21-->9/21
| JLP 1092 | JLP103c | 100170893 | PMY149984 | KM | 302053366 | JLP REV3 W/HIFORCE, FLIP, MODEL 5411 | Right | 4200274857 | 2023-09-01 | Air | 2023-09-01 | push out 7/31-->9/1
| JLP 1093 | JLP00175 | 100164287 | PMY156120 | CR | 302009764 | JLP REV3 W/MTP, IONIZER, MODEL 5460 | Left | 4200273206 | 2023-08-18 | AIR | 2023-08-18 | push out 6/16-->8/18 | CFG16435000105
| JLP 1094 | JLP00174 | 10164548 | PMY156100 | CR | 302009763 | JLP REV3 W/MTP, MODEL 5420 | Right | 4200273245 | 2023-08-18 | AIR | 2023-08-18 | push out 6/16-->8/18 | CFG16430000265
| JLP 1095 | JLP103a | 100170892 | PMY149982 | KM | 302009767 | JLP REV3 W/FLIP, IONIZER, MODEL 5450 | Left | 4200274856 | 2023-09-01 | Air | 2023-09-01 | push out 7/31-->9/1
| JLP 1096 | JLP80133 | 100141139 | PMY148832 | PG | 302053366 | JLP REV3 W/HIFORCE, FLIP, MODEL 5411 | Right | 4200260549 | 2023-09-21 | AIR | 2023-09-21 | push out 5/25-->9/21
| JLP 1097 | JLP00128 | 100133559 | PMY156103 | CR | 302009763 | JLP REV3 W/MTP, MODEL 5420 | Right | 4200254208 | 2023-10-02 | OCEAN | 2023-10-02 | push out 9/28-->10/2
| JLP 1098 | JLP00126 | 100133554 | PMY156128 | CR | 302009764 | JLP REV3 W/MTP, IONIZER, MODEL 5460 | Left | 4200254203 | 2023-10-02 | OCEAN | 2023-10-02 | push out 9/28-->10/2
| JLP 1099 | JLP80216 | 100170418 | TBA | KM | 302009763 | JLP REV3 W/MTP, MODEL 5420 | Right | 4200274708 | 2023-10-27 | Air | 2023-10-27 | push out 9/27-->10/27/23
| JLP 1100 | JLP80217 | 100170416 | PMY156126 | KM | 302009764 | JLP REV3 W/MTP, IONIZER, MODEL 5460 | Left | 4200274707 | 2023-10-27 | Air | 2023-10-27 | push out 9/27-->10/27/23
| JLP 1101 | JLP80120 | 100170422 | TBA | KM | 302009763 | JLP REV3 W/MTP, MODEL 5420 | Right | 4200274710 | 2023-10-27 | Air | 2023-10-27 | push out 9/27-->10/27/23
| JLP 1102 |  |  | TBA |  | 302009763 | JLP REV3 W/MTP, MODEL 5420 | [5 empty] | ADDITIONAL
| JLP 1103 |  |  | TBA |  | 302009763 | JLP REV3 W/MTP, MODEL 5420 | [5 empty] | ADDITIONAL
| JLP 1104 | JLP80121 | 100170420 | PMY156127 | KM | 302009764 | JLP REV3 W/MTP, IONIZER, MODEL 5460 | Left | 4200274709 | 2023-10-27 | Air | 2023-10-27 | push out 9/27-->10/27/23
| JLP 1105 | JLP00123 | 100133548 | PMY156102 | CR | 302009763 | JLP REV3 W/MTP, MODEL 5420 | Right | 4200254197 | 2023-10-30 | AIR | 2023-10-30 | push out 10/2-->10/30
| JLP 1106 | JLP00124 | 100133551 | PMY156122 | CR | 302009764 | JLP REV3 W/MTP, IONIZER, MODEL 5460 | Left | 4200254200 | 2023-10-30 | AIR | 2023-10-30 | push out 10/2-->10/30
| JLP 1107 | JLP80104 | 100136499 | PMY148834 | KM | 302053372 | JLP REV3 W/HIFORCE, RCMTP, IONIZER, FLIP, MODEL 5486 | Left | 4200257701 | 2023-11-03 | AIR | 2023-11-03 | pull in 12/8-->11/3
| JLP 1108 | JLP80103 | 100136500 | PMY148836 | KM | 302053368 | JLP REV3 W/HIFORCE, RCMTP, FLIP, MODEL 5431 | Right | 4200257702 | 2023-11-03 | AIR | 2023-11-03 | pull in 12/8-->11/3
| JLP 1109 | JLP80111 | 100137871 | TBA | KM | 302009763 | JLP REV3 W/MTP, MODEL 5420 | Right | 4200258614 | 2023-11-03 | AIR | 2023-11-03 | pull in 1/4/24-->11/3
| JLP 1110 | JLP80115 | 100137875 | PMY156124 | KM | 302009764 | JLP REV3 W/MTP, IONIZER, MODEL 5460 | Left | 4200258615 | 2023-11-03 | AIR | 2023-11-03 | pull in 1/4/24-->11/3
| JLP 1111 | JLP80122 | 100137864 | PMY156125 | KM | 302009764 | JLP REV3 W/MTP, IONIZER, MODEL 5460 | Left | 4200258613 | 2023-11-03 | AIR | 2023-11-03 | pull in 1/4/24-->11/3
| JLP 1112 | JLP80119 | 100137878 | TBA | KM | 302009763 | JLP REV3 W/MTP, MODEL 5420 | Right | 4200258616 | 2023-11-03 | AIR | 2023-11-03 | pull in 1/4/24-->11/3
| JLP 1113 | JLP80105 | 100136496 | PMY156106 | KM | 302009763 | JLP REV3 W/MTP, MODEL 5420 | Right | 4200257698 | 2023-11-10 | AIR | 2023-11-10 | pull in 12/23-->11/10
| JLP 1114 | JLP80106 | 100136497 | PMY156107 | KM | 302009763 | JLP REV3 W/MTP, MODEL 5420 | Left | 4200263356 | 2023-11-10 | AIR | 2023-11-10 | pull in 12/28-->11/10
| JLP 1115 | JLP80120 | 100142224 | PMY156109 | KM | 302009763 | JLP REV3 W/MTP, MODEL 5420 | Right | 4200261245 | 2023-11-10 | AIR | 2023-11-10 | pull in 12/28-->11/10
| JLP 1116 | JLP80117 | 100142221 | PMY156108 | KM | 302009763 | JLP REV3 W/MTP, MODEL 5420 | Left | 4200263355 | 2023-11-10 | AIR | 2023-11-10 | pull in 12/28-->11/10
| JLP 1117 | JLP2002 | 100203960 | TBA | CH | 302125607 | JLP REV3 W/MTP,VENT, MODEL 5422 | Right | 4200282397 | 2023-11-10 | OCEAN | 2023-11-10
| JLP 1118 | JLP2001 | 100203962 | TBA | CH | 302009763 | JLP REV3 W/MTP, MODEL 5420 | Left | 4200282399 | 2023-11-10 | OCEAN | 2023-11-10
| JLP 1119 | JLP90102 | 100178366 | PMY154129 | KM | 302009763 | JLP REV3 W/MTP, MODEL 5420 | RIGHT | 4200276919 | 2023-11-13 | AIR | 2023-11-13 | pull in 12/14-->11/13
| JLP 1120 | JLP90101 | 100178368 | TBA | KM | 302009763 | JLP REV3 W/MTP, MODEL 5420 | TBA | 4200276920 | 2023-11-13 | OCEAN | 2023-11-13 | pull in 12/14-->11/13
| JLP 1121 | JLP80111 | 100136494 | PMY156110 | KM | 302009763 | JLP REV3 W/MTP, MODEL 5420 | Left | 4200257694 | 2023-11-16 | AIR | 2023-11-16 | push out 8/4-->11/16
| JLP 1122 | JLP80112 | 100136485 | PMY156111 | KM | 302009763 | JLP REV3 W/MTP, MODEL 5420 | Right | 4200257690 | 2023-11-16 | AIR | 2023-11-16 | push out 8/4-->11/16
| JLP 1123 | JLP80119 | 100137046 | PMY156247 | KM | 302009765 | JLP REV3, MODEL 5400 | Left | 4200258035 | 2023-11-17 | AIR | 2023-11-17 | push out 8/18-->11/17/23
| JLP 1124 | JLP80215 | 100137050 | PMY156258 | KM | 302009765 | JLP REV3, MODEL 5400 | Left | 4200258036 | 2023-11-17 | AIR | 2023-11-17 | pull in 11/24-->11/17
| JLP 1125 | JLP80209 | 100147071 | PMY156112 | KM | 302009763 | JLP REV3 W/MTP, MODEL 5420 | Left | 4200264884 | 2023-11-24 | AIR | 2023-11-24 | push out 8/4-->11/24
| JLP 1126 | JLP80210 | 100147072 | PMY156113 | KM | 302009763 | JLP REV3 W/MTP, MODEL 5420 | Right | 4200264885 | 2023-11-24 | AIR | 2023-11-24 | push out 8/4-->11/24
| JLP 1127 | JLP80116 | 100136174 | PMY156104 | KM | 302009763 | JLP REV3 W/MTP, MODEL 5420 | Right | 4200257688 | 2023-11-24 | AIR | 2023-11-24 | pull in 12/16-->11/24
| JLP 1128 | JLP80115 | 100136492 | PMY156105 | KM | 302009763 | JLP REV3 W/MTP, MODEL 5420 | Left | 4200257693 | 2023-11-24 | AIR | 2023-11-24 | pull in 12/16-->11/24
| JLP 1129 | JLP80101 | 100151072 | PMY149379 | KM | 302009768 | JLP REV3 W/FLIP, MTP, MODEL 5430 | Right | 4200255787 | 2023-12-08 | AIR | 2023-12-08 | push out 7/14-->12/8/23
| JLP 1130 | JLP80102 | 100135371 | PMY148851 | KM | 302009767 | JLP REV3 W/FLIP, IONIZER, MODEL 5450 | Left | 4200255791 | 2023-12-08 | AIR | 2023-12-08 | push out 7/14-->12/8/23
| JLP 1131 | JLP80202 | 100135370 | PMY148849 | KM | 302009767 | JLP REV3 W/FLIP, IONIZER, MODEL 5450 | Left | 4200255789 | 2023-12-08 | AIR | 2023-12-08 | pull in 12/15-->12/8/23
| JLP 1132 | JLP80201 | 100151070 | PMY148840 | KM | 302009768 | JLP REV3 W/FLIP, MTP, MODEL 5430 | RIGHT | 4200255762 | 2023-12-08 | AIR | 2023-12-08 | pull in 12/15-->12/8/23

## Actual Build (hidden)
|  | MONTH | OCTOBER |  |  |  | NOV |  |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  |  | MAY |  |  |  |  | JUNE |  |  |  |  | JUNE
| PRODUCT | WW | WK 40 | WK 41 | WK 42 | WK 43 | WK 44 | WK 45 | WK 46 | WK 47 | WK 48 | WK 49 | WK 50 | WK 51 | WK 52 | WK01 | WK 2 | WK 3 | WK 4 | WK 5 | WK 6 | WK 7 | WK 8 | WK 9 | WK 10 | WK 11 | WK 12 | WK 13 | WK 14 | WK 15 | WK 16 | WK 17 | WK 18 | WK 19 | WK 20 | WK 21 | WK 22 | WK 23 | WK 24 | WK 25 | WK 26 | WK 27 | WK 28 | WK 29 | WK 30 | WK 31 | WK 32 | WK 33
| CONTRACT | Start Build Plan | time axis 2020-09-27 to 2021-08-09
| COMPLIANCE | End Build Date | time axis 2020-10-03 to 2021-08-15
| JLP | Prod Build | 1 | 1 | 1 | 1 | 2 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 3 |  | 3 | 3 | 3 | 3 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
|  | Actual | 1 | 1 | 1 | 1 | 2 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 1 |  | 3 | 3 | 3 | 3 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| FLIPPER | Prod Build | 2020-10-03: 1; 2021-01-03: 6; 2021-01-24: 3; 2021-02-07: 3
|  | Actual | 2020-10-03: 1; 2021-01-03: 6; 2021-01-24: 3; 2021-02-07: 3
| MTP | Prod Build |  |  |  |  | 2 |  | 3 | 5 |  |  | 5 | 5 | 3 |  | 5 | 5 | 5 | 5 | [6 empty] | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
|  | Actual |  |  |  |  | 2 |  | 3 | 5 |  |  | 5 | 5 | 3 |  | 5 | 5 | 5 | 5 | [6 empty] | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| IONIZER | Prod Build | 2020-10-10: 2; 2020-10-17: 3; 2020-12-27: 6; 2021-01-03: 5; 2021-01-10: 4; 2021-01-24: 3; 2021-02-14: 2; 2021-03-07: 2; 2021-03-28: 2; 2021-04-11: 2; 2021-04-25: 2; 2021-05-09: 2; 2021-05-23: 2; 2021-06-06: 2; 2021-06-20: 2; 2021-07-04: 2; 2021-07-18: 3
|  | Actual | 2020-10-10: 2; 2020-10-17: 3; 2020-12-27: 6; 2021-01-03: 5; 2021-01-10: 4; 2021-01-24: 3; 2021-02-14: 2; 2021-03-07: 2; 2021-03-28: 2; 2021-04-11: 2; 2021-04-25: 2; 2021-05-09: 2; 2021-05-23: 2; 2021-06-06: 2; 2021-06-20: 2; 2021-07-04: 2; 2021-07-18: 3
| JTP | Prod Build | bar: 2020-11-07; 2020-12-06; 2021-01-31; 2021-03-07
Actual | bar: 2020-11-07; 2020-12-06; 2021-01-31; 2021-03-07
| OLB | Prod Build | 2021-01-03: 0; 2021-02-14: 1; 2021-03-14: 1; 2021-04-25: 1; 2021-05-30: 1; 2021-07-25: 1
|  | Actual | 2021-01-03: 0; 2021-02-14: 1; 2021-03-14: 1; 2021-04-25: 1; 2021-05-30: 1
6 | PNP I/O | Prod Build | 2 | 2 | 2 | 4 | 1 | 3 | 4 | 1 | 6 | 4 | 2 | 6 | 6 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 16 | 16 | 16 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
|  | Actual | 2 | 2 | 2 | 4 | 1 | 3 | 4 | 1 | 6 | 4 | 2 | 6 | 6 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 16 | 16 | 16 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
| PNP T | Prod Build |  | 1 | 1 | 1 |  | 2 | 2 | 2 | 3 | 2 | 1 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
|  | Actual |  | 1 | 1 | 1 |  | 2 | 2 | 2 | 3 | 2 | 1 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| XT/XTA | Prod Build
Actual

## Wk 04 Issues (hidden)
ww | Date of Occurrence | Product | PN | What | Reason
2 | 2021-01-09 | PnP | 8330948001 | OTD Miss of x2 PnP Heads | Quality Issue- No Final Analysis yet on Root Cause
8309939001

## Spares Open PO (hidden)
SPARES OPEN PO AS OF DEC 29
PO NO | PO Date | Cohu Required Ship Date in PO | P.IMES Orig Commit | P.IMES Pick up Date | P.IMES Commit | ACTUAL SHIP | Destintion | Planner | PARTS CLASSIFICATIONS | Partnumber | Desciption | Qty
PMY29732 | 2020-10-26 | 2021-01-11 | 2021-01-11 | 2021-01-08 | 2021-01-11 |  | Cohu MY | Joel | Module ASM | 8352955001 | TRAY PLATEN QD, | 1
PMY34358 | 2020-11-24 | 2020-12-24 | 2020-12-29 | 2021-01-08 | 2021-01-11 | x5 shipped 12/22;balance | Cohu MY | Ronna | Cable ASM | 8301876003 | CABLE ASSY, 208VAC SHTL | 6
PMY37188 | 2020-12-08 | 2021-01-12 | 2021-01-12 | 2021-01-09 | 2021-01-12 |  | Cohu MY | Gen | BUY/FAB | 8307734101 | BAR,Z PUSHER-LEFT | 1
PUS7448 | 2020-12-22 | 2021-01-13 | 2021-01-13 | 2021-01-08 | 2021-01-13 |  | Cohu US | Gen | Module ASM | 8330271001 | GRIPPER, ASSEMBLY 2 | 5
PMY38980 | 2020-12-17 | 2021-01-05 | 2021-01-14 | 2021-01-09 | 2021-01-14 |  | Cohu MY | Ronna | Cable ASM | 8301876003 | CABLE ASSY, 208VAC SHTL | 5
PUS7377 | 2020-12-19 | 2020-12-18 | 2021-02-21 | 2021-01-08 | 2021-01-15 |  | Cohu US | Gen | Module ASM | 8335547901 | KIT,UPS PHASEOUT,JLP | 3
PMY32957 | 2020-11-17 | 2021-01-19 | 2021-01-19 | 2021-01-16 | 2021-01-19 |  | Cohu MY | Ronna | Cable ASM | 8330575002 | SENSOR ASSY,IND,CART | 1
PMY36722 | 2020-12-04 | 2020-12-29 | 2021-01-20 | 2021-01-17 | 2021-01-20 |  | Cohu MY | Ronna | Cable ASM | 8301876001 | CABLE ASSY, 208VAC SHTL | 4
PMY34754 | 2020-11-26 | 2021-01-21 | 2021-01-21 | 2021-01-18 | 2021-01-21 |  | Cohu MY | Gen | Module ASM | 8308980001 | PICK BODY ASSY - X8 PNP | 4
PMY34989 | 2020-11-26 | 2020-12-29 | 2020-12-29 | 2021-01-18 | 2021-01-21 |  | Cohu MY | Ronna | Cable ASM | 8301876001 | CABLE ASSY, 208VAC SHTL | 3
PMY36570 | 2020-12-07 | 2021-01-06 | 2021-01-25 | 2021-01-22 | 2021-01-25 |  | Cohu MY | Gen | BUY/FAB | 8307734101 | BAR,Z PUSHER-LEFT | 1
PMY37588 | 2020-12-09 | 2020-12-15 | 2021-01-20 | 2021-01-20 | 2021-01-25 |  | Cohu MY | Gen | Module ASM | 8335370901 | KIT,CNVR UPGR, GEN2, # | 2
PMY38373 | 2020-12-14 | 2021-01-21 | 2021-01-25 | 2021-01-20 | 2021-01-25 |  | Cohu MY | Gen | BUY/FAB | 8309022101 | SHAFT, BRAKE, PICK HEAD | 48
PMY38789 | 2020-12-14 | 2021-01-12 | 2021-01-25 | 2021-01-20 | 2021-01-25 |  | Cohu MY | Ronna | Cable ASM | 8301876001 | CABLE ASSY, 208VAC SHT | 1
PMY39111 | 2020-12-17 | 2021-01-22 | 2021-03-23 | 2021-01-22 | 2021-01-25 |  | Cohu MY | Gen | Module ASM | 100074862 | KIT,JLP GEN 2/3 TXP Y | 20
PMY34636 | 2020-11-26 | 2021-01-06 | 2021-01-07 | 2021-01-21 | 2021-01-26 |  | Cohu MY | Ronna | Cable ASM | 302023290 | SPARES KIT,CABLE ASSY | 3
PMY35951 | 2020-12-01 | 2021-01-27 | 2021-01-27 | 2021-01-24 | 2021-01-27 |  | Cohu MY | Ronna | Cable ASM | 8301876002 | CABLE ASSY, 208VAC SHT | 3
PMY35951 | 2020-12-01 | 2021-01-27 | 2021-01-27 | 2021-01-24 | 2021-01-27 |  | Cohu MY | Ronna | Cable ASM | 8301876003 | CABLE ASSY, 208VAC SHTL | 3
PUS7201 | 2020-12-15 | 2021-12-28 | 2021-01-28 | 2021-01-21 | 2021-01-28 |  | Cohu US | Gen | Module ASM | 1975222001 | ASSY,IDLER-25MM DRIVE | 10
PMY34962 | 2020-11-27 | 2021-01-29 | 2021-01-29 | 2021-01-26 | 2021-01-29 |  | Cohu MY | Gen | Module ASM | 8352246001 | ASSY,QD PLATEN,JTP | 1
PMY37362 | 2020-12-08 | 2021-01-12 | 2021-02-02 | 2021-01-30 | 2021-02-02 |  | Cohu MY | Ronna | Cable ASM | 8301876001 | CABLE ASSY, 208VAC SHTL | 1
PMY40363 | 2020-12-23 | 2021-02-03 | 2021-02-03 | 2021-01-31 | 2021-02-03 |  | Cohu MY | Gen | Module ASM | 100026168 | ASSY,QD PLATEN,JTP | 1
PMY40313 | 2020-12-23 | 2020-12-23 | 2021-02-03 | 2021-01-31 | 2021-02-03 |  | Cohu MY | Ronna | Cable ASM | 8301876001 | CABLE ASSY, 208VAC SHTL | 7
PMY37862 | 2020-12-10 | 2021-02-08 | 2021-02-08 | 2021-02-03 | 2021-02-08 |  | Cohu MY | Gen | Module ASM | 8308980001 | PICK BODY ASSY - X8 PNP | 24
PMY38500 | 2020-12-14 | 2020-12-28 | 2021-02-08 | 2021-02-03 | 2021-02-08 |  | Cohu MY | Gen | BUY/FAB | 1703057 | SPLINE, 4mm X 116.6mmL X | 62
PMY31821 | 2020-11-10 | 2020-12-15 | 2021-02-09 | 2021-02-06 | 2021-02-09 |  | Cohu MY | Joel | Module ASM | 302007274 | TRAY PLATEN QD, JTP | 1
PMY35274 | 2020-11-27 | 2021-02-09 | 2021-02-09 | 2021-02-06 | 2021-02-09 |  | Cohu MY | Gen | Module ASM | 8332812001 | VAC PROC. MATRIX II,X8 W/ | 1
PMY38503 | 2020-12-14 | 2021-02-09 | 2021-02-09 | 2021-02-04 | 2021-02-09 |  | Cohu MY | Gen | Module ASM | 8309075001 | SOFT TOUCH ASSY, FLOAT LOCK | 8
PMY39832 | 2020-12-21 | 2021-02-09 | 2021-02-09 | 2021-02-04 | 2021-02-09 |  | Cohu MY | Gen | BUY/FAB | 8307691101 | BASE,PICK BODY | 4
PMY33452 | 2020-11-19 | 2020-11-27 | 2021-02-11 | 2021-02-08 | 2021-02-11 |  | Cohu MY | Ronna | Cable ASM | 302023290 | SPARES KIT,CABLE ASSY | 3
PUS7487 | 2020-12-23 | 2021-01-20 | 2021-02-17 | 2021-02-14 | 2021-02-17 |  | Cohu US | Gen | Module ASM | 8335513901 | KIT, CONVEYOR BELT | 1
PUS7487 | 2020-12-23 | 2021-01-20 | 2021-02-17 | 2021-02-14 | 2021-02-17 |  | Cohu US | Gen | Module ASM | 8335512901 | KIT, CONVEYOR BELT | 1
PMY41079 | 2020-12-29 | 2021-02-17 | 2021-02-23 | 2021-02-18 | 2021-02-23 |  | Cohu MY | Ronna | Cable ASM | 8330512001 | CABLE ASSY,DOOR LOCK | 2
PMY41169 | 2020-12-29 | 2020-02-21 | 2021-02-23 | 2021-02-18 | 2021-02-23 |  | Cohu MY | Ronna | Cable ASM | 8301876003 | CABLE ASSY, 208VAC SHTL | 1
PMY34173 | 2020-11-23 | 2021-03-03 | 2021-03-03 | 2021-02-28 | 2021-03-03 |  | Cohu MY | Ronna | Cable ASM | 8309940001 | MOTOR ASSY, PNP-Z AXIS | 2
PMY34173 | 2020-11-23 | 2021-03-03 | 2021-03-03 | 2021-02-28 | 2021-03-03 |  | Cohu MY | Ronna | Cable ASM | 8332917001 | MOTOR ASSY, PNP-Y PITCH | 1
PMY35274 | 2020-11-27 | 2021-03-03 | 2021-03-03 | 2021-02-28 | 2021-03-03 |  | Cohu MY | Ronna | Cable ASM | 8332917001 | MOTOR ASSY, PNP-Y PITCH | 1
PMY37630 | 2020-12-09 | 2021-03-03 | 2021-03-03 | 2021-02-26 | 2021-03-03 |  | Cohu MY | Ronna | Cable ASM | 8332917001 | MOTOR ASSY, PNP-Y PITCH | 1
PMY38789 | 2020-12-14 | 2021-03-03 | 2021-03-03 | 2021-02-26 | 2021-03-03 |  | Cohu MY | Gen | Module ASM | 8330271001 | GRIPPER, ASSEMBLY 2 | 1
PMY39799 | 2020-12-21 | 2021-03-03 | 2021-03-03 | 2021-02-26 | 2021-03-03 |  | Cohu MY | Ronna | Cable ASM | 8332917001 | MOTOR ASSY, PNP-Y PITCH | 1
PMY39370 | 2020-12-17 | 2021-02-15 | 2021-03-11 | 2021-03-06 | 2021-03-11 |  | Cohu MY | Gen | Module ASM | 8308980001 | PICK BODY ASSY - X8 PNP | 2
PMY40688 | 2020-12-28 | 2021-01-08 | 2021-03-22 | 2021-03-19 | 2021-03-22 |  | Cohu MY | Gen | BUY/FAB | 1703057 | SPLINE, 4mm X 116.6mmL | 28
PMY38967 | 2020-12-17 | 2021-03-03 | 2021-03-23 | 2021-03-18 | 2021-03-23 |  | Cohu MY | Ronna | Cable ASM | 8332917001 | MOTOR ASSY, PNP-Y PITCH | 1
PMY38967 | 2020-12-17 | 2021-03-03 | 2021-03-23 | 2021-03-18 | 2021-03-23 |  | Cohu MY | Ronna | Cable ASM | 8330948001 | MOTOR ASSY, PNP X-PITCH | 1
PMY38967 | 2020-12-17 | 2021-02-02 | 2021-03-23 | 2021-03-18 | 2021-03-23 |  | Cohu MY | Ronna | Cable ASM | 8350586001 | CABLE ASSY, PNP HEAD | 20
PMY38967 | 2020-12-17 | 2021-02-02 | 2021-03-23 | 2021-03-18 | 2021-03-23 |  | Cohu MY | Ronna | Cable ASM | 8350586002 | CABLE ASSY, PNP HEAD | 20
PMY36722 | 2020-12-04 | 2021-01-26 | 2021-03-25 | 2021-03-22 | 2021-03-25 |  | Cohu MY | Ronna | Cable ASM | 8309940001 | MOTOR ASSY, PNP-Z AXIS | 2
PMY37588 | 2020-12-09 | 2020-12-15 | 2021-04-07 | 2021-04-10 | 2021-04-15 |  | Cohu MY | Gen | Module ASM | 1952309002 | CSM SUPPORT FINGERS | 2

## PNP Ramp UP (hidden)
Shipment Plan
| ww 47 Forecast | x2 per week | [5 empty] | x4 per week
| DELTA PN | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
|  | ww48 | ww49 | ww50 | ww51 | ww52 | ww01 | ww02 | ww03 | ww04 | ww05 | ww06 | ww07 | ww08 | ww09 | ww10 | ww11 | ww12 | ww13
per contarct/previous | 8307700001 | 4 | 4 | 4 | 4 | 4 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 120
| 8307700002 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 60
|  | x2 per week |  |  | x3 per week |  | x4 per week |  | x5 per week |  |  | x6 per week
New Ram Up | DELTA PN | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
|  | ww48 | ww49 | ww50 | ww51 | ww52 | ww01 | ww02 | ww03 | ww04 | ww05 | ww06 | ww07 | ww08 | ww09 | ww10 | ww11 | ww12 | ww13
| 8307700001 | 4 | 4 | 4 | 6 | 6 | 8 | 8 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 166
| 8307700002 | 2 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 83
Recommendation |  | ww48: X2 PER WEEK; ww01: X10 PER WEEK; ww06: X6 PER WEEK
| DELTA PN | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
|  | ww48 | ww49 | ww50 | ww51 | ww52 | ww01 | ww02 | ww03 | ww04 | ww05 | ww06 | ww07 | ww08 | ww09 | ww10 | ww11 | ww12 | ww13
| 8307700001 | 4 | 4 | 4 | 4 | 4 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 166
| 8307700002 | 2 | 2 | 2 | 2 | 2 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 83
|  | x2 per week |  |  | x3 per week |  | x4 per week |  | x5 per week |  |  | x6 per week
Commit | DELTA PN | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
|  | ww48 | ww49 | ww50 | ww51 | ww52 | ww01 | ww02 | ww03 | ww04 | ww05 | ww06 | ww07 | ww08 | ww09 | ww10 | ww11 | ww12 | ww13
| 8307700001 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 160
| 8307700002 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 80
Capacity
Parts with Quality Issue
Please prepare a plan (due Dec.1,2020 – 1pm) on how to ensure parts quality & availability: c/o Ricky
1. Critical parts will arrived in IQA 100% GOOD.
2. Quality issues corrected.

## Problematic (hidden)
# | PN | SAP PN | DESCRIPTION | SUPPLIER | BUYER | COMMODITY
1 | 8307691101 | ARPFAV010-MX7691101 | BASE PICK BODY | ALPHA TECHNO PRECISION | A. BERGADO | MACHINING
2 | 8308695101 | ARPFAV030-MX8695101 | MOTOR BRACKET XPITCH PNP | ALPHA TECHNO PRECISION | A. BERGADO | MACHINING
3 | 8308678101 | ARPFAV022-MX8678101 | INTERFACE PLATE TOP-X8 PNP (Output) | ALPHA TECHNO PRECISION | A. BERGADO | MACHINING
4 | 3101429 | ARPFAB1056-MX3101429 | PULLEY 15T 2MMGT 5MMID | JJC & ASSOCIATES | A. BERGADO | MECHANICAL
5 | 8308693101 | ARPFAV014-MX8693101 | DRIVE BRACKET XPITCH PNP | ALPHA TECHNO PRECISION | A. BERGADO | MACHINING
6 | 8308693102 | ARPFAV015-MX8693102 | DRIVE BRACKET XPITCH PNP | ALPHA TECHNO PRECISION | A. BERGADO | MACHINING
7 | 8308992101 | ARPFAV021-MX8992101 | INTERFACE PLATE GANTRY-PNP (Transfer) | ALPHA TECHNO PRECISION | A. BERGADO | MACHINING
8 | 8336110101 | ARPFAV018-MX6110101 | GUIDE, Y-PITCH HOSES | AAJ FABRICATION AND MACHINE SH | A. RONCAL | MACHINING
9 | 8307708101 | ARPFAV001-MX7708101 | ADAPTER BRNG TO PICK BODY | MTE TECHNOLOGY INC. | N. BUTOR | MACHINING
10 | 8307734101 | ARPFAV003-MX7734101 | BAR Z PUSHER-LEFT | ENGTEK PRECISION PHILIPPINES, INC. | N. BUTOR | MACHINING
11 | 8307735101 | ARPFAV004-MX7735101 | BAR Z PUSHER-RIGHT | ENGTEK PRECISION PHILIPPINES, INC. | N. BUTOR | MACHINING
12 | 8307710101 | ARPFAV008-MX7710101 | BASE BELT CLAMP-INNER | EFFICIENT MASCHINENTECHNIKS INC. | N. BUTOR | MACHINING
13 | 8307709101 | ARPFAV009-MX7709101 | BASE BELT CLAMP-OUTER | EFFICIENT MASCHINENTECHNIKS INC. | N. BUTOR | MACHINING
14 | 8339637101 | ARPFAV005-MX9637101 | BASE, CLUTCH BODY, PEEK | MTE TECHNOLOGY INC. | N. BUTOR | MACHINING
15 | 8307711101 | ARPFAV013-MX7711101 | CLAMP BELT-2MMX6MM | ENGTEK PRECISION PHILIPPINES, INC. | N. BUTOR | MACHINING
16 | 8307715101 | ARPFAV016-MX7715101 | FRAME X PITCH-MASTER | NSB ENGINEERING DESIGN AND FABRICATION | N. BUTOR | MACHINING
17 | 8307707101 | ARPFAV019-MX7707101 | HSNG BRNG-X DRV | ENGTEK PRECISION PHILIPPINES, INC. | N. BUTOR | MACHINING
18 | 8307707102 | ARPFAV020-MX7707102 | HSNG BRNG-X DRV | ENGTEK PRECISION PHILIPPINES, INC. | N. BUTOR | MACHINING
19 | 8307716101 | ARPFAV017-MX7716101 | FRAME X PITCH-SLAVE | NSB ENGINEERING DESIGN AND FABRICATION | N. BUTOR | MACHINING
20 | 8308324101 | ARPFAV023-MX8324101 | INTRFC BRKT Y-SLIDE-LEFT | EFFICIENT MASCHINENTECHNIKS INC. | N. BUTOR | MACHINING
21 | 8332942101 | ARPFAV025-MX2942101 | LASER SENSOR BRACKET (Transfer) | MTE TECHNOLOGY INC. | N. BUTOR | MACHINING
22 | 8335234101 | ARPFAV026-MX5234101 | LASER SENSOR COVER (Transfer) | MTE TECHNOLOGY INC. | N. BUTOR | MACHINING
23 | 8307722101 | ARPFAV028-MX7722101 | MANIFOLD IO PNP X4 | MTE TECHNOLOGY INC. | N. BUTOR | MACHINING
24 | 8332813101 | ARPFAV027-MX2813101 | MANIFOLD, X8 VAC PROCESSOR | MTE TECHNOLOGY INC. | N. BUTOR | MACHINING
25 | 8309226101 | ARPFAV029-MX9226101 | MNT PLATE, Y-AXIS NUT | MTE TECHNOLOGY INC. | N. BUTOR | MACHINING
26 | 8334365101 | ARPFAV031-MX4365101 | MOTOR BRACKET, Y PITCH SIZE 17 | ENGTEK PRECISION PHILIPPINES, INC. | N. BUTOR | MACHINING
27 | 8309106101 | ARPFAV034-MX9106101 | PISTON BRAKE-X8 | DRZ PRECISION TOOLINGS, INC. | N. BUTOR | MACHINING
28 | 8308254101 | ARPFAV036-MX8254101 | PULLEY 45T 2MM GT2 | FIRSTEC METALLICS INC. | N. BUTOR | MACHINING
29 | 8308961101 | ARPFAV045-MX8961101 | TIP ADAPTER PNP FLOAT LOCK (Output) | ENGTEK PRECISION PHILIPPINES, INC. | N. BUTOR | MACHINING
30 | 8307733101 | ARPFAV002-MX7733101 | BAR PUSHER-VC INTERFACE | EFFICIENT MASCHINENTECHNIKS INC. | N. BUTOR | MACHINING
31 | 8307727101 | ARPFAV038-MX7727101 | SHAFT 4MM-PULLEY DRV CFG | MTE TECHNOLOGY INC. | N. BUTOR | MACHINING
32 | 8307727102 | ARPFAV039-MX7727102 | SHAFT 4MM-PULLEY DRV CFG | MTE TECHNOLOGY INC. | N. BUTOR | MACHINING
33 | 8307727103 | ARPFAV040-MX7727103 | SHAFT 4MM-PULLEY DRV CFG | MTE TECHNOLOGY INC. | N. BUTOR | MACHINING
34 | 8307727104 | ARPFAV041-MX7727104 | SHAFT 4MM-PULLEY DRV CFG | MTE TECHNOLOGY INC. | N. BUTOR | MACHINING
35 | 8308325101 | ARPFAV024-MX8325101 | INTRFC BRKT Y-SLIDE-RIGHT | EFFICIENT MASCHINENTECHNIKS INC. | N. BUTOR | MACHINING
36 | 8309022101 | ARPFAV037-MX9022101 | SHAFT BRAKE PICK HEAD | MTE TECHNOLOGY INC. | N. BUTOR | MACHINING
37 | 8308679101 | ARPFAV032-MX8679101 | MOTOR BRACKET Z-AXIS PNP | MTE TECHNOLOGY INC. | N. BUTOR | MACHINING
38 | 8307731101 | ARPFAV042-MX7731101 | SIDE PLATE LEFT-X8 PNP | NSB ENGINEERING DESIGN AND FABRICATION | N. BUTOR | MACHINING
39 | 8307732101 | ARPFAV043-MX7732101 | SIDE PLATE RIGHT-X8 PNP | NSB ENGINEERING DESIGN AND FABRICATION | N. BUTOR | MACHINING
40 | 8309002101 | ARPFAV044-MX9002101 | THETA ADJ ECC PIN (Output) | ENGTEK PRECISION PHILIPPINES, INC. | N. BUTOR | MACHINING
41 | 8339636101 | ARPFAV035-MX9636101 | PLUG, EXTENDED BRAKE, PICK HD | MTE TECHNOLOGY INC. | N. BUTOR | MACHINING
42 | 8308961102 | ARPFAV046-MX8961102 | TIP ADAPTER PNP FLOAT LOCK (Transfer) | ENGTEK PRECISION PHILIPPINES, INC. | N. BUTOR | MACHINING
43 | 8332814101 | ARPFAM277-MX32814101 | CLAMP PLATE, X4 VENTURIS | MTE TECHNOLOGY INC. | N. BUTOR | SHEET METAL
44 | 8309165101 | ARPFAM272-MX09165101 | BRACKET PCB VAC PROCESSOR | MTE TECHNOLOGY INC. | N. BUTOR | SHEET METAL

## LLT Parts (hidden)
LLT Parts Constraint
P/N | Description | EQPA per head | SOH can support until | Open PO can support until | ETA Open PO | Risk | Heads to Build after SOH | Proposed to Buy | Remarks
8332917001 | MOTOR ASSY, PNP-Y PITCH | 1 | WW03 | WW10 | 2020-12-10 | Low
3101429 | PULLEY 15T 2MMGT 5MMID | 2 | WW 4 | WW 7 | 2021-01-06 | Low
8308249101 | LINEAR WAY 7 X 85MM C2 (RAIL) | 2 | WW 50 | WW 4 | 2020-12-08 | Medium | 12 | 24 | Support WW 51 if supplier commit date slides
4300125 | SEAL U-CUP 1/16X1/4X3/8 | 8 | WW 51 | WW 5 | 2021-01-06 | High | 60 | 480 | Increased LT from 4 to 9. Already raised concern to Cohu
1411653 | Encoder 2000 Lines .25In Shaft | 1 | WW02 | WW05 | 2020-12-26 | Low
2101298 | Motor Size 23 2.5Vdc 1Inlead (2101298) | 1 | WW02 | WW04 | 2020-12-03 | Low
3602585 | VACUUM-MICRO FLOW AND CAVITY | 8 | WW 2 | WW 6 | 2020-12-19 | Low
8308251101 | LINEAR WAY SIZE14W X 240MM C4 | 2 | WW 3 | WW 4 | 2020-12-19 | Low
2101306 | Motor Size 17 2.33Vdc Hybrid (2101306) | 1 | WW03 | WW10 | 2020-12-10 | Low
8309940001 | MOTOR ASSY PNP-Z AXIS | 1 | WW02 | WW05 | 2020-12-26 | Low
8308250101 | LINEAR WAY SIZE7 X 130MM C2 | 2 | WW03 | WW 7 | 2020-01-05 | Low
8330948001 | MOTOR ASSY PNP X-PITCH | 1 | WW04 | WW05 | 2020-12-18 | Low
8309939001 | MOTOR ASSY PNP X-PITCHB | 1 | WW04 | WW05 | 2020-12-18 | Low
2101184 | FAN GUARD,40MM | 2 | WW 4 | WW 7 | 2020-12-22 | Low
1503821 | CABLE, FLAT FLEX 12POS 1MM 5 | 1 | WW 5 | WW 7 | 2020-12-22 | Low
3101395 | PULLEY 2MM PITCH 6MM WIDE BELT | 10 | WW 6 | WW 9 | 2020-12-14 | Low
3101495 | BELT,2mmGTx6x80T, TRUMOTION | 2 | WW 7 | WW 9 | 2021-01-19 | Low
3101400 | DRIVE BELT 2MMP X 235T | 2 | WW 7 | WW 9 | 2021-01-19 | Low
3401308 | BEARING,BALL,4MMID,9MMOD, 4MM | 16 | WW 10 | WW 14 | 2021-01-19 | Low

## Slot Plan NOv 12 (hidden)
Unit Number | Entity | SO # | Cohu MY PO to PIMES | SITE | New Stock Code/Cofig | DESCRIPTION | Intel Requested Monitor Side | Intel PO# | Qtr. | MY WW | MY Need date | P'IMES Commit as of Nov 12 | Transit Mode | STATUS
JTP 22 | JTP502 JTP50201 | 100025330 | PMY16743 | KM | 302009770 | JTP #22 | Center | 4200205099 | Q4 | 47 | 2020-11-20 | 2020-11-20 | AIR | FG
JTP 23 | JTP101 | 100037170 | PMY25734 | CR | 302009770 | JTP #23 | Center | 4200207278 | Q4 | 51 | 2020-12-17 | 2020-12-17 | AIR | WIP
JTP 24 | JTP10951 | 100044116 | PMY31689 | PG | 302009770 | JTP (#24) | Center | 4200209592 | Q1 | 7 | 2021-02-11 | 2021-02-11 | AIR
JLP 655 | JLP81302 | 100025327 | PMY16681 | PG | 302009764 | JEDEC LP REV3 W/ MTP + AIR KNIFE | Left | 4200205098 | Q4 | 46 | 2020-11-12 | 2020-11-12 | AIR | SHIP
JLP 656 | JLP81301 | 100025615 | PMY16766 | PG | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200205089 | Q4 | 46 | 2020-11-12 | 2020-11-12 | AIR | SHIP
JLP 657 | JLP40762 | 100030516 | PMY20012 | PG | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200205973 | Q4 | 47 | 2020-11-16 | 2020-11-16 | AIR
JLP 658 | JLP40761 | 100031203 | PMY20483 | PG | 302009765 | JEDEC LP REV3 | Right | 4200206133 | Q4 | 47 | 2020-11-16 | 2020-11-16 | AIR
JLP 659 | JLP50304 | 100025322 | PMY16689 | KM | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200205093 | Q4 | 48 | 2020-11-23 | 2020-11-23 | AIR
JLP 660 | JLP50207 | 100025323 | PMY16693 | KM | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200205096 | Q4 | 48 | 2020-11-23 | 2020-11-23 | AIR
JLP 661 | JLP50303 | 100025325 | PMY16744 | KM | 302009765 | JEDEC LP REV3 | Right | 4200205097 | Q4 | 48 | 2020-11-23 | 2020-11-23 | AIR
JLP 662 | JLP00217 | 100038336 | PMY26512 | VN | 302009765 | JEDEC LP REV3 | Right | 4200207523 | Q4 | 48 | 2020-11-24 | 2020-11-24 | OCEAN
JLP 663 | JLP101b | 100038337 | PMY26513 | CR | 302009763 | JEDEC LP REV3 W/ MTP | LEFT | 4200207525 | Q4 | 48 | 2020-11-27 | 2020-11-27 | AIR
JLP 664 | JLP101a | 100038715 | PMY26632 | CR | 302009765 | JEDEC LP REV3 | Right | 4200207709 | Q4 | 48 | 2020-11-27 | 2020-11-27 | AIR
JLP 665 | JLP302 | 100038716 | PMY26514 | CR | 302009765 | JEDEC LP REV3 | Left | 4200207710 | Q4 | 48 | 2020-11-27 | 2020-11-27 | AIR
JLP 666 | JLP00218 | 100038718 | PMY26635 | VN | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200207711 | Q4 | 48 | 2020-11-27 | 2020-11-27 | OCEAN
JLP 667 | JLP301 | 100039100 | PMY27277 | CR | 302009765 | JEDEC LP REV3 | TBD | 4200207915 | Q4 | 48 | 2020-11-27 | 2020-11-27 | AIR
JLP 668 | JLP70153 | 100036877 | PMY25290 | CD | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200207185 | Q4 | 50 | 2020-12-11 | 2020-12-11 | AIR
JLP 669 | JLP70152 | 100036885 | PMY25732 | CD | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200207186 | Q4 | 50 | 2020-12-11 | 2020-12-11 | AIR
JLP 670 | JLP70149 | 100036888 | PMY25331 | CD | 302009767 | JEDEC LP REV3 W/ AIR KNIFE+ FLIPPER | Left | 4200207187 | Q4 | 50 | 2020-12-11 | 2020-12-11 | AIR
JLP 671 | JLP70148 | 100036891 | PMY25332 | CD | 302009766 | JEDEC LP REV3 W/ FLIPPER | Right | 4200207189 | Q4 | 50 | 2020-12-11 | 2020-12-11 | AIR
JLP 672 | JLP00314 | 100038528 | PMY26631 | CH | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200207596 | Q4 | 50 | 2020-12-11 | 2020-12-11 | AIR
JLP 673 | JLP00239 | 100042888 | PMY30883 | VN | 302009763 | JEDEC LP REV3 W/ MTP | LEFT | 4200209231 | Q4 | 50 | 2020-12-11 | 2020-12-11 | Ocean
JLP 674 | JLP00240 | 100042900 | PMY30884 | VN | 302009763 | JEDEC LP REV3 W/ MTP | RIGHT | 4200209236 | Q4 | 50 | 2020-12-11 | 2020-12-11 | Ocean
JLP 675 | JLP00219 | 100042894 | PMY30888 | VN | 302009765 | JEDEC LP REV3 | RIGHT | 4200209233 | Q4 | 51 | 2020-12-15 | 2020-12-15 | Ocean
JLP 676 | JLP101b | 100042930 | PMY30889 | CR | 302009763 | JEDEC LP REV3 W/ MTP | TBD | 4200209241 | Q4 | 51 | 2020-12-15 | 2020-12-15 | Air
JLP 677 | JLP101a | 100042908 | PMY30892 | CR | 302009763 | JEDEC LP REV3 W/ MTP | TBD | 4200209237 | Q4 | 51 | 2020-12-15 | 2020-12-15 | Air
JLP 678 | JLP00315 | 100038532 | PMY26520 | CH | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200207600 | Q4 | 51 | 2020-12-17 | 2020-12-17 | AIR
JLP 679 | JLP20202 | 100039626 | PMY27694 | PG | 302009767 | JEDEC LP REV3 W/ AIR KNIFE+ FLIPPER | Left | 4200207963 | Q4 | 51 | 2020-12-17 | 2020-12-17 | AIR
JLP 680 | JLP20201 | 100039630 | PMY27478 | PG | 302009766 | JEDEC LP REV3 W/ FLIPPER | Right | 4200207964 | Q4 | 51 | 2020-12-17 | 2020-12-17 | AIR
JLP 681 | JLP00220 | 100042898 | PMY30894 | VN | 302009763 | JEDEC LP REV3 W/ MTP | LEFT | 4200209234 | Q4 | 52 | 2020-12-21 | 2020-12-21 | Ocean
JLP 682 | JLP101 | 100042941 | PMY30893 | CR | 302009765 | JEDEC LP REV3 | TBD | 4200209244 | Q4 | 52 | 2020-12-23 | 2020-12-23 | Air
JLP 683 | JLP00241 | 100042889 | PMY30895 | VN | 302009763 | JEDEC LP REV3 W/ MTP | RIGHT | 4200209232 | Q4 | 53 | 2020-12-28 | 2020-12-28 | Ocean
JLP 684 | JLP00242 | 100042902 | PMY30896 | VN | 302009764 | JEDEC LP REV 3 W/ MTP AND IONIZER | LEFT | 4200209238 | Q4 | 53 | 2020-12-28 | 2020-12-28 | Air
JLP 685 | JLP70155 | 100044559 |  | CD | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200209864 | Q4 | 53 | 2020-12-28 | 2020-12-28
JLP 686 | JLP70154 | 100044561 |  | CD | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200209865 | Q4 | 53 | 2020-12-28 | 2020-12-28
JLP 687 | JLP00320 | 100042922 | PMY30897 | CH | 302009766 | JEDEC LP REV3 W/ FLIP | RIGHT | 4200209239 | Q1 | 2 | 2021-01-07 | 2021-01-07 | Air
JLP 688 | JLP00322 | 100043294 | PMY31037 | CH | 302027911 | JEDEC LP REV3 W/FLIP, MTP AND IONIZER | RIGHT | 4200209240 | Q1 | 2 | 2021-01-07 | 2021-01-07 | Air
JLP 689 | JLP00321 | 100042932 | PMY30898 | CH | 302009767 | JEDEC LP REV3 W/ FLIP AND IONIZER | LEFT | 4200209243 | Q1 | 2 | 2021-01-07 | 2021-01-07 | Air
JLP 690 | JLP50205 | 100042881 | PMY30899 | KM | 302009763 | JEDEC LP REV3 W/ MTP | RIGHT | 4200209229 | Q1 | 2 | 2021-01-07 | 2021-01-07 | Air
JLP 691 | JLP50206 | 100042885 | PMY30900 | KM | 302009764 | JEDEC LP REV3 W/ MTP AND IONIZER | Left | 4200209230 | Q1 | 2 | 2021-01-07 | 2021-01-07 | Air
JLP 692 | JLP31012 | 100044114 | PMY31690 | PG | 302009764 | JEDEC LP REV 3 W/ MTP AND IONIZER | Left | 4200209589 | Q1 | 3 | 2021-01-14 | 2021-01-14 | AIR
JLP 693 | JLP31011 | 100044115 | PMY31723 | PG | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200209590 | Q1 | 3 | 2021-01-14 | 2021-01-14 | AIR
JLP 694 | JLP10951 | 100044117 | PMY31748 | PG | 302009765 | JEDEC LP REV3 | Left | 4200209593 | Q1 | 3 | 2021-01-14 | 2021-01-14 | AIR
JLP 695 | JLP70151 | 100044547 |  | CD | 302009764 | JEDEC LP REV 3 W/ MTP AND IONIZER | Left | 4200209859 | Q1 | 3 | 2021-01-14 | 2021-01-14
JLP 696 | JLP70150 | 100044557 |  | CD | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200209862 | Q1 | 3 | 2021-01-14 | 2021-01-14

## Slot Plan Nov 9 (hidden)
what P | Entity | SO # | Cohu MY PO to PIMES | SITE | New Stock Code/Cofig | DESCRIPTION | Intel Requested Monitor Side | Intel PO# | Qtr. | MY WW | MY Need date | P'IMES Commit as of Nov 3 | Status | Transit Mode | SN# | P.IMES Shipped Date
JTP | JTP502 JTP50201 | 100025330 | PMY16743 | KM | 302009770 | JTP #22 | Center | 4200205099 | Q4 | 47 | 2020-11-20 | 2020-11-20 |  | AIR
JTP | JTP101 | 100037170 | PMY25734 | CR | 302009770 | JTP #23 | Center | 4200207278 | Q4 | 51 | 2020-12-17 | 2020-12-17 |  | AIR
JTP | JTP10951 | 100044116 |  | PG | 302009770 | JTP (#24) |  | 4200209592 | Q1 | 7 | 2021-02-11 | 2021-02-11 |  | AIR
JLP 655 | JLP81302 | 100025327 | PMY16681 | PG | 302009764 | JEDEC LP REV3 W/ MTP + AIR KNIFE | Left | 4200205098 | Q4 | 46 | 2020-11-12 | 2020-11-12 |  | AIR
JLP 656 | JLP81301 | 100025615 | PMY16766 | PG | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200205089 | Q4 | 46 | 2020-11-12 | 2020-11-12 |  | AIR
JLP 657 | JLP40762 | 100030516 | PMY20012 | PG | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200205973 | Q4 | 47 | 2020-11-16 | 2020-11-16 |  | AIR
JLP 658 | JLP40761 | 100031203 | PMY20483 | PG | 302009765 | JEDEC LP REV3 | Right | 4200206133 | Q4 | 47 | 2020-11-16 | 2020-11-16 |  | AIR
JLP 659 | JLP50304 | 100025322 | PMY16689 | KM | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200205093 | Q4 | 48 | 2020-11-23 | 2020-11-23 |  | AIR
JLP 660 | JLP50207 | 100025323 | PMY16693 | KM | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200205096 | Q4 | 48 | 2020-11-23 | 2020-11-23 |  | AIR
JLP 661 | JLP50303 | 100025325 | PMY16744 | KM | 302009765 | JEDEC LP REV3 | Right | 4200205097 | Q4 | 48 | 2020-11-23 | 2020-11-23 |  | AIR
JLP 662 | JLP00217 | 100038336 | PMY26512 | VN | 302009765 | JEDEC LP REV3 | Right | 4200207523 | Q4 | 48 | 2020-11-24 | 2020-11-24 |  | OCEAN
JLP 663 | JLP00218 | 100038718 | PMY26635 | VN | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200207711 | Q4 | 48 | 2020-11-27 | 2020-11-24 |  | OCEAN
JLP 664 | JLP101b | 100038337 | PMY26513 | CR | 302009763 | JEDEC LP REV3 W/ MTP | LEFT | 4200207525 | Q4 | 48 | 2020-11-27 | 2020-11-27 |  | AIR
JLP 665 | JLP101a | 100038715 | PMY26632 | CR | 302009765 | JEDEC LP REV3 | Right | 4200207709 | Q4 | 48 | 2020-11-27 | 2020-11-27 |  | AIR
JLP 666 | JLP302 | 100038716 | PMY26514 | CR | 302009765 | JEDEC LP REV3 | Left | 4200207710 | Q4 | 48 | 2020-11-27 | 2020-11-27 |  | AIR
JLP 667 | JLP301 | 100039100 | PMY27277 | CR | 302009765 | JEDEC LP REV3 | TBD | 4200207915 | Q4 | 48 | 2020-11-27 | 2020-11-27 |  | AIR
JLP 668 | JLP70153 | 100036877 | PMY25290 | CD | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200207185 | Q4 | 50 | 2020-12-11 | 2020-12-11 |  | AIR
JLP 669 | JLP70152 | 100036885 | PMY25732 | CD | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200207186 | Q4 | 50 | 2020-12-11 | 2020-12-11 |  | AIR
JLP 670 | JLP70149 | 100036888 | PMY25331 | CD | 302009767 | JEDEC LP REV3 W/ AIR KNIFE+ FLIPPER | Left | 4200207187 | Q4 | 50 | 2020-12-11 | 2020-12-11 |  | AIR
JLP 671 | JLP70148 | 100036891 | PMY25332 | CD | 302009766 | JEDEC LP REV3 W/ FLIPPER | Right | 4200207189 | Q4 | 50 | 2020-12-11 | 2020-12-11 |  | AIR
JLP 672 | JLP00314 | 100038528 | PMY26631 | CH | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200207596 | Q4 | 50 | 2020-12-11 | 2020-12-11 |  | AIR
JLP 673 | JLP00239 | 100042888 | PMY30883 | VN | 302009763 | JEDEC LP REV3 W/ MTP | LEFT | 4200209231 | Q4 | 50 | 2020-12-11 | 2020-12-11 |  | Ocean
JLP 674 | JLP00240 | 100042900 | PMY30884 | VN | 302009763 | JEDEC LP REV3 W/ MTP | RIGHT | 4200209236 | Q4 | 50 | 2020-12-11 | 2020-12-11 |  | Ocean
JLP 675 | JLP00315 | 100038532 | PMY26520 | CH | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200207600 | Q4 | 51 | 2020-12-17 | 2020-12-11 |  | AIR
JLP 676 | JLP00219 | 100042894 | PMY30888 | VN | 302009765 | JEDEC LP REV3 | RIGHT | 4200209233 | Q4 | 51 | 2020-12-15 | 2020-12-15 |  | Ocean
JLP 677 | JLP101b | 100042930 | PMY30889 | CR | 302009763 | JEDEC LP REV3 W/ MTP | TBD | 4200209241 | Q4 | 51 | 2020-12-15 | 2020-12-15 |  | Air
JLP 678 | JLP101a | 100042908 | PMY30892 | CR | 302009763 | JEDEC LP REV3 W/ MTP | TBD | 4200209237 | Q4 | 51 | 2020-12-15 | 2020-12-15 |  | Air
JLP 679 | JLP00220 | 100042898 | PMY30894 | VN | 302009763 | JEDEC LP REV3 W/ MTP | LEFT | 4200209234 | Q4 | 52 | 2020-12-21 | 2020-12-15 |  | Ocean
JLP 680 | JLP20202 | 100039626 | PMY27694 | PG | 302009767 | JEDEC LP REV3 W/ AIR KNIFE+ FLIPPER | Left | 4200207963 | Q4 | 51 | 2020-12-17 | 2020-12-17 |  | AIR
JLP 681 | JLP20201 | 100039630 | PMY27478 | PG | 302009766 | JEDEC LP REV3 W/ FLIPPER | Right | 4200207964 | Q4 | 51 | 2020-12-17 | 2020-12-17 |  | AIR
JLP 682 | JLP101 | 100042941 | PMY30893 | CR | 302009765 | JEDEC LP REV3 | TBD | 4200209244 | Q4 | 52 | 2020-12-23 | 2020-12-23 |  | Air
JLP 683 | JLP00241 | 100042889 | PMY30895 | VN | 302009763 | JEDEC LP REV3 W/ MTP | RIGHT | 4200209232 | Q4 | 53 | 2020-12-28 | 2020-12-23 |  | Ocean
JLP 684 | JLP00242 | 100042902 | PMY30896 | VN | 302009764 | JEDEC LP REV 3 W/ MTP AND IONIZER | LEFT | 4200209238 | Q4 | 53 | 2020-12-28 | 2020-12-23 |  | Air
JLP 685 | JLP00320 | 100042922 | PMY30897 | CH | 302009766 | JEDEC LP REV3 W/ FLIP | RIGHT | 4200209239 | Q1 | 2 | 2021-01-07 | 2021-01-07 |  | Air
JLP 686 | JLP00322 | 100043294 | PMY31037 | CH | 302027911 | JEDEC LP REV3 W/FLIP, MTP AND IONIZER | RIGHT | 4200209240 | Q1 | 2 | 2021-01-07 | 2021-01-07 |  | Air
JLP 687 | JLP00321 | 100042932 | PMY30898 | CH | 302009767 | JEDEC LP REV3 W/ FLIP AND IONIZER | LEFT | 4200209243 | Q1 | 2 | 2021-01-07 | 2021-01-07 |  | Air
JLP 688 | JLP50205 | 100042881 | PMY30899 | KM | 302009763 | JEDEC LP REV3 W/ MTP | RIGHT | 4200209229 | Q1 | 2 | 2021-01-07 | 2021-01-07 |  | Air
JLP 689 | JLP50206 | 100042885 | PMY30900 | KM | 302009764 | JEDEC LP REV3 W/ MTP AND IONIZER | Left | 4200209230 | Q1 | 2 | 2021-01-07 | 2021-01-07 |  | Air
JLP 690 | JLP31012 | 100044114 |  | PG | 302009764 | JEDEC LP REV 3 W/ MTP AND IONIZER | Left | 4200209589 | Q1 | 3 | 2021-01-14 | 2021-01-14 |  | AIR
JLP 691 | JLP31011 | 100044115 |  | PG | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200209590 | Q1 | 3 | 2021-01-14 | 2021-01-14 |  | AIR
JLP 692 | JLP10951 | 100044117 |  | PG | 302009765 | JEDEC LP REV3 | Left | 4200209593 | Q1 | 3 | 2021-01-14 | 2021-01-14 |  | AIR

## slot Plan Nov 5 (hidden)
PIMES JLP No | Entity | SO # | Cohu MY PO to PIMES | SITE | New Stock Code/Cofig | DESCRIPTION | Intel Requested Monitor Side | Intel PO# | Qtr. | MY WW | Pick up date 11/4 | Crating | Pick up date as of 11/5 | Status | Transit Mode | Remarks | SN#
JTP 22 | JTP502 JTP50201 | 100025330 | PMY16743 | KM | 302009770 | JTP #22 | Center | 4200205099 | Q4 | 47 | 2020-11-20 |  | 2020-11-20 |  | AIR | push out delivery to Q4.
JTP 23 | JTP101 | 100037170 | PMY25734 | CR | 302009770 | JTP #23 | Center | 4200207278 | Q4 | 51 | 2020-12-17 |  | 2020-12-17 |  | AIR
JLP 653 | JLP70146 | 100012272 | PMY12237 | CD | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200202809 | Q4 | 46 | 2020-11-08 |  | 2020-11-06 |  | AIR | for installation of FM Reduction kit
JLP 654 | JLP70147 | 100012273 | PMY12239 | CD | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200202810 | Q4 | 46 | 2020-11-08 |  | 2020-11-06 |  | AIR | for installation of FM Reduction kit
JLP 655 | JLP81301 | 100025615 | PMY16766 | PG | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200205089 | Q4 | 46 | 2020-11-12 |  | 2020-11-12 |  | AIR | for installation of FM Reduction kit
JLP 656 | JLP81302 | 100025327 | PMY16681 | PG | 302009764 | JEDEC LP REV3 W/ MTP + AIR KNIFE | Left | 4200205098 | Q4 | 46 | 2020-11-12 |  | 2020-11-12 |  | AIR | for installation of FM Reduction kit
JLP 657 | JLP40761 | 100031203 | PMY20483 | PG | 302009765 | JEDEC LP REV3 | Right | 4200206133 | Q4 | 46 | 2020-11-13 |  | 2020-11-12 |  | AIR | for installation of FM Reduction kit
JLP 658 | JLP40762 | 100030516 | PMY20012 | PG | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200205973 | Q4 | 47 | 2020-11-16 |  | 2020-11-12 |  | AIR | for installation of FM Reduction kit
JLP 659 | JLP50304 | 100025322 | PMY16689 | KM | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200205093 | Q4 | 48 | 2020-11-23 |  | 2020-11-23 |  | AIR | for installation of FM Reduction kit
JLP 660 | JLP50207 | 100025323 | PMY16693 | KM | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200205096 | Q4 | 48 | 2020-11-23 |  | 2020-11-23 |  | AIR | for installation of FM Reduction kit
JLP 661 | JLP50303 | 100025325 | PMY16744 | KM | 302009765 | JEDEC LP REV3 | Right | 4200205097 | Q4 | 48 | 2020-11-23 |  | 2020-11-23 |  | AIR | for installation of FM Reduction kit
JLP 662 | JLP00217 | 100038336 | PMY26512 | VN | 302009765 | JEDEC LP REV3 | Right | 4200207523 | Q4 | 48 | 2020-11-24 |  | 2020-11-24 |  | OCEAN | for installation of FM Reduction kit
JLP 663 | JLP101b | 100038337 | PMY26513 | CR | 302009763 | JEDEC LP REV3 W/ MTP | LEFT | 4200207525 | Q4 | 48 | 2020-11-24 |  | 2020-11-24 |  | AIR | for installation of FM Reduction kit
JLP 664 | JLP101a | 100038715 | PMY26632 | CR | 302009765 | JEDEC LP REV3 | Right | 4200207709 | Q4 | 48 | 2020-11-27 |  | 2020-11-27 |  | AIR | for installation of FM Reduction kit
JLP 665 | JLP302 | 100038716 | PMY26514 | CR | 302009765 | JEDEC LP REV3 | Left | 4200207710 | Q4 | 48 | 2020-11-27 |  | 2020-11-27 |  | AIR | for installation of FM Reduction kit
JLP 666 | JLP00218 | 100038718 | PMY26635 | VN | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200207711 | Q4 | 48 | 2020-11-27 |  | 2020-11-27 |  | OCEAN | for installation of FM Reduction kit
JLP 667 | JLP301 | 100039100 | PMY27277 | CR | 302009765 | JEDEC LP REV3 | TBD | 4200207915 | Q4 | 48 | 2020-11-27 |  | 2020-11-27 |  | AIR | for installation of FM Reduction kit
JLP 668 | JLP70153 | 100036877 | PMY25290 | CD | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200207185 | Q4 | 50 | 2020-12-11 |  | 2020-12-11 |  | AIR | for installation of FM Reduction kit
JLP 669 | JLP70152 | 100036885 | PMY25732 | CD | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200207186 | Q4 | 50 | 2020-12-11 |  | 2020-12-11 |  | AIR | for installation of FM Reduction kit
JLP 670 | JLP70149 | 100036888 | PMY25331 | CD | 302009767 | JEDEC LP REV3 W/ AIR KNIFE+ FLIPPER | Left | 4200207187 | Q4 | 50 | 2020-12-11 |  | 2020-12-11 |  | AIR | for installation of FM Reduction kit
JLP 671 | JLP70148 | 100036891 | PMY25332 | CD | 302009766 | JEDEC LP REV3 W/ FLIPPER | Right | 4200207189 | Q4 | 50 | 2020-12-11 |  | 2020-12-11 |  | AIR | for installation of FM Reduction kit
JLP 672 | JLP00314 | 100038528 | PMY26631 | CH | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200207596 | Q4 | 50 | 2020-12-11 |  | 2020-12-11 |  | AIR | for installation of FM Reduction kit
JLP 673 | JLP00239 | 100042888 | PMY30883 | VN | 302009763 | JEDEC LP REV3 W/ MTP | LEFT | 4200209231 | Q4 | 50 | 2020-12-11 |  | 2020-12-11 |  | Ocean
JLP 674 | JLP00240 | 100042900 | PMY30884 | VN | 302009763 | JEDEC LP REV3 W/ MTP | RIGHT | 4200209236 | Q4 | 50 | 2020-12-11 |  | 2020-12-11 |  | Ocean
JLP 675 | JLP00219 | 100042894 | PMY30888 | VN | 302009765 | JEDEC LP REV3 | RIGHT | 4200209233 | Q4 | 51 | 2020-12-15 |  | 2020-12-15 |  | Ocean
JLP 676 | JLP101b | 100042930 | PMY30889 | CR | 302009763 | JEDEC LP REV3 W/ MTP | TBD | 4200209241 | Q4 | 51 | 2020-12-15 |  | 2020-12-15 |  | Air
JLP 677 | JLP101a | 100042908 | PMY30892 | CR | 302009763 | JEDEC LP REV3 W/ MTP | TBD | 4200209237 | Q4 | 51 | 2020-12-15 |  | 2020-12-15 |  | Air
JLP 678 | JLP00315 | 100038532 | PMY26520 | CH | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200207600 | Q4 | 51 | 2020-12-17 |  | 2020-12-17 |  | AIR | for installation of FM Reduction kit
JLP 679 | JLP20202 | 100039626 | PMY27694 | PG | 302009767 | JEDEC LP REV3 W/ AIR KNIFE+ FLIPPER | Left | 4200207963 | Q4 | 51 | 2020-12-17 |  | 2020-12-17 |  | AIR
JLP 680 | JLP20201 | 100039630 | PMY27478 | PG | 302009766 | JEDEC LP REV3 W/ FLIPPER | Right | 4200207964 | Q4 | 51 | 2020-12-17 |  | 2020-12-17 |  | AIR
JLP 681 | JLP00220 | 100042898 | PMY30894 | VN | 302009763 | JEDEC LP REV3 W/ MTP | LEFT | 4200209234 | Q4 | 52 | 2020-12-21 |  | 2020-12-23 |  | Ocean
JLP 682 | JLP101 | 100042941 | PMY30893 | CR | 302009765 | JEDEC LP REV3 | TBD | 4200209244 | Q4 | 52 | 2020-12-23 |  | 2020-12-23 |  | Air
JLP 683 | JLP00241 | 100042889 | PMY30895 | VN | 302009763 | JEDEC LP REV3 W/ MTP | RIGHT | 4200209232 | Q4 | 53 | 2020-12-28 |  | 2020-12-23 |  | Ocean
JLP 684 | JLP00242 | 100042902 | PMY30896 | VN | 302009764 | JEDEC LP REV 3 W/ MTP AND IONIZER | LEFT | 4200209238 | Q4 | 53 | 2020-12-28 |  | 2020-12-23 |  | Air
JLP 685 | JLP00320 | 100042922 | PMY30897 | CH | 302009766 | JEDEC LP REV3 W/ FLIP | RIGHT | 4200209239 | Q1 | 2 | 2021-01-07 |  | 2021-01-07 |  | Air
JLP 686 | JLP00322 | TBD |  | CH |  | JEDEC LP REV3 W/FLIP, MTP AND IONIZER | RIGHT | 4200209240 | Q1 | 2 | 2021-01-07 |  | 2021-01-07 |  | Air
JLP 687 | JLP00321 | 100042932 | PMY30898 | CH | 302009767 | JEDEC LP REV3 W/ FLIP AND IONIZER | LEFT | 4200209243 | Q1 | 2 | 2021-01-07 |  | 2021-01-07 |  | Air
JLP 688 | JLP50205 | 100042881 | PMY30899 | KM | 302009763 | JEDEC LP REV3 W/ MTP | RIGHT | 4200209229 | Q1 | 2 | 2021-01-07 |  | 2021-01-07 |  | Air
JLP 689 | JLP50206 | 100042885 | PMY30900 | KM | 302009764 | JEDEC LP REV3 W/ MTP AND IONIZER | Left | 4200209230 | Q1 | 2 | 2021-01-07 |  | 2021-01-07 |  | Air
707

## SUMMARY (hidden)
ADVANCE TECHNOLOGY SOLUTIONS
DEMAND PLANNING AND INVENTORY CONTROL
PLAN VS. ACTUAL OUTPUT
NO. | PROJECT | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01
1 | JLP | 55%
2 | JTP | 50%
3 | FLIPPER | -
3 | MTP | 72%
4 | IONIZER | 77%
5 | MATRIX | 115%

## JTP Slot Plan
JTP Number Mark | Entity | SO # | Cohu MY PO to PIMES | SITE | New Stock Code/Cofig | DESCRIPTION | Intel Requested Monitor Side | Intel PO# | MY Need date | Transit Mode | P.IMES Commit
JTP 38 | JTP11051 | 100110473 | PMY93390 | PG | 302034315 | JTP CONFIG 1 PLATEN WITH LIGHT | Center | 4200237745 | 2022-05-19 | AIR | 2022-05-26
JTP 39 | JTP10951 | 100110476 | PMY93415 | PG | 302034315 | JTP CONFIG 1 PLATEN WITH LIGHT | Center | 4200237748 | 2022-05-19 | AIR | 2022-05-26
JTP 40 | JTP00007 | 100145852 | TBA | CR | 302034315 | JTP CONFIG 1 PLATEN WITH LIGHT | Center | 4200264344 | 2022-08-24 | AIR | 2022-08-24
JTP 41 | JTP80101 | 100137042 | TBA | KM | 302034315 | JTP CONFIG 1 PLATEN WITH LIGHT | Center | 4200258032 | 2023-11-16 | AIR | 2023-11-16
JTP 42 | JTP80102 | 100137043 | TBA | KM | 302034315 | JTP CONFIG 1 PLATEN WITH LIGHT | Center | 4200258034 | 2023-11-16 | AIR | 2023-11-16

## PNP Shipment (hidden)
Status | Shipped | On-going
Work Week | WW 21 | WW 21
| 2023-05-24 | 2023-05-27
8307700001 I/O | 7 | 6
8307700002 TFR | 3 | 5
Total Heads | 10 | 11
Formulas:
Shipped = "WW"&" "&WEEKNUM([Shipped, row below])

## OLB Slot Plan
Entity | SO # | Cohu MY PO to PIMES | SITE | New Stock Code/Cofig | DESCRIPTION | Intel PO# | MY Need date | Transit Mode | P.IMES Commit
DOB802 | 100136503 | TBA | KM | 100006503 | OLB#44 | 4200257699 | 2023-11-13 | AIR | 2023-11-13
DOB802 | 100136503 | TBA | KM | 100006504 | OLB#44 ( ABLP) | 4200257699 | 2023-11-13 | AIR | 2023-11-13
DOB801 | 100136504 | TBA | KM | 100006503 | OLB#45 | 4200257697 | 2023-11-13 | AIR | 2023-11-13
DOB801 | 100136504 | TBA | KM | 100006504 | OLB#45 ( ABLP) | 4200257697 | 2023-11-13 | AIR | 2023-11-13

## REvision
Control Number | Revision Date | Product | WW | Revision Details
MS 2023_0074 | 2023-07-10 | All product | WW28~ | Update Customer latest firm order and shipment Shipped x3 heads-PNP
MS 2023_0073 | 2023-07-03 | All product | WW27~ | Update Customer latest firm order Additional x2-JLP and MTP
MS 2023_0072 rev. 1 | 2023-06-19 | PNP Matrix | WW25 | Revised Build Plan
MS 2023_0072 | 2023-06-19 | All product | WW26 | Update shipment and customer order
MS 2023_0071 rev.1 | 2023-06-15 | PNP Matrix | WW25 | Revised build for PNP Matrix 6 heads/week-Q3 9 heads/week-Q4
MS 2023_0071 | 2023-06-14 | PNP Matrix | WW25 | Additional build for PNP Matrix WW25
MS 2023_0070 | 2023-06-02 | PNP Matrix | WW22~ | No build plan WK25-WW26
MS 2023_0069 | 2023-05-29 | All product | WW21~ | Update latest build and shipment
MS 2022_0068 | 2023-05-24 | PNP/JLP | WW21~ | Update latest build
MS 2022_0067 | 2023-05-15 | All product | WW20~ | Update latest customer order
MS 2022_0066 | 2023-05-02 | All product | WW18~ | No revision on build plan
MS 2022_0065 | 2023-04-28 | Matrix | WW21~ | Revised build from 9/week to 12/week
MS 2022_0064 | 2023-04-25 | JLP | WW20~ | No build plan WK20-WK22 No build plan WK26-WK28
MS 2022_0063 | 2023-04-18 | All Product | WW16~ | Update shipment and customer order
MS 2022_0062 | 2023-04-13 | All Product | WW15~ | Include build plan until December 2023
MS 2022_0061 | 2023-04-03 | PNP Matrix | WW15~ | Update build for PNP Matrix, Update customer PO
MS 2022_0060 | 2023-03-27 | All Product | WW13~ | Update shipment and customer order
MS 2022_0059 | 2023-03-21 | PNP | WW17~ | No plan (no open order)
MS 2022_0058 | 2023-03-14 | PNP JLP | WW14 WW18 | Revised build from 18 heads per week to 9 heads per week Revised build from 2 per week to 1 per week
MS 2022_0057 | 2023-03-07 | All product | WW14~ | Revised build plan for Matrix from 18 heads per week to 9 heads per week
MS 2022_0056 | 2023-02-28 | All product | WW9~ | Update shipment and customer order
MS 2022_0055 | 2023-02-21 | All product | WW7~ | Update shipment and customer order
MS 2022_0054 | 2023-02-14 | All product | WW6~ | Update shipment and customer order
MS 2022_0053 | 2023-02-07 | All product | WW6~ | Update shipment and customer order
MS 2022_0052 | 2023-01-30 | All product | WW5~ | Update shipment and customer order
MS 2022_0051 | 2023-01-24 | All product | WW4~ | Update shipment and customer order
MS 2022_0050 | 2023-01-17 | All product | WW4~ | Update shipment and customer order
MS 2022_0049 | 2023-01-10 | Matrix | WW4~ | Update shipment for Matrix
MS 2022_0048 | 2023-01-04 | All product | WW1~ | Update shipment and latest customer order
MS 2022_0047 | 2022-12-20 | All product | WW51~ | Update shipment and latest customer order
MS 2022_0046 | 2022-12-13 | All product | WW50~ | Update shipment and latest customer order
MS 2022_0045 | 2022-12-06 | All product | WW49~ | Update shipment and latest customer order
MS 2022_0044 | 2022-11-09 | All product | WW48~ | Update shipment and latest customer order
MS 2022_0043 | 2022-11-09 | All product | WW45~ | Update shipment and latest customer order
MS 2022_0042 | 2022-11-04 | All product | WW45~ | Update shipment and latest customer order
MS 2022_0041 | 2022-10-11 | JTP/OLB | WW42-WW44 | Adjusted build plan for OLB and JTP from WW42-WW44
MS 2022_0040 | 2022-10-11 | Flipper | WW37-WW40 | Adjust build plan for Flipper
MS 2022_0039 | 2022-10-04 | JLP Matrix JTP | WW41~WW44 WW44 WW42 | Revised build plan from x3 to x2 Revised build plan from x24 to x36 JTP advance build
MS 2022_0038 | 2022-09-20 | All product | WW40~ | Update shipment and latest firm order
MS 2022_0037 | 2022-09-20 | OLB | WW41 | Advance build of OLB 43
|  | JLP | WW40~ | Revision of build plan due to lacking of boards and push out from customer
MS 2022_0036 | 2022-09-13 | All products | WW37~ | Update latest shipment and order
MS 2022_0035 | 2022-09-06 | All products | WW37~ WW47 WW48 | Update build plan for Ionizer due to spares requirements Advance build of JTP41 Advance build of OBL43
MS 2022_0034 | 2022-08-31 | All products | WW35~ | Update latest shipment and order
MS 2022_0033 | 2022-08-23 | All products | WW35~ | Update latest shipment and order
Control Number | Revision Date | Product | WW | Revision Details
MS 2022_0032 | 2022-08-16 | All products | WW35~ | Update latest shipment and order
Control Number | Revision Date | Product | WW | Revision Details
MS 2022_0031 | 2022-08-09 | All products | WW32~ | Update latest shipment and order
MS 2022_0030 | 2022-08-02 | All products | WW32~ | Update lastest shipment and order
Control Number | Revision Date | Product | WW | Revision Details
MS 2022_0029 | 2022-07-19 | All products | WW41~ | Additional build plan for the month of September
Control Number | Revision Date | Product | WW | Revision Details
MS 2022_0028 | 2022-07-12 | All products | WW32~ | Updated shipment and latest firm order
MS 2022_0027 | 2022-07-05 | Ionizer | WW32~ | Revised build plan due to inclusion of spares requirements
MS 2022_0026 | 2022-06-28 | All Product | WW28~ | Update shipment and latest firm order
MS 2022_0025 | 2022-06-21 | All Product | WW26 | Update customer latest firm order Revision of build plan for flipper-inclusion of spares
MS 2022_0024 | 2022-06-15 | Ionizer | WW32 | Change Build plan-inclusion of spares x6
MS 2022_0023 | 2022-06-07 | All product | WW23~ | Update shipment and customer order
MS 2022_0022 | 2022-05-30 | All product | WW21~ | Update shipment and customer order
MS 2022_0021 | 2022-05-24 | All product | WW21~ | Update shipment and customer order
MS 2022_0020 | 2022-05-17 | All product | WW21~ | Update build plan, shipment and customer order
MS 2022_0019 | 2022-05-12 | All product | WW19~ | Update shipment and customer order
MS 2022_0018 | 2022-05-05 | Options | WW19~ | Revision of build plan for options considering spares requirements
MS 2022_0017 | 2022-04-26 | JLP/Options | WW18~ | Revision of build plan and latest customer order
MS 2022_0016 | 2022-04-19 | JLP/Options | WW16~ | Update latest shipment and customer order
MS 2022_0015 | 2022-04-13 | JLP/Options | WW16~ | Update latest shipment and customer order
MS 2022_0014 | 2022-04-05 | JLP/Options | WW15~ | Update latest shipment and customer order
MS 2022_0013 | 2022-03-29 | JLP/Options | WW14~ | Update latest shipment and customer order
MS 2022_0012 | 2022-03-23 | JLP/Options | WW11~WW14 | Revision of build plan for JLP Add'l Build Plan for MTP Reducer Update latest shipment and customer order
MS 2022_0011 | 2022-03-21 | All product | WW12~ | Update shipment and latest customer P.O.
MS 2022_0010 | 2022-03-15 | All product | WW11~ | Update shipment and latest customer P.O.
MS 2022_0009 | 2022-03-08 | All product | WW11~ | Update shipment and latest customer P.O.
MS 2022_0008 | 2022-03-02 | All product | WW9~ | Update shipment and latest customer P.O.
MS 2022_0007 | 2022-02-22 | All product | WW8~ | Update shipment and latest customer P.O.
MS 2022_0006 | 2022-02-15 | All producrt | WW7~ | Update shipment and latest customer P.O. Build plan for High Mag Force
MS 2022_0005 | 2022-02-08 | JLP,MTP, IONIZER | WW21~22 | Update latest P.O.
|  | PNP | WW8~ | Revision of build plan from 12 heads to 18 heads per week
MS 2022_0004 | 2022-02-02 | All product | WW6~ | Update Actual shipment and P.O. Revision of build plan for JLP based on improved commitment
MS 2022_0003 | 2022-01-25 | All product | WW3~ | Update Actual shipment and P.O. Revision of build plan for JLP based on improved commitment
MS 2022_0002 | 2022-01-17 | All product | WW2~ | Update Actual shipment and P.O. Revision of build plan
MS 2022_0001 | 2022-01-04 | PNP | WW2 | Revision of build plan for the month of January

## PnP (hidden)
COHU REQUIREMENTS | WW | WW49 | WW50 | WW51 | WW52 | WW53 | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12
| Shipment Date |  |  |  |  | 2020-12-30 | 2021-01-04 | 2020-01-11 | 2020-01-18 | 2020-01-25 | 2020-02-01 | 2020-02-08 | 2020-02-15 | 2020-02-22 | 2020-03-01 | 2020-03-08 | 2020-03-15 | 2020-03-22
| No of Sets | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6
PnP Heads | Delivery Date | 2020-12-11 | 2020-12-18 | 2020-12-23 | 2020-12-29 | 2021-01-04 | 2021-01-06 | 2021-01-11 | 2021-01-16 | 2021-01-25 | 2021-02-01 | 2021-02-08 | 2020-02-15 | 2020-02-22 | 2020-02-29 | 2020-03-07 | 2020-03-14 | 2020-03-21
| No of Sets | 2 | 3 | 3 | 3 | 3 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6
TOTAL NEEDED QTY UNTIL FEB 01
8330050501 - PWA PNP CONTROLLER MATRIX II
8330053501 - PWA PNP Z MOTOR CONTROL
8309472501 - PWA, VAC SENSOR, MATRIX II
8307700001 | No of Heads | 4 | 6 | 6 | 6 | 6 | 8 | 10 | 10 | 10 | 10 | 12
8307700002 |  | 2 | 3 | 3 | 3 | 3 | 4 | 5 | 5 | 5 | 5 | 6
TOTAL |  | 6 | 9 | 9 | 9 | 9 | 12 | 15 | 15 | 15 | 15 | 18

## Issue (hidden)
JLP 678 | Rejected Frame, for dis assy

## Slot Plan (hidden)
| what P | Entity | SO # | Cohu MY PO to PIMES | SITE | New Stock Code/Cofig | DESCRIPTION | Intel Requested Monitor Side | Intel PO# | Qtr. | MY WW | P'IMES Commit as of Nov 17 | Transit Mode | Remarks | Cohu MY PO to PIMES | PO date | P.IMES Shipped Date | P.IMES Invoice
| JTP #22 | JTP502 JTP50201 | 100025330 | PMY16743 | KM | 302009770 | JTP #22 | Center | 4200205099 | Q4 | 47 | 2020-11-20 | AIR | push out delivery to Q4. | PMY16743
| JTP #23 | JTP101 | 100037170 | PMY25734 | CR | 302009770 | JTP #23 | Center | 4200207278 | Q4 | 51 | 2020-12-17 | AIR
JLP 698 | JTP (#24) | JTP10951 | 100044116 | PMY31689 | PG | 302009770 | JTP (#24) | Center | 4200209592 | Q1 | 7 | 2021-02-11 | AIR |  |  | 2020-11-09
| JLP658 | JLP50304 | 100025322 | PMY16689 | KM | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200205093 | Q4 | 48 | 2020-11-23 | AIR | for installation of FM Reduction kit | PMY16689 |  |  | 100025322
| JLP659 | JLP50207 | 100025323 | PMY16693 | KM | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200205096 | Q4 | 48 | 2020-11-23 | AIR | for installation of FM Reduction kit | PMY16693 |  |  | 100025323
| JLP660 | JLP50303 | 100025325 | PMY16744 | KM | 302009765 | JEDEC LP REV3 | Right | 4200205097 | Q4 | 48 | 2020-11-23 | AIR | for installation of FM Reduction kit | PMY16744 |  |  | 100025325
| JLP661 | JLP00217 | 100038336 | PMY26512 | VN | 302009765 | JEDEC LP REV3 | Right | 4200207523 | Q4 | 48 | 2020-11-21 | OCEAN | for installation of FM Reduction kit |  |  |  | 100038336
| JLP662 | JLP101b | 100038337 | PMY26513 | CR | 302009763 | JEDEC LP REV3 W/ MTP | LEFT | 4200207525 | Q4 | 47 | 2020-11-27 | AIR | for installation of FM Reduction kit |  |  |  | 100038337
| JLP663 | JLP101a | 100038715 | PMY26632 | CR | 302009765 | JEDEC LP REV3 | Right | 4200207709 | Q4 | 48 | 2020-11-27 | AIR | for installation of FM Reduction kit |  |  |  | 100038715
| JLP664 | JLP302 | 100038716 | PMY26514 | CR | 302009765 | JEDEC LP REV3 | Left | 4200207710 | Q4 | 48 | 2020-11-27 | AIR | for installation of FM Reduction kit |  |  |  | 100038716
| JLP665 | JLP00218 | 100038718 | PMY26635 | VN | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200207711 | Q4 | 48 | 2020-11-27 | OCEAN | for installation of FM Reduction kit |  |  |  | 100038718
| JLP666 | JLP301 | 100039100 | PMY27277 | CR | 302009765 | JEDEC LP REV3 | left | 4200207915 | Q4 | 48 | 2020-11-27 | AIR | for installation of FM Reduction kit |  |  |  | 100039100
| JLP667 | JLP70149 | 100036888 | PMY25331 | CD | 302009767 | JEDEC LP REV3 W/ AIR KNIFE+ FLIPPER | Left | 4200207187 | Q4 | 48 | 2020-11-30 | AIR | for installation of FM Reduction kit |  |  |  | 100036888
| JLP668 | JLP70148 | 100036891 | PMY25332 | CD | 302009766 | JEDEC LP REV3 W/ FLIPPER | Right | 4200207189 | Q4 | 48 | 2020-11-30 | AIR | for installation of FM Reduction kit |  |  |  | 100036891
| JLP669 | JLP70153 | 100036877 | PMY25290 | CD | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200207185 | Q4 | 50 | 2020-12-11 | AIR | for installation of FM Reduction kit |  |  |  | 100036877
| JLP670 | JLP70152 | 100036885 | PMY25732 | CD | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200207186 | Q4 | 50 | 2020-12-11 | AIR | for installation of FM Reduction kit |  |  |  | 100036885
| JLP671 | JLP00314 | 100038528 | PMY26631 | CH | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200207596 | Q4 | 50 | 2020-12-11 | AIR | for installation of FM Reduction kit |  |  |  | 100038528
| JLP672 | JLP00239 | 100042888 | PMY30883 | VN | 302009763 | JEDEC LP REV3 W/ MTP | LEFT | 4200209231 | Q4 | 50 | 2020-12-11 | Ocean |  |  |  |  | 100042888
| JLP673 | JLP00240 | 100042900 | PMY30884 | VN | 302009763 | JEDEC LP REV3 W/ MTP | RIGHT | 4200209236 | Q4 | 50 | 2020-12-11 | Ocean |  |  |  |  | 100042900
| JLP674 | JLP00219 | 100042894 | PMY30888 | VN | 302009765 | JEDEC LP REV3 | RIGHT | 4200209233 | Q4 | 51 | 2020-12-15 | Ocean |  |  |  |  | 100042894
| JLP675 | JLP101b | 100042930 | PMY30889 | CR | 302009763 | JEDEC LP REV3 W/ MTP | right | 4200209241 | Q4 | 51 | 2020-12-15 | Air |  |  |  |  | 100042930
| JLP676 | JLP101a | 100042908 | PMY30892 | CR | 302009763 | JEDEC LP REV3 W/ MTP | right | 4200209237 | Q4 | 51 | 2020-12-15 | Air |  |  |  |  | 100042908
| JLP677 | JLP00315 | 100038532 | PMY26520 | CH | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200207600 | Q4 | 51 | 2020-12-17 | AIR | for installation of FM Reduction kit |  |  |  | 100038532
| JLP678 | JLP20202 | 100039626 | PMY27694 | PG | 302009767 | JEDEC LP REV3 W/ AIR KNIFE+ FLIPPER | Left | 4200207963 | Q4 | 51 | 2020-12-17 | AIR |  |  |  |  | 100039626
| JLP679 | JLP20201 | 100039630 | PMY27478 | PG | 302009766 | JEDEC LP REV3 W/ FLIPPER | Right | 4200207964 | Q4 | 51 | 2020-12-17 | AIR |  |  |  |  | 100039630
| JLP680 | JLP00241 | 100042889 | PMY30895 | VN | 302009763 | JEDEC LP REV3 W/ MTP | RIGHT | 4200209232 | Q4 | 53 | 2020-12-18 | Ocean |  |  |  |  | 100042889
| JLP681 | JLP00242 | 100042902 | PMY30896 | VN | 302009764 | JEDEC LP REV 3 W/ MTP AND IONIZER | LEFT | 4200209238 | Q4 | 53 | 2020-12-18 | Air |  |  |  |  | 100042902
| JLP682 | JLP00220 | 100042898 | PMY30894 | VN | 302009763 | JEDEC LP REV3 W/ MTP | LEFT | 4200209234 | Q4 | 52 | 2020-12-21 | Ocean |  |  |  |  | 100042898
| JLP683 | JLP101 | 100042941 | PMY30893 | CR | 302009765 | JEDEC LP REV3 | left | 4200209244 | Q4 | 52 | 2020-12-23 | Air |  |  |  |  | 100042941
| JLP684 | JLP70155 | 100044559 | PMY31951 | CD | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200209864 | Q4 | 53 | 2020-12-28 | AIR |  |  | 2020-11-11 |  | 100044559
| JLP685 | JLP70154 | 100044561 | PMY32149 | CD | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200209865 | Q4 | 53 | 2020-12-28 | AIR |  |  | 2020-11-11 |  | 100044561
| JLP686 | JLP00232 | 100046218 |  | VN | 302009767 | JEDEC LP REV3 W/ FLIP AND IONIZER | Left | 4200210355 | Q4 | 53 | 2020-12-28
| JLP687 | JLP00231 | 100046219 |  | VN | 302009766 | JEDEC LP REV3 W/ FLIPPER | Right | 4200210355 | Q4 | 52 | 2020-12-28
| JLP688 | JLP00320 | 100042922 | PMY30897 | CH | 302009766 | JEDEC LP REV3 W/ FLIP | RIGHT | 4200209239 | Q1 | 2 | 2021-01-07 | Air |  |  |  |  | 100042922
| JLP689 | JLP00322 | 100043294 | PMY31037 | CH | 302027911 | JEDEC LP REV3 W/FLIP, MTP AND IONIZER | RIGHT | 4200209240 | Q1 | 2 | 2021-01-07 | Air |  |  |  |  | 100043294
| JLP690 | JLP00321 | 100042932 | PMY30898 | CH | 302009767 | JEDEC LP REV3 W/ FLIP AND IONIZER | LEFT | 4200209243 | Q1 | 2 | 2021-01-07 | Air |  |  |  |  | 100042932
| JLP691 | JLP50205 | 100042881 | PMY30899 | KM | 302009763 | JEDEC LP REV3 W/ MTP | RIGHT | 4200209229 | Q1 | 2 | 2021-01-07 | Air |  |  |  |  | 100042881
| JLP692 | JLP50206 | 100042885 | PMY30900 | KM | 302009764 | JEDEC LP REV3 W/ MTP AND IONIZER | Left | 4200209230 | Q1 | 2 | 2021-01-07 | Air |  |  |  |  | 100042885
| JLP693 | JLP31012 | 100044114 | PMY31690 | PG | 302009764 | JEDEC LP REV 3 W/ MTP AND IONIZER | Left | 4200209589 | Q1 | 3 | 2021-01-14 | AIR |  |  | 2020-11-09 |  | 100044114
| JLP694 | JLP31011 | 100044115 | PMY31723 | PG | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200209590 | Q1 | 3 | 2021-01-14 | AIR |  |  | 2020-11-09 |  | 100044115
| JLP695 | JLP10951 | 100044117 | PMY31748 | PG | 302009765 | JEDEC LP REV3 | Left | 4200209593 | Q1 | 3 | 2021-01-14 | AIR |  |  | 2020-11-09 |  | 100044117
| JLP696 | JLP70151 | 100044547 | PMY31953 | CD | 302009764 | JEDEC LP REV 3 W/ MTP AND IONIZER | Left | 4200209859 | Q1 | 3 | 2021-01-14 | AIR |  |  | 2020-11-11 |  | 100044547
| JLP697 | JLP70150 | 100044557 | PMY32150 | CD | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200209862 | Q1 | 3 | 2021-01-14 | AIR |  |  | 2020-11-11 |  | 100044557

## PnP PO (hidden)
PO date |  | Org. | PO | Line | Stockcode | Description | Quantity | New Request date | ww | PIMES Commit | Pick Up Date
2020-10-28 | 44 | M01 | PMY30142 | 1 | 8307700001 | PNP ASSY,X8-DPH INPUT/OUTPUT | 2 | 2020-12-04 | 49 | 2020-12-04 | 2020-12-01 | 49
2020-10-28 | 44 | M01 | PMY30142 | 2 | 8307700002 | PNP ASSY,X8-DPH TRANSFER | 1 | 2020-12-04 | 49 | 2020-12-04 | 2020-12-01 | 49
2020-11-18 | 47 | M01 | PMY33119 | 1 | 8307700001 | PNP ASSY,X8-DPH INPUT/OUTPUT | 2 | 2020-12-07 | 50 | 2020-12-07 | 2020-12-04 | 50
2020-11-18 | 47 | M01 | PMY33119 | 2 | 8307700002 | PNP ASSY,X8-DPH TRANSFER | 1 | 2020-12-07 | 50 | 2020-12-07 | 2020-12-04 | 50
2020-11-18 | 47 | M01 | PMY33129 | 1 | 8307700001 | PNP ASSY,X8-DPH INPUT/OUTPUT | 2 | 2020-12-09 | 50 | 2020-12-09 | 2020-12-06 | 50
2020-11-18 | 47 | M01 | PMY33129 | 2 | 8307700002 | PNP ASSY,X8-DPH TRANSFER | 1 | 2020-12-09 | 50 | 2020-12-09 | 2020-12-06 | 50
2020-11-18 | 47 | M01 | PMY33131 | 1 | 8307700001 | PNP ASSY,X8-DPH INPUT/OUTPUT | 2 | 2020-12-14 | 51 | 2020-12-14 | 2020-12-14 | 51
2020-11-18 | 47 | M01 | PMY33131 | 2 | 8307700002 | PNP ASSY,X8-DPH TRANSFER | 1 | 2020-12-14 | 51 | 2020-12-14 | 2020-12-14 | 51
2020-11-18 | 47 | M01 | PMY33135 | 1 | 8307700001 | PNP ASSY,X8-DPH INPUT/OUTPUT | 2 | 2020-12-16 | 51 | 2020-12-16 | 2020-12-14 | 51
2020-11-18 | 47 | M01 | PMY33135 | 2 | 8307700002 | PNP ASSY,X8-DPH TRANSFER | 1 | 2020-12-16 | 51 | 2020-12-16 | 2020-12-14 | 51
2020-11-18 | 47 | M01 | PMY33375 | 1 | 8307700001 | PNP ASSY,X8-DPH INPUT/OUTPUT | 2 | 2020-12-16 | 51 | 2020-12-23 | 2020-12-21 | 52
2020-11-18 | 47 | M01 | PMY33375 | 2 | 8307700002 | PNP ASSY,X8-DPH TRANSFER | 1 | 2020-12-16 | 51 | 2020-12-23 | 2020-12-21 | 52
2020-11-18 | 47 | M01 | PMY33418 | 1 | 8307700001 | PNP ASSY,X8-DPH INPUT/OUTPUT | 2 | 2020-12-17 | 51 | 2020-12-23 | 2020-12-21 | 52
2020-11-18 | 47 | M01 | PMY33418 | 2 | 8307700002 | PNP ASSY,X8-DPH TRANSFER | 1 | 2020-12-17 | 51 | 2020-12-23 | 2020-12-28 | 52
2020-11-21 | 47 | M01 | PMY33943 | 1 | 8307700001 | PNP ASSY,X8-DPH INPUT/OUTPUT | 5 | 2020-12-18 | 51 | 2020-12-28 | 2020-12-28 | 53
2020-11-21 | 47 | M01 | PMY33943 | 1 | 8307700001 | PNP ASSY,X8-DPH INPUT/OUTPUT | 4 | 2020-12-24 | 52 | 2020-01-07 | 2020-12-28 | 2
2020-11-21 | 47 | M01 | PMY33943 | 1 | 8307700001 | PNP ASSY,X8-DPH INPUT/OUTPUT | 4 | 2020-12-31 | 53 | 2020-01-07 | 2020-01-03 | 2
2020-11-21 | 47 | M01 | PMY33943 | 1 | 8307700001 | PNP ASSY,X8-DPH INPUT/OUTPUT | 2 | 2020-01-07 | 2 | 2020-01-14 | 2020-01-03 | 3
2020-11-21 | 47 | M01 | PMY33943 | 2 | 8307700002 | PNP ASSY,X8-DPH TRANSFER | 3 | 2020-12-18 | 51 | 2020-12-28 | 2020-12-28 | 53
2020-11-21 | 47 | M01 | PMY33943 | 2 | 8307700002 | PNP ASSY,X8-DPH TRANSFER | 3 | 2020-12-24 | 52 | 2020-01-07 | 2020-12-28 | 2
2020-11-21 | 47 | M01 | PMY33943 | 2 | 8307700002 | PNP ASSY,X8-DPH TRANSFER | 2 | 2020-12-31 | 53 | 2020-01-07 | 2020-01-03 | 2
2020-11-21 | 47 | M01 | PMY33943 | 2 | 8307700002 | PNP ASSY,X8-DPH TRANSFER | 1 | 2020-01-07 | 2 | 2020-01-14 | 2020-01-11 | 3
[7 empty] | 45 | 2020-11-23 | 48
33
Best Regards,
29
16
45
Formulas:
ww = WEEKNUM([New Request date])
Pick Up Date = [PIMES Commit]-3

## Sheet4 (hidden)
Unit Number | Entity | SO # | Cohu MY PO to PIMES | SITE | New Stock Code/Cofig | DESCRIPTION | Intel Requested Monitor Side | Intel PO# | MY Need date | P'IMES Commit as of Nov 17 | Status | Transit Mode | SN# | Cohu MY PO to PIMES | PO date | P.IMES Shipped Date | P.IMES Invoice
JTP | JTP502 JTP50201 | 100025330 | PMY16743 | KM | 302009770 | JTP #22 | Center | 4200205099 | 2020-11-20 | 2020-11-20 |  | AIR |  | PMY16743
JTP | JTP101 | 100037170 | PMY25734 | CR | 302009770 | JTP #23 | Center | 4200207278 | 2020-12-17 | 2020-12-17 |  | AIR
JTP | JTP10951 | 100044116 | PMY31689 | PG | 302009770 | JTP (#24) | Center | 4200209592 | 2021-02-11 | 2021-02-11 |  | AIR |  |  | 2020-11-09
JLP 659 | JLP50304 | 100025322 | PMY16689 | KM | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200205093 | 2020-11-23 | 2020-11-23 |  | AIR |  | PMY16689 |  |  | 100025322
JLP 658 | JLP50207 | 100025323 | PMY16693 | KM | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200205096 | 2020-11-23 | 2020-11-23 |  | AIR |  | PMY16693 |  |  | 100025323
JLP 657 | JLP50303 | 100025325 | PMY16744 | KM | 302009765 | JEDEC LP REV3 | Right | 4200205097 | 2020-11-23 | 2020-11-23 |  | AIR |  | PMY16744 |  |  | 100025325
JLP 656 | JLP00217 | 100038336 | PMY26512 | VN | 302009765 | JEDEC LP REV3 | Right | 4200207523 | 2020-11-24 | 2020-11-24 |  | OCEAN |  |  |  |  | 100038336
JLP 655 | JLP101b | 100038337 | PMY26513 | CR | 302009763 | JEDEC LP REV3 W/ MTP | LEFT | 4200207525 | 2020-11-27 | 2020-11-24 |  | AIR |  |  |  |  | 100038337
JLP 654 | JLP101a | 100038715 | PMY26632 | CR | 302009765 | JEDEC LP REV3 | Right | 4200207709 | 2020-11-27 | 2020-11-27 |  | AIR |  |  |  |  | 100038715
JLP 653 | JLP302 | 100038716 | PMY26514 | CR | 302009765 | JEDEC LP REV3 | Left | 4200207710 | 2020-11-27 | 2020-11-27 |  | AIR |  |  |  |  | 100038716
JLP 652 | JLP00218 | 100038718 | PMY26635 | VN | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200207711 | 2020-11-27 | 2020-11-27 |  | OCEAN |  |  |  |  | 100038718
JLP 651 | JLP301 | 100039100 | PMY27277 | CR | 302009765 | JEDEC LP REV3 | left | 4200207915 | 2020-11-27 | 2020-11-27 |  | AIR |  |  |  |  | 100039100
JLP 650 | JLP70149 | 100036888 | PMY25331 | CD | 302009767 | JEDEC LP REV3 W/ AIR KNIFE+ FLIPPER | Left | 4200207187 | 12/11/2020 12/01/20 | 2020-11-30 | request pull in | AIR |  |  |  |  | 100036888
JLP 649 | JLP70148 | 100036891 | PMY25332 | CD | 302009766 | JEDEC LP REV3 W/ FLIPPER | Right | 4200207189 | 12/11/2020 12/01/20 | 2020-11-30 | request pull in | AIR |  |  |  |  | 100036891
JLP 648 | JLP70153 | 100036877 | PMY25290 | CD | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200207185 | 2020-12-11 | 2020-12-11 |  | AIR |  |  |  |  | 100036877
JLP 647 | JLP70152 | 100036885 | PMY25732 | CD | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200207186 | 2020-12-11 | 2020-12-11 |  | AIR |  |  |  |  | 100036885
JLP 646 | JLP00314 | 100038528 | PMY26631 | CH | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200207596 | 2020-12-11 | 2020-12-11 |  | AIR |  |  |  |  | 100038528
JLP 645 | JLP00239 | 100042888 | PMY30883 | VN | 302009763 | JEDEC LP REV3 W/ MTP | LEFT | 4200209231 | 2020-12-11 | 2020-12-11 |  | Ocean |  |  |  |  | 100042888
JLP 644 | JLP00240 | 100042900 | PMY30884 | VN | 302009763 | JEDEC LP REV3 W/ MTP | RIGHT | 4200209236 | 2020-12-11 | 2020-12-11 |  | Ocean |  |  |  |  | 100042900
JLP 643 | JLP00219 | 100042894 | PMY30888 | VN | 302009765 | JEDEC LP REV3 | RIGHT | 4200209233 | 2020-12-15 | 2020-12-15 |  | Ocean |  |  |  |  | 100042894
JLP 642 | JLP101b | 100042930 | PMY30889 | CR | 302009763 | JEDEC LP REV3 W/ MTP | right | 4200209241 | 2020-12-15 | 2020-12-15 |  | Air |  |  |  |  | 100042930
JLP 641 | JLP101a | 100042908 | PMY30892 | CR | 302009763 | JEDEC LP REV3 W/ MTP | right | 4200209237 | 2020-12-15 | 2020-12-15 |  | Air |  |  |  |  | 100042908
JLP 640 | JLP00315 | 100038532 | PMY26520 | CH | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200207600 | 2020-12-17 | 2020-12-17 |  | AIR |  |  |  |  | 100038532
JLP 639 | JLP20202 | 100039626 | PMY27694 | PG | 302009767 | JEDEC LP REV3 W/ AIR KNIFE+ FLIPPER | Left | 4200207963 | 2020-12-17 | 2020-12-17 |  | AIR |  |  |  |  | 100039626
JLP 638 | JLP20201 | 100039630 | PMY27478 | PG | 302009766 | JEDEC LP REV3 W/ FLIPPER | Right | 4200207964 | 2020-12-17 | 2020-12-17 |  | AIR |  |  |  |  | 100039630
JLP 637 | JLP00241 | 100042889 | PMY30895 | VN | 302009763 | JEDEC LP REV3 W/ MTP | RIGHT | 4200209232 | 2020-12-28 | 2020-12-18 | request pull in 12/18 | Ocean |  |  |  |  | 100042889
JLP 636 | JLP00242 | 100042902 | PMY30896 | VN | 302009764 | JEDEC LP REV 3 W/ MTP AND IONIZER | LEFT | 4200209238 | 2020-12-28 | 2020-12-18 | request pull in 12/18 | Air |  |  |  |  | 100042902
JLP 635 | JLP00220 | 100042898 | PMY30894 | VN | 302009763 | JEDEC LP REV3 W/ MTP | LEFT | 4200209234 | 2020-12-21 | 2020-12-21 |  | Ocean |  |  |  |  | 100042898
JLP 634 | JLP101 | 100042941 | PMY30893 | CR | 302009765 | JEDEC LP REV3 | left | 4200209244 | 2020-12-23 | 2020-12-23 |  | Air |  |  |  |  | 100042941
JLP 633 | JLP70155 | 100044559 | PMY31951 | CD | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200209864 | 2020-12-28 | 2020-12-28 |  | AIR |  |  | 2020-11-11 |  | 100044559
JLP 632 | JLP70154 | 100044561 | PMY32149 | CD | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200209865 | 2020-12-28 | 2020-12-28 |  | AIR |  |  | 2020-11-11 |  | 100044561
JLP 631 | JLP00232 | 100046218 |  | VN | 302009767 | JEDEC LP REV3 W/ FLIP AND IONIZER | Left | 4200210355 | 2020-12-28 | 2020-12-28
JLP 630 | JLP00231 | 100046219 |  | VN | 302009766 | JEDEC LP REV3 W/ FLIPPER | Right | 4200210355 | 2020-12-28 | 2020-12-28
JLP 629 | JLP00320 | 100042922 | PMY30897 | CH | 302009766 | JEDEC LP REV3 W/ FLIP | RIGHT | 4200209239 | 2021-01-07 | 2021-01-07 |  | Air |  |  |  |  | 100042922
JLP 628 | JLP00322 | 100043294 | PMY31037 | CH | 302027911 | JEDEC LP REV3 W/FLIP, MTP AND IONIZER | RIGHT | 4200209240 | 2021-01-07 | 2021-01-07 |  | Air |  |  |  |  | 100043294
JLP 627 | JLP00321 | 100042932 | PMY30898 | CH | 302009767 | JEDEC LP REV3 W/ FLIP AND IONIZER | LEFT | 4200209243 | 2021-01-07 | 2021-01-07 |  | Air |  |  |  |  | 100042932
JLP 626 | JLP50205 | 100042881 | PMY30899 | KM | 302009763 | JEDEC LP REV3 W/ MTP | RIGHT | 4200209229 | 2021-01-07 | 2021-01-07 |  | Air |  |  |  |  | 100042881
JLP 625 | JLP50206 | 100042885 | PMY30900 | KM | 302009764 | JEDEC LP REV3 W/ MTP AND IONIZER | Left | 4200209230 | 2021-01-07 | 2021-01-07 |  | Air |  |  |  |  | 100042885
JLP 624 | JLP31012 | 100044114 | PMY31690 | PG | 302009764 | JEDEC LP REV 3 W/ MTP AND IONIZER | Left | 4200209589 | 2021-01-14 | 2021-01-14 |  | AIR |  |  | 2020-11-09 |  | 100044114
JLP 623 | JLP31011 | 100044115 | PMY31723 | PG | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200209590 | 2021-01-14 | 2021-01-14 |  | AIR |  |  | 2020-11-09 |  | 100044115
JLP 622 | JLP10951 | 100044117 | PMY31748 | PG | 302009765 | JEDEC LP REV3 | Left | 4200209593 | 2021-01-14 | 2021-01-14 |  | AIR |  |  | 2020-11-09 |  | 100044117
JLP 621 | JLP70151 | 100044547 | PMY31953 | CD | 302009764 | JEDEC LP REV 3 W/ MTP AND IONIZER | Left | 4200209859 | 2021-01-14 | 2021-01-14 |  | AIR |  |  | 2020-11-11 |  | 100044547
JLP 620 | JLP70150 | 100044557 | PMY32150 | CD | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200209862 | 2021-01-14 | 2021-01-14 |  | AIR |  |  | 2020-11-11 |  | 100044557

## budget (hidden)
Projects | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Total
Matrix 001 | 8 | 8 | 8 | 12 | 12 | 12 | 8 | 8 | 8 | 12 | 12 | 12 | 120
Matrix 002 | 4 | 4 | 4 | 6 | 6 | 6 | 4 | 4 | 4 | 6 | 6 | 6 | 60
JLP Main Assy | 13 | 13 | 14 | 13 | 13 | 14 | 17 | 17 | 16 | 17 | 17 | 16 | 180
Option - KIT,MANUAL TRAY PLATF,JLP G2 D | 11 | 11 | 10 | 11 | 11 | 10 | 13 | 13 | 14 | 13 | 13 | 14 | 144
Option - KIT, JLP AIR KNIFE OPTION F | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 2 | 3 | 3 | 1 | 27
Option - KIT,TRAY FLIP MECHANISM,JLP G2 C | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 9
Pyramid | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Eclipse XT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Eclipse XTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
JTP | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 8
OLB | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 10
Projects | Q1 | Q2 | Q3 | Q4 | Total
Matrix 001 | 24 | 36 | 24 | 36 | 120
Matrix 002 | 12 | 18 | 12 | 18 | 60
JLP Main Assy | 40 | 40 | 50 | 50 | 180
Option - KIT,MANUAL TRAY PLATF,JLP G2 D | 32 | 32 | 40 | 40 | 144
Option - KIT, JLP AIR KNIFE OPTION F | 6 | 6 | 8 | 7 | 27
Option - KIT,TRAY FLIP MECHANISM,JLP G2 C | 2 | 2 | 3 | 2 | 9
Pyramid | 0 | 0 | 0 | 1 | 1
Eclipse XT | 0 | 0 | 0 | 0 | 0
Eclipse XTA | 0 | 0 | 0 | 0 | 0
JTP | 2 | 2 | 2 | 2 | 8
OLB | 2 | 3 | 2 | 3 | 10

## SHIP PLAN (hidden)
SHIPMENT PLAN |  | WITH PO | WITH PO
as of Nov 5 |  | FORECAST | FORECAST | WK 40 | [6 empty] | WK 41 | [6 empty] | WK 42 | [6 empty] | WK 43 | [6 empty] | WK 44 | [6 empty] | WK 45 | [6 empty] | WK 46 | [6 empty] | WK 47 | [6 empty] | WK 48 | [6 empty] | WK 49 | [6 empty] | WK 50 | [6 empty] | WK 51
|  |  | SHIPPED | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | JAN 2021 |  |  |  | FEB 2021 |  |  |  | MAR 2021
PROJECT | CUSTOMER PN | SAP PN | DESCRIPTION | [84 empty] | WW01 | WW02 | WW03 | WW04 | WW05 | WW06 | WW07 | WW08 | WW09 | WW10 | WW11 | WW12 | time axis 2020-09-28 to 2020-12-20
OLB | 100006503 | LFCH-OB-100006503 | DELTA Test Handling Equipment Handler Machine Equipment | 2020-12-07: OLB 41 | [7 empty] | OLB 42 |  |  |  | OLB 43
JLP | 8337800001 | LFCH-JLP-8337800001 | JLP Gen 3, Main Assembly (8337800001) | 2020-10-06: JLP 643 JLP 644; 2020-10-15: JLP 645 JLP 646; 2020-10-29: JLP 647 JLP 648; 2020-10-31: JLP 649 JLP 650 JLP 651 JLP 652; 2020-11-08: JLP 653 JLP 654; 2020-11-16: JLP 657 JLP 658; 2020-11-21: JLP 662; 2020-11-23: JLP 659 JLP 660 JLP 661; 2020-11-27: JLP 663 JLP 664 JLP 665 JLP 666 JLP 667; 2020-11-30: JLP 670 JLP 671; 2020-12-11: JLP 668 JLP 669 JLP 672 JLP 673 JLP 674; 2020-12-17: JLP 673 JLP 674 JLP 675 | JLP 676 JLP 677 JLP 678 JLP 679 JLP 680 | JLP 681 JLP 682 JLP 683 JLP 684 JLP 685 | JLP 686 JLP 687 JLP 688 JLP 689 JLP 690 | JLP 691 JLP 692 JLP 693 JLP 694 JLP 695 | JLP 696 JLP 697 JLP 698 JLP 699 JLP 700 | JLP 701 JLP 702 JLP 703 JLP 704 JLP 705 | JLP 706 JLP 707 JLP 708 JLP 709 JLP 710 | JLP 711 JLP 712 JLP 713 JLP 714 JLP 715 | JLP 716 JLP 717 JLP 718 JLP 719 JLP 720 | JLP 721 JLP 722 JLP 723 JLP 724 JLP 725 | JLP 726 JLP 727 JLP 728 JLP 729 JLP 730 | JLP 731 JLP 732 JLP 733 JLP 734 JLP 735
MTP | 8332104901 | LFCH-JLP-MTPF4901 | Kit, Manual Tray Platf, JLP G2 (8332104901) | 2020-10-06: 2; 2020-10-15: 2; 2020-10-29: 2; 2020-11-08: 2; 2020-11-16: 2; 2020-11-23: 2; 2020-11-27: 1; 2020-12-11: 3; 2020-12-17: 2
IONIZER | 8335499901 | LFCH-JLP-8335499901 | Kit, JLP Air Knife Option (8335499901) | 2020-10-15: 1; 2020-10-29: 1; 2020-11-16: 1; 2020-12-11: 1; 2020-12-17: 3
FLIPPER | 8333454901 | LFCH-JLP-8333454901 | Kit Tray Flip Mechanism (8333454901) | 2020-12-11: 2; 2020-12-17: 4
JTP | 8330201001 | LFCH-JT-8330201001 | DELTA Test Handling Equipment Handler Machine Equipment | 2020-11-20: JTP 22; 2020-12-17: JTP 23 | [7 empty] | JTP 24
XT | 8334633901 | LFCH-EC-8334633901 | X1-X16 TS No Contactor (D2006066) (8334633901)
XTA | 100004565 | LFCH-EC-100004565 | XTA X1-X16 TS No Contactor (100004565)
PNP I/O | 8307700001 | LFCH-MX-8307700001 | PNP Assy, X8-DPH Input/Output U (8307700001) | 2020-09-28: 2; 2020-10-05: 2; 2020-10-09: 2; 2020-10-23: 4; 2020-10-28: 2; 2020-11-03: Batch 004 PMY27721; 2020-11-06: Batch 005 PMY28035; 2020-11-13: Batch 006 PMY28161; 2020-11-16: Batch 006 PMY28168; 2020-11-30: Batch 007 & 008 PMY30142 | BATCH 013 BATCH 014 | BATCH 015 BATCH 016 | BATCH 017 BATCH 018 | BATCH 019 BATCH 020 | BATCH 021 BATCH 022 | BATCH 023 BATCH 024 | BATCH 024 BATCH 025 | BATCH 026 BATCH 027 | BATCH 028 BATCH 029 | BATCH 030 BATCH 031 | BATCH 032 BATCH 033 | BATCH 034 BATCH 035
|  |  |  | 2020-10-28: Batch 003; 2020-11-03: 2; 2020-11-06: 2; 2020-11-13: 2; 2020-11-16: 2; 2020-11-30: 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PNP T | 8307700002 | LFCH-MX-8307700002 | PNP Assy, X8-DPH Transfer U (8307700002) | 2020-09-28: 1; 2020-10-05: 1; 2020-10-09: 1; 2020-10-23: 2; 2020-10-28: 1; 2020-11-03: Batch 004 PMY27721; 2020-11-06: Batch 005 PMY28035; 2020-11-13: Batch 006 PMY28161; 2020-11-16: Batch 006 PMY28168; 2020-11-30: Batch 007 & 008 PMY30142 | BATCH 013 BATCH 014 | BATCH 015 BATCH 016 | BATCH 017 BATCH 018 | BATCH 019 BATCH 020 | BATCH 021 BATCH 022 | BATCH 023 BATCH 024 | BATCH 024 BATCH 025 | BATCH 026 BATCH 027 | BATCH 028 BATCH 029 | BATCH 030 BATCH 031 | BATCH 032 BATCH 033 | BATCH 034 BATCH 035
PYRAMID | 1975022001 | LFCH-PYIO-1975022001 | PNP Assy, X8-DPH Input/Output U (8307700001)
Batch 003

## fORECAST (hidden)
PRODUCT | Q1 |  |  | Q1 TTL | Q2 |  |  | Q2 TTL | Q3 |  |  | Q3 TTL | Q4 |  |  | Q4 TTL | Total | REMARKS
| DEC | JAN | FEB |  | MAR | APR | MAY |  | JUN | JUL | AUG |  | SEPT | OCT | NOV
JLP | 17 | 15 | 7 | 39 | 15 | 15 | 15 | 45 | 20 | 20 | 20 | 60 | 20 | 20 | 20 | 60 | 204 | X5 PER WEEK
PnP | 36 | 24 | 51 | 111 | 72 | 96 | 96 | 264 | 48 | 48 | 24 | 120 | 24 | 24 | 24 | 72 | 567 | Jan -x15/wk,Feb-to March x18/wk, April-May - x24/wk, Jun-July -x12/wk,Aug -onwards ,x6 /wk
JTP | 1 | 0 | 1 | 2 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 5 | x1 per Quarter
OLB | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 1 | 0 | 1 | 2 | 1 | 0 | 1 | 2 | 6 | x2 per quarter
XT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PYR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ACTUAL
W/PO
FORECAST

## Sheet6 (hidden)
PRODUCT | Q1 |  |  | Q1 TTL | Q2 |  |  | Q2 TTL | Q3 |  |  | Q3 TTL | Q4 |  |  | Q4 TTL | Total | REMARKS
| DEC | JAN | FEB |  | MAR | APR | MAY |  | JUN | JUL | AUG |  | SEPT | OCT | NOV
JLP | 17 | 15 | 7 | 39 | 15 | 15 | 15 | 45 | 20 | 20 | 20 | 60 | 20 | 20 | 20 | 60 | 204 | X5 PER WEEK
PnP | 36 | 24 | 51 | 111 | 72 | 96 | 96 | 264 | 48 | 48 | 24 | 120 | 24 | 24 | 24 | 72 | 567 | Jan -x15/wk,Feb-to March x18/wk, April-May - x24/wk, Jun-July -x12/wk,Aug -onwards ,x6 /wk
JTP | 1 | 0 | 1 | 2 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 5 | x1 per Quarter
OLB | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 1 | 0 | 1 | 2 | 1 | 0 | 1 | 2 | 6 | x2 per quarter
XT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PYR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ACTUAL
W/PO
FORECAST

## Feb 25 Slot Plan (hidden)
Entity | SO # | Cohu MY PO to PIMES | SITE | New Stock Code/Cofig | DESCRIPTION | Intel Requested Monitor Side | Intel PO# | Intel PO RCV Date | MY New Date | Pick Up Date | Transit Mode | Status
JLP101b | 100056031 | PMY42262 | KM | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200212363 | 2020-12-30 | 2021-03-04 | 2021-03-04 | OCEAN
JLP101a | 100056032 | PMY41792 | KM | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200212364 | 2020-12-30 | 2021-03-04 | 2021-03-04 | OCEAN
JLP00005 | 100050818 | PMY37036 | CR | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200211196 | 2020-12-03 | 2021-03-12 | 2021-03-12 | AIR
JLP00004 | 100050822 | PMY37113 | CR | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200211198 | 2020-12-03 | 2021-03-12 | 2021-03-12 | AIR
JLP00006 | 100050859 | PMY37123 | CR | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200211204 | 2020-12-03 | 2021-03-12 | 2021-03-12 | AIR
JLP00003 | 100050861 | PMY37124 | CR | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200211205 | 2020-12-03 | 2021-03-12 | 2021-03-12 | AIR
JLP00323 | 100049940 | PMY35971 | CH | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200210896 | 2020-11-30 | 2021-03-18 | 2021-03-18 | AIR
JLP00324 | 100049949 | PMY35972 | CH | 302009764 | JEDEC LP REV3 W/ MTP AND IONIZER | Left | 4200210898 | 2020-11-30 | 2021-03-18 | 2021-03-18 | AIR
JLP00329 | 100064697 | PMY48817 | CH | 302009763 | JEDEC LP REV3 W/ MTP | TBD | 4200213925 | 2021-02-09 | 2021-03-18 | 2021-03-18 | AIR
JLP00034 | 100065057 | PMY48907 | CR | 302009764 | JEDEC LP REV3 W/ MTP AND IONIZER | Left | 4200214017 | 2021-02-10 | 2021-03-18 | 2021-03-18 | OCEAN
JLP00033 | 100065072 | PMY48818 | CR | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200214020 | 2021-02-10 | 2021-03-18 | 2021-03-18 | OCEAN
JLP00038 | 100065064 | PMY48821 | CR | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200214018 | 2021-02-10 | 2021-03-18 | 2021-03-18 | OCEAN
JLP00039 | 100065073 | PMY48822 | CR | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200214021 | 2021-02-10 | 2021-03-18 | 2021-03-18 | OCEAN
JLP00216 | 100064044 | PMY48122 | VN | 302009764 | JEDEC LP REV3 W/ MTP AND IONIZER | Left | 4200213871 | 2021-02-05 | 2021-03-19 | 2021-03-19 | AIR
JLP00215 | 100064048 | PMY48126 | VN | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200213872 | 2021-02-05 | 2021-03-19 | 2021-03-19 | AIR
JLP00233 | 100064052 | PMY48127 | VN | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200213873 | 2021-02-05 | 2021-03-25 | 2021-03-25 | AIR
JLP00234 | 100064057 | PMY48133 | VN | 302009764 | JEDEC LP REV3 W/ MTP AND IONIZER | Left | 4200213875 | 2021-02-05 | 2021-03-25 | 2021-03-25 | AIR
JLP00035 | 100066181 | PMY49743 | CR | 302009765 | JEDEC LP REV3 | Left | 4200214387 | 2021-02-16 | 2021-03-25 | 2021-03-25 | AIR
JLP00026 | 100066182 | PMY49744 | CR | 302009767 | JEDEC LP REV3 W/ IONIZER AND FLIPPER | Left | 4200214388 | 2021-02-16 | 2021-03-25 | 2021-03-25 | AIR
JLP00025 | 100066183 | PMY49745 | CR | 302009768 | JEDEC LP REV3 W/ MTP AND FLIPPER | Right | 4200214389 | 2021-02-16 | 2021-03-25 | 2021-03-25 | AIR
JLP00263 | 100064054 | PMY48139 | VN | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200213874 | 2021-02-05 | 2021-04-12 | 2021-04-12 | AIR
JLP00326 | 100053599 | PMY39380 | CH | 302009763 | JEDEC LP REV3 W/ MTP | Right | 4200211737 | 2020-12-16 | 2021-05-20 | 2021-05-20 | AIR
JLP00325 | 100053601 | PMY39381 | CH | 302009763 | JEDEC LP REV3 W/ MTP | Left | 4200211738 | 2020-12-16 | 2021-05-20 | 2021-05-20 | AIR
JLP00332 | 100065630 | PMY49043 | CH | 302009763 | JEDEC LP REV3 W/ MTP | TBD | 4200214261 | 2021-02-12 | 2021-06-11 | 2021-06-11 | AIR
JLP00333 | 100065632 | PMY49071 | CH | 302009764 | JEDEC LP REV3 W/ MTP AND IONIZER | TBD | 4200214263 | 2021-02-12 | 2021-06-11 | 2021-06-11 | AIR
JLP00334 | 100065631 | PMY49072 | CH | 302009763 | JEDEC LP REV3 W/ MTP | TBD | 4200214262 | 2021-02-12 | 2021-08-13 | 2021-08-13 | AIR
JLP00335 | 100065629 | PMY49073 | CH | 302009764 | JEDEC LP REV3 W/ MTP AND IONIZER | TBD | 4200214260 | 2021-02-12 | 2021-08-13 | 2021-08-13 | AIR

## Summary of Open PO (hidden)
2021-03-19
PRODUCT | ACTUAL SHIPMENT | [29 empty] | OPEN PO | [12 empty] | TTL OPEN PO | YTD SHIPMENT | YTD SHIPMENT | Materials
| TTL DEC | 2021-01-09 | 2021-01-11 | 2021-01-13 | 2021-01-16 | 2021-01-18 | 2021-01-21 | 2021-01-28 | 2021-01-30 | TTL JAN | 2021-02-01 | 2021-02-05 | 2021-02-11 | 2021-02-12 | 2021-02-18 | 2021-02-24 | 2021-02-27 | TTL FEB | 2021-03-01 | 2021-03-04 | 2021-03-09 | 2021-03-11 | 2021-03-12 | 2021-03-13 | 2021-03-18 | 2021-03-17 | 2021-03-19 | 2021-03-20 | 2021-03-23 | TTL March as of 3/23 | MAR Target | Mar Balance | APR | MAY | JUNE | JULY | AUG | SEP | OCT | NOV | SEP | OCT | NOV |  | YTD SHIPMENT | MTD Shipment
JLP | 17 |  |  | 4 | 3 |  | 2 | 4 | 2 | 15 |  |  |  | 3 |  |  | 4 | 7 |  | 2 |  |  | 4 |  | 9 |  |  | 3 | 2 | 20 | 20 | 0 | 9 | 7 | 2 | 0 | 4 | 4 |  | 2 | 0 | 0 | 0 | 28 | 59 |  | Kaman - from 8 weeks -RM from ABB | 14 |  | PMY26515 | 2020-10-31 | SHIP | 18
FLIPPER | 4 |  |  |  | 3 |  |  | 0 |  | 3 | [7 empty] | 0 | [9 empty] | 2 |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 9 |  | No Risk | 7 | shipped | PMY26516 | 2020-10-31 | SHIP | 2
MTP | 12 |  |  | 2 | 1 |  | 2 | 4 | 1 | 12 |  |  |  | 2 |  |  | 4 | 6 |  | 2 |  |  | 4 |  | 9 |  |  | 1 |  | 16 | 18 | 2 | 7 | 5 | 2 | 0 | 4 | 4 |  | 2 | 0 | 0 | 0 | 26 | 46 |  | No Risk | 3 | Open PO | PMY25331 | 2020-12-11 | SHIP | 11
IONIZER | 3 |  |  | 2 | 2 |  | 1 | 2 |  | 7 |  |  | 1 |  |  |  | 1 | 2 | [6 empty] | 3 |  |  | 1 |  | 4 | 5 | 1 | 2 | 1 | 1 | 0 | 2 | 2 |  | 1 | 0 | 0 | 0 | 10 | 16 |  | Clayton Control -Cohu Manage |  |  | PMY25332 | 2020-12-11 | SHIP | 2
JTP | 1 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 1 |  |  |  |  | 1 | [5 empty] | 1 | [5 empty] | 1 | 1 | 0 | 2 | 0 | 2 | 0 | 0 |  |  |  | 0 | 0 | 0 | 4 | 3 |  | No Risk |  |  | PMY27694 | 2020-12-17 | SHIP | 1
OLB | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [7 empty] | 0 | [11 empty] | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 1 | 0 |  |  | 4 | balance | PMY27478 | 2020-12-17 | SHIP | 0
PNP I/O | 24 | 2 | 2 | 6 |  | 6 |  |  |  | 16 | 6 | 6 | 6 |  | 7 | 7 | 2 | 34 |  | 5 | 3 |  |  |  | 3 |  | 2 |  |  | 13 | 29 | 16 | 86 | 40 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 142 | 87 |  | Spline |  |  | PMY32947 | 2020-12-28 | SHIP | 15
PNP T | 12 | 2 |  | 3 |  | 3 |  |  |  | 8 | 3 | 3 | 3 |  | 4 | 3 | 1 | 17 | 4 | 5 | 3 | 5 |  |  | 2 | 4 |  |  |  | 23 | 29 | 6 | 59 | 32 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 97 | 60 |  | Spline |  |  | PMY30897 | 2020-01-13 |  | 9
XT/XTA | 0 | [8 empty] | 0 | [7 empty] | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | PMY31037 | 2020-01-13
[50 empty] | PMY30898 | 2020-01-13
[32 empty] | 102 | 24 | 38 | 40 | 32 | 8 | 142 | [14 empty] | 173.75
[32 empty] | 65 | 1 | 24 | 40 | 32 |  | 97
[33 empty] | apr | apr | apr | MAY | MAY

## CONFIG (hidden)
JLP Config |  |  | JTP Config |  |  |  | OLB Config
Set | Stock Code | Description | Set | Stock Code | Description |  | Set | Stock Code | Description
CFG | 302009763 | JLP CONFIG 1 MAN TRY | 1 | 302009770 | JTP CONFIG 1 TRAY PLATN |  | 1 | 302009772 | OLB2 CONFIG 1
1 | 8337800001 | JLP GEN 3, MAIN ASSEMBLY |  | 8330201001 | JTP-MAIN ASSEMBLY |  |  | 100006503 | OLB2 SYSTEM
| 8338390001 | LOADPORT, CRATE JLP |  | 8352955001 | TRAY PLATEN QD, JTP-222052 |  |  | 100006504 | AUTO BLP, OLB2
| 8332104901 | KIT,MANUAL TRAY PLATF,JLP G2 | [5 empty] | 100006511 | OLB2 IN HOUSE UPGRADE KIT
CFG | 302009764 | JLP CONFIG 2 MAN TRY, AIR KNF
2 | Stock Code | JLP GEN 3, MAIN ASSEMBLY
| 8338390001 | LOADPORT, CRATE JLP
| 8335499901 | KIT, JLP AIR KNIFE OPTION
| 8332104901 | KIT,MANUAL TRAY PLATF,JLP G2
CFG | 302009765 | JLP CONFIG 3 MAIN, LDPT CRT
3 | 8337800001 | JLP GEN 3, MAIN ASSEMBLY
| 8338390001 | LOADPORT, CRATE JLP
CFG | 302009766 | JLP CONFIG 4 TRY FLP
4 | 8337800001 | JLP GEN 3, MAIN ASSEMBLY
| 8333454901 | KIT,TRAY FLIP MECHANISM,JLP G2
| 8338390001 | LOADPORT, CRATE JLP
CFG | 302009767 | JLP CONFIG 5 TRY FLP, AIR KNF
5 | 8337800001 | JLP GEN 3, MAIN ASSEMBLY
| 8333454901 | KIT,TRAY FLIP MECHANISM,JLP G2
| 8338390001 | LOADPORT, CRATE JLP
| 8335499901 | KIT, JLP AIR KNIFE OPTION
CFG | 302009768 | JLP CONFIG 6 MAN, TRY FLP
6 | 8337800001 | JLP GEN 3, MAIN ASSEMBLY
| 8333454901 | KIT,TRAY FLIP MECHANISM,JLP G2
| 8338390001 | LOADPORT, CRATE JLP
| 8332104901 | KIT,MANUAL TRAY PLATF,JLP G2
CFG | 302009769 | JLP CONFIG 7 AIR KNF
7 | 8337800001 | JLP GEN 3, MAIN ASSEMBLY
| 8338390001 | LOADPORT, CRATE JLP
| 8335499901 | KIT, JLP AIR KNIFE OPTION
CFG | 302027911 | JLP CONFIG 8 TRY FLP, AIR KNF, MAN TR | 57558.54 | 57558.54 |  | Difference
8 | 8337800001 | JLP GEN 3, MAIN ASSEMBLY | 37864.35 | 37864.35 | 41925.29 | 4060.94
| 8338390001 | LOADPORT, CRATE JLP | 781.92 | 781.92
| 8333454901 | KIT,TRAY FLIP MECHANISM,JLP G2 | 15410.01 | 15410.01
| 8332104901 | KIT,MANUAL TRAY PLATF,JLP G2 | 1806.12 | 1806.12
| 8335499901 | KIT, JLP AIR KNIFE OPTION | 1696.14 | 1696.14

## Sheet1 (hidden)
Legend
Completed
On-going
Goal
PRODUCTION PLAN
PROJECT | WK 24 | [6 empty] | WK 25 | [6 empty] | WK 26
| MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN
| 2019-06-10 | 2019-06-11 | 2019-06-12 | 2019-06-13 | 2019-06-14 | 2019-06-15 | 2019-06-16 | 2019-06-17 | 2019-06-18 | 2019-06-19 | 2019-06-20 | 2019-06-21 | 2019-06-22 | 2019-06-23 | 2019-06-24 | 2019-06-25 | 2019-06-26 | 2019-06-27 | 2019-06-28 | 2019-06-29 | 2019-06-30
JLP | 2019-06-10: JLP 481-485; 2019-06-13: JLP 486-490; 2019-06-20: JLP 491 -495; 2019-06-27: JLP 496 -500
OLB | 2019-06-10: OLB#24; 2019-06-17: OLB#25; 2019-06-24: OLB#26
XT | 2019-06-10: XT#60; 2019-06-17: XT#61; 2019-06-24: XT#62

## Sheet2 (hidden)
PIMES JLP No | Entity | SO # | Cohu MY PO to PIMES | SITE | DESCRIPTION | Intel Requested Monitor Side | Intel PO# | Q3 | Cohu MY NEED DATE | MY WW | PIMES WW Commit | PIMES Commit | KWE PICK-UP DATE | actual Ship | Intel Approved Ship date | Transit Mode
2019-06-18
475 | JLP013b | 285872 | 56266 | KM | JEDEC LP REV3 W/ MTP | Right | 4200182245 | Q3 | 2019-05-23 | 21 | 29 | 2019-07-18 |  | FG | 2019-10-27 | OCEAN
476 | JLP013a | 285874 | 56269 | KM | JEDEC LP REV3 W/ MTP | Left | 4200182246 | Q3 | 2019-05-23 | 21 | 29 | 2019-07-18 |  | FG | 2019-10-27 | OCEAN
490 | JLP20332 | 286107 | 56724 | PG | JEDEC LP REV3 W/ MTP | Right | 4200182843 | Q3 | 2019-06-13 | 24 | 29 | 2019-07-18 |  | FG | 2019-10-27 | OCEAN
492 | JLP40561 | 286373 | 56959 | PG | JEDEC LP REV3 | Right | 4200183268 | Q3 | 2019-06-20 | 25 | 29 | 2019-07-18 |  | FG | 2019-10-23 | OCEAN
491 | JLP20331 | 286108 | 56725 | PG | JEDEC LP REV3 W/ MTP | Left | 4200182845 | Q3 | 2019-06-13 | 24 | 29 | 2019-07-18 |  | FG | 2019-10-27 | OCEAN
493 | JLP40562 | 286375 | 56989 | PG | JEDEC LP REV3 W/ MTP | Left | 4200183269 | Q3 | 2019-06-20 | 25 | 30 | 2019-07-23 |  | FG | 2019-10-21 | OCEAN
500 | JLP00106 | 288027 | 61291 | VN | JEDEC LP REV3 W/ FLIP + AIR KNIFE | Left | 4200185799 | Q3 | 2019-08-02 | 31 | 30 | 2019-07-25 |  | FG | 2019-09-22 | OCEAN
501 | JLP00105 | 288028 | 61107 | VN | JEDEC LP REV3 W/ FLIP | Right | 4200185800 | Q3 | 2019-08-02 | 31 | 30 | 2019-07-25 |  | FG | 2019-09-22 | OCEAN
502 | JLP21501 | 288490 | 62079 | PG | JEDEC LP REV3 W/ FLIP | Left | 4200186211 | Q3 | 2019-08-08 | 32 | 32 | 2019-08-08 |  | FG | 2019-09-19 | AIR
503 | JLP21502 | 288491 | 62121 | PG | JEDEC LP REV3 W/ FLIP | Right | 4200186212 | Q3 | 2019-08-08 | 32 | 32 | 2019-08-08 |  | FG | 2019-09-19 | AIR
504 | JLP81001 | 288488 | 62015 | PG | JEDEC LP REV3 W/ MTP | Right | 4200186205 | Q3 | 2019-08-08 | 32 | 32 | 2019-08-08 |  | FG | 2019-10-01 | OCEAN
505 | JLP81002 | 288489 | 62052 | PG | JEDEC LP REV3 W/ MTP + AIR KNIFE | Left | 4200186206 | Q3 | 2019-08-08 | 32 | 32 | 2019-08-08 |  | FG | 2019-10-01 | OCEAN
506 | JLP00108 | 288821 | 62566 | VN | JEDEC LP REV3 W/ MTP | Left | 4200186835 | Q3 | 2019-08-15 | 33 | 34 | 2019-08-22 | 2019-09-05 | FG | 2019-09-08 | AIR
507 | JLP00107 | 288822 | 62576 | VN | JEDEC LP REV3 | Right | 4200186836 | Q3 | 2019-08-15 | 33 | 34 | 2019-08-22 | 2019-09-05 | FG | 2019-09-08 | AIR

## Sheet5 (hidden)
PO No | (Multiple Items)
Row Labels | Item/Service Description | Sum of Remaining Open Quantity
ARPCBF850-OB53627001 | Cable Assy Motor Conveyor (1953627001) | 1
LFCH-EC-100004565 | XTA X1-X16 TS No Contactor (100004565) | 8
LFCH-EC-8334633901 | X1-X16 TS No Contactor (D2006066) (8334633901) | 1
LFCH-JLP-8335499901 | Kit, JLP Air Knife Option (8335499901) | 1
LFCH-JLP-8337800001 | JLP Gen 3, Main Assembly (8337800001) | 8
LFCH-JLP-MTPF4901 | Kit, Manual Tray Platf, JLP G2 (8332104901) | 7
LFCH-MX-8307700001 | PNP Assy, X8-DPH Input/Output U (8307700001) | 15
LFCH-MX-8307700002 | PNP Assy, X8-DPH Transfer U (8307700002) | 9
LFCH-SP-100065652 | Assy, Bracket Leoni, Rear, XT (100065652) | 2
LFCH-SP-1952309002 | CSM Support Finger Assy (1952309002) | 3
SOPPBX069 | Loadport, Crate JLP, (Crating Cost) (8338390001) | 8
Grand Total |  | 63