## Sheet1
System Proposal | Activities | PIC | Dependencies | Status | Feb. 2023 | Mar. 2023 | Apr. 2023 | May. 2023 | June.2023 | Remarks
PRODUCTION PPMS PORTAL (JLP) | Analyze the problem | Programmer | Sir. Grignon | CLOSED | [5 empty] | Closed - Nov '22
| Design the program | Programmer | - | CLOSED | [5 empty] | Closed - Nov '22
| Code the program | Programmer | - | CLOSED | [5 empty] | Closed -Dec '22
| Debug the program | Programmer | - | CLOSED | [5 empty] | Closed - Jan '23
| Formalize the solution | Programmer | - | CLOSED | [5 empty] | Closed - Jan '23
| Documentation and maintain the program,dry run and debugging | Programmer | - | CLOSED | [5 empty] | Started - Jan '23
| Full Implementation | Programmer | Production | CLOSED | [5 empty] | DONE
System Proposal | Activities | PIC | Dependencies | Status | April. 2023 | May. 2023 | June. 2023 | July. 2023 | Aug.2023 | Remarks
PRODUCTION PPMS PORTAL (PNP) | Analyze the problem | Programmer | Production | CLOSED | [5 empty] | Closed -April '23
| Design the program | Programmer | - | CLOSED | [5 empty] | Closed - May'23
| Code the program | Programmer | - | ON-GOING | [5 empty] | Started -May '23
| Debug the program | Programmer | - | ON-GOING | [5 empty] | Started -June '23
| Formalize the solution | Programmer | - | ON-GOING | [5 empty] | data validation from users input
| Documentation and maintain the program,dry run and debugging | Programmer | - | ON-GOING (75%) | [5 empty] | ongoing PNP FVI,monitoring and validating data's in PNP for reports, additional functions
| Full Implementation | Programmer | Production | OPEN
System Proposal | Activities | PIC | Dependencies | Status | Sept. 2023 | Oct. 2023 | Nov. 2023 | Remarks
ATS PPIC PORTAL | Analyze the problem | Dev | PPIC | OPEN
| Design the program | Dev | PPIC | OPEN
| Code the program | Dev | - | OPEN
| Debug the program | Dev | - | OPEN
| Formalize the solution | Dev | - | OPEN
| Documentation and maintain the program,dry run and debugging | Dev | - | OPEN
| Full Implementation | Dev | PPIC | OPEN